## Sheet1
No. | Funding Programme | LA | Scheme/Project Name | No. of Units | Approved Housing Body | Stage 1 Capital Appraisal | Stage 2 Pre Planning | Stage 3 Pre Tender design | Stage 4 Tender Report or Final Turnkey/CALF approval | On Site | Completed
1 | SHIP CONSTRUCTION TURNKEY | Carlow | Carrigbrook, Tullow Road, Carlow | 16 | *N/A | [5 empty] | Q4-2021
2 | SHIP CONSTRUCTION TURNKEY | Carlow | Carrigbrook, Tullow Road, Carlow | 13 | *N/A | [5 empty] | Q2-2021
3 | SHIP CONSTRUCTION TURNKEY | Carlow | Granville Court, Granby Row,Carlow | 4 | *N/A | [5 empty] | Q4-2021
4 | SHIP CONSTRUCTION TURNKEY | Carlow | Millrace, Carlow | 10 | *N/A | [5 empty] | Q4-2023
5 | SHIP CONSTRUCTION TURNKEY | Carlow | Thomas Traynor Road, Tullow, Carlow | 10 | *N/A |  |  |  |  | Q3-2023
6 | SHIP CONSTRUCTION TURNKEY | Carlow | Thomas Traynor Road, Tullow, Carlow | 11 | *N/A |  |  |  |  | Q3-2023
7 | SHIP CONSTRUCTION TURNKEY | Carlow | Laraghbeg, Ballon | 5 | *N/A | [5 empty] | Q4-2023
8 | SHIP CONSTRUCTION SINGLE STAGE | Carlow | Brownbog, Hacketstown | 1 | *N/A | [5 empty] | Q4-2022
9 | SHIP CONSTRUCTION SINGLE STAGE | Carlow | St. Mary’s Court, Carlow | 4 | *N/A | [5 empty] | Q4-2022
10 | SHIP CONSTRUCTION SINGLE STAGE | Carlow | Drumphea, Garryhill, Bagenalstown | 1 | *N/A | [5 empty] | Q1-2023
11 | SHIP CONSTRUCTION SINGLE STAGE | Carlow | Constable Hill, Hackettstown | 1 | *N/A | [5 empty] | Q4-2023
12 | SHIP CONSTRUCTION SINGLE STAGE | Carlow | Old Leighlin Road, Carlow | 1 | *N/A | [5 empty] | Q4-2023
13 | SHIP CONSTRUCTION SINGLE STAGE | Carlow | Lackabeg, Kildavin | 3 | *N/A | [5 empty] | Q3-2023
14 | SHIP CONSTRUCTION SINGLE STAGE | Carlow | Bahana, Glynn | 5 | *N/A | [5 empty] | Q3-2023
15 | SHIP CONSTRUCTION SINGLE STAGE | Carlow | Upper Main Street, Borris, Co. Carlow | 2 | *N/A |  |  |  |  | Q2-2024
16 | SHIP CONSTRUCTION SINGLE STAGE | Carlow | The Bungalow, Ballinkillbeg | 1 | *N/A |  |  |  |  | Q4-2023
17 | SHIP CONSTRUCTION SINGLE STAGE | Carlow | Main Street, Myshall | 2 | *N/A |  |  |  |  | Q4-2023
18 | SHIP CONSTRUCTION SINGLE STAGE | Carlow | Bilboa, Co, Carlow | 3 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
19 | SHIP CONSTRUCTION RENEWAL | Carlow | Barrack Street, Carlow | 8 | *N/A |  |  |  |  | Q3-2024
20 | SHIP CONSTRUCTION RENEWAL | Carlow | Bog Lane, Borris | 1 | *N/A | [5 empty] | Q2-2022
21 | SHIP CONSTRUCTION RENEWAL | Carlow | 2a Chapel Street, Graiguecullen | 1 | *N/A | [5 empty] | Q2-2023
22 | SHIP CONSTRUCTION RENEWAL | Carlow | 24 Church Street, Graiguecullen | 1 | *N/A | [5 empty] | Q2-2023
23 | SHIP CONSTRUCTION RENEWAL | Carlow | Breens Shop Units, Main Street, Borris | 2 | *N/A | [5 empty] | Q3-2024
24 | SHIP CONSTRUCTION RENEWAL | Carlow | 41-42 Dublin Street & Cox's Lane, Carlow | 12 | *N/A |  |  |  |  | Q4-2023
25 | SHIP CONSTRUCTION RENEWAL | Carlow | 22a Burrin Street, Carlow | 1 | *N/A | [5 empty] | Q4-2023
26 | SHIP CONSTRUCTION RENEWAL | Carlow | Limegrove, Palatine, Carlow | 4 | *N/A | [5 empty] | Q4-2023
27 | SHIP CONSTRUCTION RENEWAL | Carlow | 11 Bourlum Wood, Green Road, Co. Carlow | 1 | *N/A | [5 empty] | Q4-2022
28 | SHIP CONSTRUCTION RENEWAL | Carlow | Haymarket | 2 | *N/A |  |  |  |  | Q4-2023
29 | SHIP CONSTRUCTION RENEWAL | Carlow | 25 Staplestown Road, Carlow Town | 1 | *N/A |  |  |  |  | Q4-2023
30 | SHIP CONSTRUCTION RENEWAL | Carlow | 15,16 Dublin Street, Carlow | 2 | *N/A |  |  |  |  | Q4-2023
31 | SHIP CONSTRUCTION RENEWAL | Carlow | Corries, Bagenalstown | 1 | *N/A | [5 empty] | Q4-2023
32 | SHIP CONSTRUCTION RENEWAL | Carlow | 1 St. Olivers Park, Myshall, Co. Carlow | 2 | *N/A |  |  |  |  | Q2-2024
33 | SHIP CONSTRUCTION RENEWAL | Carlow | Springdale, Tullow Road, Carlow | 1 | *N/A | [5 empty] | Q3-2024
34 | SHIP CONSTRUCTION RENEWAL | Carlow | 21 Burrin Street, Carlow | 1 | *N/A |  |  |  |  | Q3-2024
35 | SHIP CONSTRUCTION RENEWAL | Carlow | 14 Woodlawn, Borris | 1 | *N/A |  |  |  |  | Q3-2024
36 | SHIP CONSTRUCTION | Carlow | Pound Lane, Borris | 9 | *N/A | [5 empty] | Q2-2021
37 | SHIP CONSTRUCTION | Carlow | Gleann na Bearu, Bagenalstown (Phase 2) | 10 | *N/A | [5 empty] | Q4-2022
38 | SHIP CONSTRUCTION | Carlow | Fr. Flood Park, Rathvilly | 18 | *N/A |  |  |  |  | Q3-2023
39 | SHIP CONSTRUCTION | Carlow | Gleann na Bearu, Bagenalstown (Phase 2) | 6 | *N/A | [5 empty] | Q4-2022
40 | SHIP CONSTRUCTION | Carlow | Gleann na Bearu, Bagenalstown (Phase 2) | 6 | *N/A | [5 empty] | Q1-2023
41 | SHIP CONSTRUCTION | Carlow | Kealy's Bar, Main Street, Hacketstown, Co. Carlow | 12 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
42 | SHIP CONSTRUCTION | Carlow | Culan Eanna, Sleaty Road, Graiguecullen, Carlow | 4 | *N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
43 | SHIP Accel MMC | Carlow | Pembroke Street, Carlow Town | 60 | *N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
44 | CAS CONSTRUCTION TURNKEY | Carlow | The Green Drake, Lower Main Street, Borris | 15 | Tintean Housing Association Ltd |  |  |  |  | Q1-2024
45 | CAS CONSTRUCTION | Carlow | Gleann na Bearu, Royal Oak Road, Bagenalstown | 6 | Respond | [5 empty] | Q4-2023
46 | CAS CONSTRUCTION | Carlow | Homefield, Blackbog Road, Carlow | 3 | Carlow Voluntary Housing Association | [5 empty] | Q2-2021
47 | SHIP CONSTRUCTION TURNKEY | Cavan | Ashgrove, Derrylurgan, Ballyjamesduff | 4 | *N/A | [5 empty] | Q4-2021
48 | SHIP CONSTRUCTION TURNKEY | Cavan | Woodlands, Killyfinla, Ballyjamesduff | 4 | *N/A | [5 empty] | Q2-2024
49 | SHIP CONSTRUCTION TURNKEY | Cavan | Woodlands, Killyfinla, Ballyjamesduff | 4 | *N/A |  |  |  |  | Q4-2022
50 | SHIP CONSTRUCTION TURNKEY | Cavan | Woodlands, Killyfinla, Ballyjamesduff | 12 | *N/A |  |  |  |  | Q4-2022
51 | SHIP CONSTRUCTION TURNKEY | Cavan | Woodlands, Killyfinla, Ballyjamesduff | 12 | *N/A |  |  |  |  | Q4-2022
52 | SHIP CONSTRUCTION TURNKEY | Cavan | Mullaghduff, Ballyconnell | 7 | *N/A | [5 empty] | Q2-2022
53 | SHIP CONSTRUCTION TURNKEY | Cavan | Mullaghduff, Ballyconnell | 11 | *N/A | [5 empty] | Q4-2022
54 | SHIP CONSTRUCTION TURNKEY | Cavan | Mullaghduff, Ballyconnell | 10 | *N/A | [5 empty] | Q3-2023
55 | SHIP CONSTRUCTION TURNKEY | Cavan | Mullaghduff, Ballyconnell | 11 | *N/A | [5 empty] | Q4-2023
56 | SHIP CONSTRUCTION TURNKEY | Cavan | Clankee Court, Lisdrumskea, Shercock | 2 | *N/A | [5 empty] | Q2-2024
57 | SHIP CONSTRUCTION TURNKEY | Cavan | Abhainn Dubh, Rosehill, Mullagh | 4 | *N/A | [5 empty] | Q4-2021
58 | SHIP CONSTRUCTION TURNKEY | Cavan | Kilnavara Heights, Cavan Town | 2 | *N/A | [5 empty] | Q4-2022
59 | SHIP CONSTRUCTION TURNKEY | Cavan | Errigal, Cootehill | 6 | *N/A |  |  |  |  | Q3-2023
60 | SHIP CONSTRUCTION TURNKEY | Cavan | Taoibh Coille, Yew Park, Virginia | 4 | *N/A |  |  |  |  | Q1-2023
61 | SHIP CONSTRUCTION TURNKEY | Cavan | Tullybuck, Butlersbridge | 6 | *N/A | [5 empty] | Q4-2023
62 | SHIP CONSTRUCTION TURNKEY | Cavan | Lisasturrin, Kingscourt | 8 | N/A | [5 empty] | Q3-2024
63 | SHIP CONSTRUCTION TURNKEY | Cavan | Lisasturrin, Kingscourt | 13 | *N/A |  |  |  |  | Q3-2023
64 | SHIP CONSTRUCTION TURNKEY | Cavan | Lisasturrin, Kingscourt | 9 | *N/A |  |  |  |  | Q3-2023
65 | SHIP CONSTRUCTION TURNKEY | Cavan | Kilnavara Heights, Cavan Town, Cavan | 3 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
66 | SHIP CONSTRUCTION TURNKEY | Cavan | Coolkill, Kilnaleck | 10 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
67 | SHIP CONSTRUCTION | Cavan | Corstruce, Ballinagh | 4 | *N/A | [5 empty] | Q2-2021
68 | SHIP CONSTRUCTION | Cavan | Main Street, Mullagh | 19 | *N/A |  |  |  |  | Q4-2020
69 | SHIP CONSTRUCTION | Cavan | Elm Grove, Main St, Cavan Town | 13 | *N/A | [5 empty] | Q1-2024
70 | SHIP CONSTRUCTION | Cavan | Cavan Road, Ballinagh | 15 | *N/A | [5 empty] | Q4-2022
71 | SHIP CONSTRUCTION | Cavan | Main St., Butlersbridge | 6 | *N/A | [5 empty] | Q3-2022
72 | SHIP CONSTRUCTION | Cavan | Cluain Dara, Kingscourt | 3 | *N/A | [5 empty] | Q4-2021
73 | SHIP CONSTRUCTION | Cavan | Fairymount Close, Kingscourt | 3 | *N/A | [5 empty] | Q3-2024
74 | SHIP CONSTRUCTION | Cavan | St. Bridgets Terrace, Cavan Town (Infill) | 8 | *N/A |  |  |  |  | Q3-2023
75 | SHIP CONSTRUCTION | Cavan | Pairc na Teile, Beckscourt, Bailieborough | 45 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
76 | SHIP CONSTRUCTION | Cavan | Duckin Stool, Main Street, Belturbet | 3 | *N/A |  |  |  |  | Q2-2023
77 | SHIP CONSTRUCTION | Cavan | The Widow's Row, Widow's House Lane, Belturbet | 9 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
78 | SHIP CONSTRUCTION | Cavan | Derrylurgan, Ballyjamesduff | 12 | N/A | Stage 1 approved Q4-2021, outline design and costs being prepared.
79 | SHIP CONSTRUCTION | Cavan | Ashgrove, Derrylurgan, Ballyjamesduff | 9 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
80 | SHIP CONSTRUCTION | Cavan | 157 Barrack Road, Kilnaleck | 5 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
81 | SHIP CONSTRUCTION | Cavan | Briody Hardware, Main St., Kilnaleck | 8 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
82 | SHIP CONSTRUCTION | Cavan | Portaliffe, Killeshandra | 8 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
83 | SHIP CONSTRUCTION | Cavan | Mossy Meadows, Swellan Lr., Cavan | 13 | *N/A | Stage 1 approved Q1-2023, outline design and costs being prepared.
84 | SHIP CONSTRUCTION | Cavan | Drumbarlow Road, Kilconny, Belturbet | 4 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
85 | SHIP CONSTRUCTION | Cavan | Chapel Lane, Cootehill | 13 | *N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
86 | SHIP CONSTRUCTION | Cavan | Townpark, Ballyhaise | 7 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
87 | SHIP CONSTRUCTION | Cavan | Lios na Rí, Munnilly, Cootehill | 44 | *N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
88 | SHIP CONSTRUCTION | Cavan | Aughnaskerry, Cavan | 3 | *N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
89 | SHIP CONSTRUCTION | Cavan | Swellan Lr., Cavan Town | 64 | *N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
90 | SHIP CONSTRUCTION | Cavan | St. Brigid's Terrae, Cavan Town | 20 | *N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
91 | SHIP CONSTRUCTION | Cavan | St. Bridgets Terrace, Cavan Town (Infill) | 12 | *N/A |  |  |  |  | Q3-2023
92 | CAS CONSTRUCTION TURNKEY | Cavan | Loreto Lodge, Loreto Wood, Cavan Town | 7 | North ＆ East Housing Association Ltd | [5 empty] | Q4-2022
93 | CAS CONSTRUCTION RENEWAL | Cavan | 16 River St., Cavan | 1 | Society of Saint Vincent de Paul |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
94 | CAS CONSTRUCTION | Cavan | St. Killian's Housing Association Ltd., Mullagh, Co. Cavan | 4 | St. Killian's Housing Association, Mullagh, Co. Cavan | [5 empty] | Q4-2022
95 | CAS CONSTRUCTION | Cavan | 29 Bridge Street Cavan | 6 | Society of Saint Vincent de Paul | Stage 1 approved Q3-2022, outline design and costs being prepared.
96 | SHIP CONSTRUCTION TURNKEY | Clare | Shantraud Woods, Killaloe | 4 | *N/A | [5 empty] | Q1-2022
97 | SHIP CONSTRUCTION TURNKEY | Clare | Cluain Greine, Drumcliff Rd., Ennis | 20 | N/A | [5 empty] | Q4-2022
98 | SHIP CONSTRUCTION TURNKEY | Clare | Cluain Greine, Drumcliff Rd., Ennis | 12 | N/A | [5 empty] | Q2-2022
99 | SHIP CONSTRUCTION TURNKEY | Clare | Main St., Mountshannon | 4 | *N/A | [5 empty] | Q3-2022
100 | SHIP CONSTRUCTION TURNKEY | Clare | Cluain Greine, Drumcliff Rd., Ennis | 23 | *N/A | [5 empty] | Q4-2022
101 | SHIP CONSTRUCTION TURNKEY | Clare | Clarehill, Clarecastle, Co Clare | 10 | N/A |  |  |  |  | Q3-2023
102 | SHIP CONSTRUCTION TURNKEY | Clare | Clarehill, Clarecastle, Co Clare | 3 | N/A |  |  |  |  | Q3-2023
103 | SHIP CONSTRUCTION TURNKEY | Clare | Garna House, Sixmilebridge | 9 | N/A | [5 empty] | Q4-2023
104 | SHIP CONSTRUCTION TURNKEY | Clare | Pella Road, Leadmore, Kilrush | 13 | N/A |  |  |  |  | Q3-2023
105 | SHIP CONSTRUCTION TURNKEY | Clare | 70 O'Connell St., Ennis | 7 | *N/A | [5 empty] | Q4-2023
106 | SHIP CONSTRUCTION TURNKEY | Clare | 70 O'Connell Street, Ennis | 3 | N/A | [5 empty] | Q4-2023
107 | SHIP CONSTRUCTION TURNKEY | Clare | Estuary View, Shanakyle Road | 10 | N/A |  |  |  |  | Q2-2024
108 | SHIP CONSTRUCTION TURNKEY | Clare | Estuary View, Shanakyle Road | 8 | N/A |  |  |  |  | Q2-2024
109 | SHIP CONSTRUCTION TURNKEY | Clare | Main Street, Clarecastle | 7 | N/A |  |  |  |  | Q2-2024
110 | SHIP CONSTRUCTION TURNKEY | Clare | Circular Road, Ennistymon | 4 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
111 | SHIP CONSTRUCTION TURNKEY | Clare | Harveys Quay, Ennis | 4 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
112 | SHIP CONSTRUCTION SINGLE STAGE | Clare | Dun na Mara, Doonbeg | 2 | *N/A | [5 empty] | Q2-2021
113 | SHIP CONSTRUCTION SINGLE STAGE | Clare | St Senan’s Terrace, Kilrush -No5-No 6 | 2 | *N/A | [5 empty] | Q3-2021
114 | SHIP CONSTRUCTION SINGLE STAGE | Clare | Dun na hInse, Ennis | 1 | N/A | [5 empty] | Q3-2024
115 | SHIP CONSTRUCTION RENEWAL | Clare | Nagles Terrace, Kilrush | 3 | N/A | [5 empty] | Q4-2022
116 | SHIP CONSTRUCTION RENEWAL | Clare | St. Senan's Terrace, Kilrush | 4 | N/A | [5 empty] | Q4-2023
117 | SHIP CONSTRUCTION RENEWAL | Clare | 272 Newtown, Corofin | 1 | N/A | [5 empty] | Q4-2023
118 | SHIP CONSTRUCTION RENEWAL | Clare | Main Street, Clarecastle | 1 | N/A |  |  |  |  | Q4-2023
119 | SHIP CONSTRUCTION RENEWAL | Clare | 19 & 20 Sycamore Drive, Kilrush | 2 | N/A | [5 empty] | Q4-2023
120 | SHIP CONSTRUCTION RENEWAL | Clare | St. Senan's Terrace, Kilrush | 1 | N/A | [5 empty] | Q3-2024
121 | SHIP CONSTRUCTION RENEWAL | Clare | Church Street, Miltown Malbay | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
122 | SHIP CONSTRUCTION RENEWAL | Clare | Church Road, Miltown Malbay | 1 | N/A | [5 empty] | Q3-2024
123 | SHIP CONSTRUCTION RENEWAL | Clare | 25 Crossroads, Killaloe | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
124 | SHIP CONSTRUCTION | Clare | Ashline, Kilrush Road, Ennis | 40 | *N/A | [5 empty] | Q2-2022
125 | SHIP CONSTRUCTION | Clare | Ballard Rd,Miltown Malbay | 27 | *N/A | [5 empty] | Q4-2022
126 | SHIP CONSTRUCTION | Clare | Doonaun, Tulla | 25 | *N/A | [5 empty] | Q2-2022
127 | SHIP CONSTRUCTION | Clare | Boheraroan, Newmarket-on-Fergus | 18 | *N/A | [5 empty] | Q1-2022
128 | SHIP CONSTRUCTION | Clare | Droichead Nua, Ballyminogue,Feakle Rd., Scariff | 18 | *N/A |  |  |  |  | Q1-2023
129 | SHIP CONSTRUCTION | Clare | Madden's Terrace, Clarecastle | 5 | *N/A | [5 empty] | Q4-2023
130 | SHIP CONSTRUCTION | Clare | Kilkee Road, Doonbeg | 8 | *N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
131 | SHIP CONSTRUCTION | Clare | Tulla Road, Roslevan, Ennis (Fannings site) | 8 | *N/A | [5 empty] | Q4-2022
132 | SHIP CONSTRUCTION | Clare | Drumcliff Road, Ennis | 26 | *N/A |  |  | Stage 3 approved Q4-2023, the scheme is now approved to proceed to tender.
133 | SHIP CONSTRUCTION | Clare | Baile Uí Loideáin, Ballyliddan West, Sixmilebridge | 15 | *N/A |  |  |  |  | Q1-2023
134 | SHIP CONSTRUCTION | Clare | Gort Road Ennis | 20 | N/A |  |  |  |  | Q3-2024
135 | SHIP CONSTRUCTION | Clare | Moore Street, Kilrush | 16 | N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
136 | SHIP CONSTRUCTION | Clare | Back Road, Kilrush | 12 | N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
137 | SHIP CONSTRUCTION | Clare | Shallee Drive/Cloughleigh Road | 5 | N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
138 | CAS CONSTRUCTION TURNKEY | Clare | Clon Road, Ennis, Co. clare | 10 | Society of Saint Vincent de Paul |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
139 | CAS CONSTRUCTION RENEWAL | Clare | 17 Kincora Park, Ennis | 1 | Society of Saint Vincent de Paul | [5 empty] | Q1-2023
140 | CAS CONSTRUCTION RENEWAL | Clare | 12A Derg Estate, Scariff | 4 | Inis Housing Association Ltd | [5 empty] | Q4-2023
141 | CAS CONSTRUCTION RENEWAL | Clare | 63 Shannon Heights, Kilrush | 4 | Sophia Housing Association Ltd |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
142 | CAS CONSTRUCTION | Clare | Teach Rua, Edenvale Ennis | 4 | Newgrove Housing Association Ltd | [5 empty] | Q2-2021
143 | SHIP DIALOG | Cork City | Barrack Street | 28 | *N/A | [5 empty] | Q4-2023
144 | SHIP DIALOG | Cork City | Woods Street | 16 | *N/A |  |  |  |  | Q1-2019
145 | SHIP DIALOG | Cork City | Skehard Road, Blackrock, Cork | 16 | *N/A | [5 empty] | Q2-2022
146 | SHIP DIALOG | Cork City | Coach Street, Cork | 12 | *N/A | [5 empty] | Q2-2023
147 | SHIP DIALOG | Cork City | Shanakiel Road, Cork | 20 | *N/A | [5 empty] | Q3-2022
148 | SHIP DIALOG | Cork City | Spring Lane, Blackpool, Cork | 8 | *N/A | [5 empty] | Q4-2022
149 | SHIP DIALOG | Cork City | Glen Ryan Road, Cork | 9 | *N/A | [5 empty] | Q4-2023
150 | SHIP DIALOG | Cork City | Pouladuff Road, Cork | 11 | *N/A | [5 empty] | Q2-2022
151 | SHIP DIALOG | Cork City | Watercourse Road, Blackpool, Cork | 37 | *N/A | [5 empty] | Q4-2022
152 | SHIP DIALOG | Cork City | Denroche's Cross, Glasheen Road, Cork | 43 | *N/A | [5 empty] | Q4-2023
153 | SHIP DIALOG | Cork City | Wolsey Court, Blackpool, Cork | 49 | *N/A |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
154 | SHIP DIALOG | Cork City | Sunview, South Douglas Road, Douglas, Cork | 25 | *N/A | [5 empty] | Q3-2022
155 | SHIP DIALOG | Cork City | Old Mallow Road | 54 | *N/A | [5 empty] | Q2-2023
156 | SHIP DIALOG | Cork City | Killeens | 12 | *N/A | [5 empty] | Q4-2023
157 | SHIP DIALOG | Cork City | Church Road, Black Rock, Cork | 30 | *N/A | [5 empty] | Q2-2024
158 | SHIP DIALOG | Cork City | Kinsale road Cork City | 39 | *N/A |  |  |  |  | Q2-2023
159 | SHIP DIALOG | Cork City | Ballincrokig, Ballyvolane | 72 | *N/A |  |  |  | Stage 4 approved Q2-2023, the scheme is fully approved.
160 | SHIP DIALOG | Cork City | Greenvalley, Douglas, Cork City | 25 | *N/A |  |  |  |  | Q2-2023
161 | SHIP DIALOG | Cork City | Farranferris Cork City | 26 | *N/A |  |  |  |  | Q4-2023
162 | SHIP DIALOG | Cork City | Grange Scairt Cross | 54 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
163 | SHIP DIALOG | Cork City | 21-22 Dominick Street, Shandon, Cork City | 9 | *N/A |  |  |  |  | Q1-2023
164 | SHIP DIALOG | Cork City | Hawkes Road, Bishopstown Road, Bishopstown, Cork City | 29 | *N/A | [5 empty] | Q4-2022
165 | SHIP DIALOG | Cork City | Lower John Street | 3 | *N/A |  |  |  | Stage 4 approved Q1-2022, the scheme is fully approved.
166 | SHIP DIALOG | Cork City | Killeens | 32 | N/A | [5 empty] | Q4-2023
167 | SHIP DIALOG | Cork City | Gerald Griffin Street/Burke’s Avenue, Cork City | 67 | N/A |  |  |  |  | Q3-2023
168 | SHIP DIALOG | Cork City | Redemption Heights, Redemption road, Blackpool, Cork | 54 | N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
169 | SHIP DIALOG | Cork City | Barrack Street | 3 | N/A | [5 empty] | Q2-2024
170 | SHIP DIALOG | Cork City | Farranlea Road, Cork | 12 | N/A |  |  |  |  | Q3-2024
171 | SHIP DIALOG | Cork City | Gerald Griffin Street, Blackpool, Cork City | 17 | N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
172 | SHIP DIALOG | Cork City | Barrack Street | 1 | *N/A | [5 empty] | Q3-2024
173 | SHIP CONSTRUCTION TURNKEY | Cork City | 1 Summerville Place, Blarney Street | 1 | N/A | [5 empty] | Q1-2023
174 | SHIP CONSTRUCTION TURNKEY | Cork City | Bridgefield, Curraheen, Cork | 6 | N/A | [5 empty] | Q4-2023
175 | SHIP CONSTRUCTION TURNKEY | Cork City | Great William O'Brien, Blackpool, Cork | 7 | N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
176 | SHIP CONSTRUCTION TURNKEY | Cork City | Carriganarra, Ballincollig, Cork | 3 | N/A | [5 empty] | Q4-2023
177 | SHIP CONSTRUCTION TURNKEY | Cork City | North Main Street, Cork City | 7 | N/A | [5 empty] | Q4-2023
178 | SHIP CONSTRUCTION TURNKEY | Cork City | Meadow Broome, Cooneys Lane, Grange, Cork | 27 | N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
179 | SHIP CONSTRUCTION TURNKEY | Cork City | 31 & 34 Stephen Street, Cork | 6 | N/A |  |  |  |  | Q2-2024
180 | SHIP CONSTRUCTION TURNKEY | Cork City | Popes Road, Off Richmond Hill, Blackpoll, Cork | 7 | N/A |  |  |  |  | Q2-2024
181 | SHIP CONSTRUCTION TURNKEY | Cork City | 8 & 8a Ballinure Cottages, Mahon, Cork | 3 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
182 | SHIP CONSTRUCTION TURNKEY | Cork City | Herbert Lawn, Garryduff, Rochestown | 8 | N/A | [5 empty] | Q3-2024
183 | SHIP CONSTRUCTION TURNKEY | Cork City | Ballinure Cottages | 11 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
184 | SHIP CONSTRUCTION TURNKEY | Cork City | Meadow Broome, Cooneys Lane, Grange, Cork | 6 | N/A |  |  |  |  | Q4-2023
185 | SHIP CONSTRUCTION TURNKEY | Cork City | Meadow Broome, Cooneys Lane, Grange, Cork | 5 | N/A |  |  |  |  | Q4-2023
186 | SHIP CONSTRUCTION RENEWAL | Cork City | 38 Gould Street | 1 | *N/A |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
187 | SHIP CONSTRUCTION RENEWAL | Cork City | 1 Evenus Ville, Albert Road, Cork City | 1 | *N/A | [5 empty] | Q4-2023
188 | SHIP CONSTRUCTION RENEWAL | Cork City | Ard na Ri, Pouladuff Road, Cork City | 1 | *N/A | [5 empty] | Q2-2023
189 | SHIP CONSTRUCTION RENEWAL | Cork City | Mount Eden Road, Cork City | 1 | *N/A | [5 empty] | Q4-2022
190 | SHIP CONSTRUCTION RENEWAL | Cork City | 21 St Anthony's Road | 1 | *N/A | [5 empty] | Q4-2022
191 | SHIP CONSTRUCTION RENEWAL | Cork City | 26 Watercourse Road | 1 | *N/A | [5 empty] | Q4-2022
192 | SHIP CONSTRUCTION RENEWAL | Cork City | 22 Summerstown Grove | 1 | *N/A | [5 empty] | Q4-2022
193 | SHIP CONSTRUCTION RENEWAL | Cork City | 2A Fairhill | 1 | *N/A | [5 empty] | Q4-2022
194 | SHIP CONSTRUCTION RENEWAL | Cork City | 99 Ballinderry Park | 1 | *N/A | [5 empty] | Q4-2022
195 | SHIP CONSTRUCTION DESIGN BUILD | Cork City | Clover Hill Court, Bessboro Road, Mahon, Cork | 90 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
196 | SHIP CONSTRUCTION | Cork City | Poulavone, Ballincollig | 35 | *N/A | [5 empty] | Q4-2023
197 | SHIP CONSTRUCTION | Cork City | Boyces Street; Cattle Market Street | 14 | *N/A | [5 empty] | Q3-2023
198 | SHIP CONSTRUCTION | Cork City | Madonna House, Ballincollig | 6 | *N/A |  |  |  |  | Q1-2024
199 | SHIP CONSTRUCTION | Cork City | Bramble Cottages | 4 | *N/A |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
200 | SHIP CONSTRUCTION | Cork City | Errigal Heights, The Glen, Cork City | 28 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
201 | SHIP CONSTRUCTION | Cork City | Glenamoy Lawn, Mayfield, Cork | 3 | *N/A | [5 empty] | Q4-2023
202 | SHIP CONSTRUCTION | Cork City | CNWQR Knocknaheeny Phase 3B | 62 | *N/A |  |  | Stage 3 approved Q4-2023, the scheme is now approved to proceed to tender.
203 | SHIP CONSTRUCTION | Cork City | Hollywood Estate, Blarney Road, Cork | 7 | *N/A | [5 empty] | Q3-2024
204 | SHIP CONSTRUCTION | Cork City | Westside, Model Farm Road, Cork | 43 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
205 | SHIP CONSTRUCTION | Cork City | 16A Kerry Road (former Slí Gartan), Mayfield, Cork | 1 | *N/A | [5 empty] | Q3-2023
206 | SHIP CONSTRUCTION | Cork City | CNWQR Knocknaheeny Phase 4A | 43 | *N/A |  | Stage 2 approved Q1-2022, full design/tender being prepared.
207 | SHIP CONSTRUCTION | Cork City | Boyces street | 37 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
208 | SHIP CONSTRUCTION | Cork City | 15 Loughview Terrace, The Lough, Glasheen | 1 | *N/A | [5 empty] | Q4-2023
209 | SHIP CONSTRUCTION | Cork City | Rope Walk, Blackrock, Co. Cork | 3 | N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
210 | SHIP CONSTRUCTION | Cork City | Hollyville, Hollyhill, Cork City | 2 | N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
211 | SHIP CONSTRUCTION | Cork City | Poulavone, Ballincollig | 29 | N/A | [5 empty] | Q2-2024
212 | SHIP CONSTRUCTION | Cork City | Clanrickarde Lodges, Boreenmanna Rd | 4 | N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
213 | REGENERATION | Cork City | CNWQR Knocknaheeny Phase 1C | 41 | *N/A |  |  |  |  | Q4-2022
214 | REGENERATION | Cork City | CNWQR Knocknaheeny Phase 2B | 38 | *N/A |  |  |  |  | Q4-2022
215 | REGENERATION | Cork City | CNWQR Knocknaheeny Phase 2C | 24 | *N/A |  |  |  |  | Q4-2019
216 | REGENERATION | Cork City | Foyle Ave Infill and Ardmore Avenue, Knocknaheeny | 2 | *N/A | [5 empty] | Q4-2023
217 | CAS CONSTRUCTION TURNKEY | Cork City | O'Connell Court (former Doughcloyne Hotel) Lehenaghmore, Togher, | 90 | Oakdene House |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
218 | CAS CONSTRUCTION TURNKEY | Cork City | Blue Anchor Yard, Douglas St., Cork | 4 | Focus Ireland | [5 empty] | Q4-2023
219 | CAS CONSTRUCTION TURNKEY | Cork City | Smithgrove Terrace, Middle Glanmire Road, Cork | 5 | Shanbally Housing Association Ltd | [5 empty] | Q3-2024
220 | CAS CONSTRUCTION TURNKEY | Cork City | 22 Lower John Street, Cork City | 4 | Focus Ireland |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
221 | CAS CONSTRUCTION TURNKEY | Cork City | Watercours Mews, Water Course Road, Cork | 3 | Focus Ireland |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
222 | CAS CONSTRUCTION SINGLE STAGE | Cork City | Eastville, Albert Road, Cork | 1 | Galtan Ltd | [5 empty] | Q1-2022
223 | CAS CONSTRUCTION SINGLE STAGE | Cork City | 14 Glanmire Road Cork | 2 | Galtan Ltd | [5 empty] | Q1-2022
224 | CAS CONSTRUCTION | Cork City | Ard na Ri, Closes Green, Farranree, Cork | 20 | Farranree Sheltered Housing Association |  | Stage 2 approved Q3-2022, full design/tender being prepared.
225 | CAS CONSTRUCTION | Cork City | Apts 2 & 3 Cois Coille, Tivoli, Cork | 2 | Galtan Ltd | [5 empty] | Q4-2021
226 | CAS CONSTRUCTION | Cork City | 88 Sundays Well | 2 | Galtan Ltd |  |  |  |  | Q4-2023
227 | CAS CONSTRUCTION | Cork City | Deerpark Mews, Deerpark, De Paul Hostel, Friarswalk Cork City | 8 | Society of Saint Vincent de Paul |  |  |  |  | Q3-2024
228 | CAS CONSTRUCTION | Cork City | DVR @ Evergreen street, Turner's Cross | 20 | Good Shepherd Services Ltd | Stage 1 approved Q4-2023, outline design and costs being prepared.
229 | SHIP CONSTRUCTION TURNKEY | Cork County | Claragh Road, Millstreet | 5 | *N/A | [5 empty] | Q2-2021
230 | SHIP CONSTRUCTION TURNKEY | Cork County | Sweetfields, Youghal | 3 | *N/A | [5 empty] | Q4-2021
231 | SHIP CONSTRUCTION TURNKEY | Cork County | Copper Point, Schull | 5 | *N/A | [5 empty] | Q2-2022
232 | SHIP CONSTRUCTION TURNKEY | Cork County | Mill Road, Avoncore, Bloomfield, Midleton | 11 | *N/A | [5 empty] | Q1-2021
233 | SHIP CONSTRUCTION TURNKEY | Cork County | Mill Road, Avoncore, Bloomfield, Midleton | 17 | *N/A | [5 empty] | Q2-2021
234 | SHIP CONSTRUCTION TURNKEY | Cork County | Copper Point, Schull | 5 | *N/A | [5 empty] | Q3-2022
235 | SHIP CONSTRUCTION TURNKEY | Cork County | Millview Road, Kanturk | 4 | *N/A | [5 empty] | Q1-2021
236 | SHIP CONSTRUCTION TURNKEY | Cork County | Ard an Bhaile, Creggane, Buttevant | 6 | *N/A | [5 empty] | Q4-2022
237 | SHIP CONSTRUCTION TURNKEY | Cork County | Meenane, Watergrasshill | 4 | *N/A | [5 empty] | Q2-2021
238 | SHIP CONSTRUCTION TURNKEY | Cork County | Kilmoney, Carrigaline | 12 | *N/A | [5 empty] | Q2-2022
239 | SHIP CONSTRUCTION TURNKEY | Cork County | Caherdaniel, Bantry | 10 | *N/A | [5 empty] | Q4-2023
240 | SHIP CONSTRUCTION TURNKEY | Cork County | An Goritin Rua, Millstreet Road, Macroom | 14 | *N/A | [5 empty] | Q2-2021
241 | SHIP CONSTRUCTION TURNKEY | Cork County | Lyraneag, Rockchapel, | 2 | *N/A |  |  |  |  | Q3-2023
242 | SHIP CONSTRUCTION TURNKEY | Cork County | Eyeries, Castletownbere | 6 | *N/A | [5 empty] | Q4-2022
243 | SHIP CONSTRUCTION TURNKEY | Cork County | Lios Ard, Ballyhooly | 6 | *N/A | [5 empty] | Q1-2021
244 | SHIP CONSTRUCTION TURNKEY | Cork County | Spa Glen,Ballyviniter, Mallow | 18 | *N/A | [5 empty] | Q2-2021
245 | SHIP CONSTRUCTION TURNKEY | Cork County | Drakes Point, Knocknagore, Crosshaven | 5 | *N/A | [5 empty] | Q3-2021
246 | SHIP CONSTRUCTION TURNKEY | Cork County | Scarteen, Newmarket | 11 | *N/A |  |  |  | Stage 4 approved Q4-2022, the scheme is fully approved.
247 | SHIP CONSTRUCTION TURNKEY | Cork County | Caherdaniel, Bantry | 6 | *N/A |  |  |  |  | Q1-2020
248 | SHIP CONSTRUCTION TURNKEY | Cork County | Caherdaniel, Bantry | 6 | *N/A |  |  |  |  | Q1-2020
249 | SHIP CONSTRUCTION TURNKEY | Cork County | Abbeyfort, Kinsale | 19 | *N/A | [5 empty] | Q4-2021
250 | SHIP CONSTRUCTION TURNKEY | Cork County | Clarendon Brooks, Carrs Hill, Douglas | 4 | *N/A | [5 empty] | Q1-2021
251 | SHIP CONSTRUCTION TURNKEY | Cork County | Abbeyfort, Kinsale (Phase 2) | 17 | *N/A | [5 empty] | Q3-2022
252 | SHIP CONSTRUCTION TURNKEY | Cork County | Ard Cashel, Watergrasshill | 6 | *N/A | [5 empty] | Q1-2022
253 | SHIP CONSTRUCTION TURNKEY | Cork County | Lios Ard, Ballyhooly | 6 | *N/A | [5 empty] | Q2-2021
254 | SHIP CONSTRUCTION TURNKEY | Cork County | Courtbrack, Tower | 1 | *N/A | [5 empty] | Q4-2021
255 | SHIP CONSTRUCTION TURNKEY | Cork County | Sweetfields, Youghal | 10 | *N/A | [5 empty] | Q4-2022
256 | SHIP CONSTRUCTION TURNKEY | Cork County | Lisgoold, An Tui | 2 | *N/A | [5 empty] | Q2-2022
257 | SHIP CONSTRUCTION TURNKEY | Cork County | The Pastures, Charleville | 4 | *N/A | [5 empty] | Q4-2021
258 | SHIP CONSTRUCTION TURNKEY | Cork County | Meenane, Watergrasshill | 7 | *N/A | [5 empty] | Q2-2021
259 | SHIP CONSTRUCTION TURNKEY | Cork County | Meenane, Watergrasshill | 3 | *N/A | [5 empty] | Q1-2022
260 | SHIP CONSTRUCTION TURNKEY | Cork County | The Pastures, Charleville | 5 | *N/A | [5 empty] | Q2-2022
261 | SHIP CONSTRUCTION TURNKEY | Cork County | Kilmoney, Carrigaline | 4 | *N/A | [5 empty] | Q3-2022
262 | SHIP CONSTRUCTION TURNKEY | Cork County | Kilmoney, Carrigaline | 12 | *N/A | [5 empty] | Q3-2022
263 | SHIP CONSTRUCTION TURNKEY | Cork County | Kilmoney, Carrigaline | 5 | *N/A | [5 empty] | Q4-2022
264 | SHIP CONSTRUCTION TURNKEY | Cork County | Meenane, Watergrasshill | 4 | *N/A | [5 empty] | Q4-2021
265 | SHIP CONSTRUCTION TURNKEY | Cork County | The Meadows, Dunmanway | 4 | N/A | [5 empty] | Q3-2022
266 | SHIP CONSTRUCTION TURNKEY | Cork County | Sweetfields, Youghal | 7 | N/A | [5 empty] | Q1-2022
267 | SHIP CONSTRUCTION TURNKEY | Cork County | Caherdaniel, Bantry | 12 | *N/A |  |  |  |  | Q1-2020
268 | SHIP CONSTRUCTION TURNKEY | Cork County | Dromdiah Park, Killeagh Gardens, Killeagh | 10 | *N/A | [5 empty] | Q4-2022
269 | SHIP CONSTRUCTION TURNKEY | Cork County | Meenane, Watergrasshill | 7 | *N/A | [5 empty] | Q2-2022
270 | SHIP CONSTRUCTION TURNKEY | Cork County | The Pastures, Charleville | 7 | *N/A | [5 empty] | Q2-2022
271 | SHIP CONSTRUCTION TURNKEY | Cork County | The Meadows, Dunmanway (Phase 2) | 8 | *N/A | [5 empty] | Q3-2022
272 | SHIP CONSTRUCTION TURNKEY | Cork County | Reanrour East, Bantry | 5 | *N/A | [5 empty] | Q4-2023
273 | SHIP CONSTRUCTION TURNKEY | Cork County | Copper Point, Schull Phase 3 | 2 | *N/A | [5 empty] | Q4-2022
274 | SHIP CONSTRUCTION TURNKEY | Cork County | Dromahane, Mallow | 6 | N/A | [5 empty] | Q4-2022
275 | SHIP CONSTRUCTION TURNKEY | Cork County | Foxglove Close, Charleville, | 12 | N/A | [5 empty] | Q3-2023
276 | SHIP CONSTRUCTION TURNKEY | Cork County | Kilmoney, Carrigaline | 11 | N/A | [5 empty] | Q4-2022
277 | SHIP CONSTRUCTION TURNKEY | Cork County | Copper Point, Schull | 4 | N/A | [5 empty] | Q4-2022
278 | SHIP CONSTRUCTION TURNKEY | Cork County | Pike Road, Fermoy | 25 | N/A | [5 empty] | Q4-2023
279 | SHIP CONSTRUCTION TURNKEY | Cork County | Kilmoney, Carrigaline | 5 | N/A | [5 empty] | Q4-2022
280 | SHIP CONSTRUCTION TURNKEY | Cork County | Dromahane, Mallow | 2 | *N/A | [5 empty] | Q3-2023
281 | SHIP CONSTRUCTION TURNKEY | Cork County | Kilmoney, Carrigaline | 9 | *N/A | [5 empty] | Q2-2023
282 | SHIP CONSTRUCTION TURNKEY | Cork County | Cluain Ard, Cobh | 16 | *N/A | [5 empty] | Q4-2023
283 | SHIP CONSTRUCTION TURNKEY | Cork County | The Hermitage, Rushbrooke | 10 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
284 | SHIP CONSTRUCTION TURNKEY | Cork County | The Hermitage, Rushbrooke | 5 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
285 | SHIP CONSTRUCTION TURNKEY | Cork County | Cluain Ard, Cobh | 30 | *N/A | [5 empty] | Q4-2023
286 | SHIP CONSTRUCTION TURNKEY | Cork County | Mountleader, Millstreet | 14 | *N/A |  |  |  | Stage 4 approved Q2-2023, the scheme is fully approved.
287 | SHIP CONSTRUCTION TURNKEY | Cork County | The Waters Edge, Carrigaline | 1 | *N/A | [5 empty] | Q4-2023
288 | SHIP CONSTRUCTION TURNKEY | Cork County | Silverwood, Youghal | 5 | *N/A |  |  |  | Stage 4 approved Q2-2023, the scheme is fully approved.
289 | SHIP CONSTRUCTION TURNKEY | Cork County | Crann Ard, Fermoy | 12 | *N/A |  |  |  | Stage 4 approved Q2-2023, the scheme is fully approved.
290 | SHIP CONSTRUCTION TURNKEY | Cork County | Ard Abhainn, Knockraha | 2 | *N/A | [5 empty] | Q3-2024
291 | SHIP CONSTRUCTION TURNKEY | Cork County | Clonmore, Mallow | 1 | N/A | [5 empty] | Q4-2023
292 | SHIP CONSTRUCTION TURNKEY | Cork County | The Spinning Wheel, Friar Street, Youghal | 16 | N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
293 | SHIP CONSTRUCTION TURNKEY | Cork County | The Tannery, Bandon | 24 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
294 | SHIP CONSTRUCTION TURNKEY | Cork County | An Sraidbhaile Main Street, Mogeely | 2 | *N/A | [5 empty] | Q4-2023
295 | SHIP CONSTRUCTION TURNKEY | Cork County | Mill Road, Kanturk | 2 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
296 | SHIP CONSTRUCTION TURNKEY | Cork County | Cluain Ard, Cobh | 8 | N/A |  |  |  |  | Q1-2023
297 | SHIP CONSTRUCTION TURNKEY | Cork County | Dromdiah Park, Killeagh Gardens, Killeagh, | 20 | *N/A |  |  |  |  | Q2-2023
298 | SHIP CONSTRUCTION TURNKEY | Cork County | Clonmore, Mallow | 2 | *N/A | [5 empty] | Q2-2024
299 | SHIP CONSTRUCTION TURNKEY | Cork County | Glebe Manor, Whitegate | 4 | *N/A | [5 empty] | Q4-2023
300 | SHIP CONSTRUCTION TURNKEY | Cork County | Loughbeg, Ringaskiddy | 15 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
301 | SHIP CONSTRUCTION TURNKEY | Cork County | Ballyclough, Mallow | 15 | *N/A |  |  |  |  | Q4-2023
302 | SHIP CONSTRUCTION TURNKEY | Cork County | Dromahane, Mallow | 1 | N/A | [5 empty] | Q4-2023
303 | SHIP CONSTRUCTION TURNKEY | Cork County | Bridgeland, Rathcormac, Cork | 3 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
304 | SHIP CONSTRUCTION TURNKEY | Cork County | Ballyadam, Carrigtwohill | 19 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
305 | SHIP CONSTRUCTION TURNKEY | Cork County | 37 - 40 The Estuary, Magners Hill, Youghal | 5 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
306 | SHIP CONSTRUCTION TURNKEY | Cork County | Flaxmills Court, Skibbereen | 4 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
307 | SHIP CONSTRUCTION TURNKEY | Cork County | Percival Street, Kanturk | 6 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
308 | SHIP CONSTRUCTION TURNKEY | Cork County | Glenbeg, The Beeches, Boherbue | 14 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
309 | SHIP CONSTRUCTION TURNKEY | Cork County | Ard na Ri, Castlelyons, Co. Cork | 5 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
310 | SHIP CONSTRUCTION TURNKEY | Cork County | Ballydahin & Bolster Terrace, Mallow, Co. Cork | 47 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
311 | SHIP CONSTRUCTION TURNKEY | Cork County | Warrens Court, Ringaskiddy, Co. Cork | 14 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
312 | SHIP CONSTRUCTION TURNKEY | Cork County | Crann Ard, Fermoy | 36 | N/A |  |  |  | Stage 4 approved Q2-2023, the scheme is fully approved.
313 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | 2A Glenview, Lyre, Banteer | 1 | *N/A | [5 empty] | Q2-2023
314 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | Cuirt Na Slini, Cloyne, East Cork | 2 | *N/A | [5 empty] | Q4-2022
315 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | 81 Belmont Place, Cobh | 1 | *N/A | [5 empty] | Q4-2022
316 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | Main St. Dunmanway combined with N4-2-64 See Note | 1 | *N/A | [5 empty] | Q4-2021
317 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | Croke Place, Garranmacgarrett, Kilbrin, Kanturk | 2 | *N/A | [5 empty] | Q2-2023
318 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | High St., Sleaveen Hill, Macroom | 1 | *N/A | [5 empty] | Q2-2022
319 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | 49 Masseytown, Macroom | 1 | *N/A | [5 empty] | Q2-2022
320 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | Aisling Gheal, Hospital Hill, Kanturk | 1 | *N/A | [5 empty] | Q3-2024
321 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | Carrig Rossa, Rossmore - Phase 2 | 2 | *N/A | [5 empty] | Q3-2024
322 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | Fana Na gCann | 2 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
323 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | 3 Knockbrogan Park, Bandon | 1 | *N/A | [5 empty] | Q4-2021
324 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | 87 Belmont, Cobh | 1 | *N/A | [5 empty] | Q3-2022
325 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | 33 Market Place, Kanturk | 1 | *N/A |  |  |  | Stage 4 approved Q4-2022, the scheme is fully approved.
326 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | 19 & 20 Dr Croke Place, Kilbrin | 2 | N/A |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
327 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | 4 Church View Ballindangan | 1 | *N/A | [5 empty] | Q4-2022
328 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | Dean McNamara Place, Newtownshandrum | 2 | *N/A |  |  |  | Stage 4 approved Q2-2023, the scheme is fully approved.
329 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | St Olans Place, Aghabullogue | 8 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
330 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | Coolmucky, Cloughduv, Co Cork | 8 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
331 | SHIP CONSTRUCTION SINGLE STAGE | Cork County | Glenbower View, Killeagh, Co. Cork | 2 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
332 | SHIP CONSTRUCTION RENEWAL | Cork County | Former Garda Station, Goleen | 2 | *N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
333 | SHIP CONSTRUCTION RENEWAL | Cork County | Former Garda Station, Ardigole | 2 | *N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
334 | SHIP CONSTRUCTION | Cork County | Ard Na Greine, Cortmacsherry | 17 | *N/A | [5 empty] | Q4-2023
335 | SHIP CONSTRUCTION | Cork County | Beechgrove, Clonakilty | 51 | *N/A | [5 empty] | Q4-2021
336 | SHIP CONSTRUCTION | Cork County | Newtown House , Bantry | 1 | *N/A | [5 empty] | Q4-2021
337 | SHIP CONSTRUCTION | Cork County | Kilnagleary, Carrigaline (Phase 4) | 15 | *N/A | [5 empty] | Q4-2022
338 | SHIP CONSTRUCTION | Cork County | Townsend Street, Skibbereen | 6 | *N/A | [5 empty] | Q2-2022
339 | SHIP CONSTRUCTION | Cork County | Kearney's field Dunmanway | 5 | *N/A | [5 empty] | Q3-2022
340 | SHIP CONSTRUCTION | Cork County | Richmond Court, Bandon | 6 | *N/A | [5 empty] | Q4-2023
341 | SHIP CONSTRUCTION | Cork County | Brigown Road, Mitchelstown | 8 | *N/A |  |  |  |  | Q4-2023
342 | SHIP CONSTRUCTION | Cork County | Sleaveen East, Macroom | 8 | *N/A | [5 empty] | Q4-2023
343 | SHIP CONSTRUCTION | Cork County | Pound Lane, Kilworth | 7 | *N/A | [5 empty] | Q2-2023
344 | SHIP CONSTRUCTION | Cork County | Avoncore, Midleton (Rae Avoncore) | 10 | *N/A | Stage 1 approved Q2-2019, outline design and costs being prepared.
345 | SHIP CONSTRUCTION | Cork County | Knocknagown, Rylane | 1 | *N/A | [5 empty] | Q3-2021
346 | SHIP CONSTRUCTION | Cork County | Uplands (Phase 2), College Road, Fermoy | 11 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
347 | SHIP CONSTRUCTION | Cork County | Lissoran, Ballinspittle | 4 | *N/A | [5 empty] | Q4-2021
348 | SHIP CONSTRUCTION | Cork County | Convent Road, Doneraile | 17 | *N/A | [5 empty] | Q4-2022
349 | SHIP CONSTRUCTION | Cork County | Kearney's field Dunmanway | 13 | *N/A | [5 empty] | Q3-2022
350 | SHIP CONSTRUCTION | Cork County | Mill Road, Kanturk (Ceide Keating) | 13 | *N/A |  |  | Stage 3 approved Q4-2023, the scheme is now approved to proceed to tender.
351 | SHIP CONSTRUCTION | Cork County | Chapel Lane, Ballydehob, Co. Cork (Radharc na Scol, Greenmount Rd) | 12 | *N/A |  |  |  |  | Q1-2024
352 | SHIP CONSTRUCTION | Cork County | An Clós, Macroom (Sleaveen East) Phase 2 | 16 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
353 | SHIP CONSTRUCTION | Cork County | Coastguard Cottages, Lower Roads, Crosshaven, Co. Cork | 33 | *N/A |  | Stage 2 approved Q4-2022, full design/tender being prepared.
354 | SHIP CONSTRUCTION | Cork County | Beechgrove, Clonakilty | 6 | N/A | [5 empty] | Q2-2022
355 | SHIP CONSTRUCTION | Cork County | Porters Lane, Youghal, Co. Cork | 6 | N/A | Stage 1 approved Q1-2022, outline design and costs being prepared.
356 | SHIP CONSTRUCTION | Cork County | Baldwin Street, Mitchelstown | 14 | *N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
357 | SHIP CONSTRUCTION | Cork County | Millview Terrace, Dripsey | 8 | N/A | Stage 1 approved Q3-2023, outline design and costs being prepared.
358 | SHIP CONSTRUCTION | Cork County | Dr Patrick O'Sullivan Terrace, Aghada Cork | 4 | *N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
359 | SHIP CONSTRUCTION | Cork County | Ceithre Mhuire, Church Road, Durras, Co Cork | 8 | *N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
360 | SHIP CONSTRUCTION | Cork County | Broomfield West, Midleton | 37 | *N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
361 | SHIP CONSTRUCTION | Cork County | St Gobnaits, Ballyvourney | 8 | *N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
362 | SHIP CONSTRUCTION | Cork County | Radharc na Croise, Crosshaven, Co. Cork | 8 | *N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
363 | SHIP CONSTRUCTION | Cork County | Kilmallock Road, Charleville Co. Cork | 43 | *N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
364 | SHIP Accel MMC | Cork County | Clontead Beg, Coachford, Co. Cork | 26 | N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
365 | SHIP Accel MMC | Cork County | Hegarty Street, Millstreet, Co. Cork | 26 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
366 | CAS CONSTRUCTION TURNKEY | Cork County | Ardmanagh, Schull | 12 | Túath Housing Association Ltd |  |  |  |  | Q2-2023
367 | CAS CONSTRUCTION TURNKEY | Cork County | 1-10 Vickerys Inn, New Street Bantry | 10 | Peter McVerry Trust Ltd | [5 empty] | Q4-2022
368 | CAS CONSTRUCTION TURNKEY | Cork County | Apartment 1-10, Main Street, Charleville | 9 | Peter McVerry Trust Ltd | [5 empty] | Q4-2022
369 | CAS CONSTRUCTION TURNKEY | Cork County | Mullavale, Castletownroche | 8 | Respond | [5 empty] | Q4-2022
370 | CAS CONSTRUCTION RENEWAL | Cork County | 8 Harbour Row, Cobh | 5 | Óglaigh Náisiúnta na hÉireann (O.N.E.) | [5 empty] | Q3-2022
371 | CAS CONSTRUCTION RENEWAL | Cork County | Apt 1-4, 36 South Main Street, Youghal | 4 | Focus Ireland |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
372 | CAS CONSTRUCTION RENEWAL | Cork County | Apt 1-6 Bank House, Strand Street, Passage West | 6 | Focus Ireland |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
373 | CAS CONSTRUCTION | Cork County | Bantry Convent, Church and Convent Buildings, Bantry | 18 | Cluid Housing Association | [5 empty] | Q4-2023
374 | CAS CONSTRUCTION | Cork County | Masseytown, Macroom | 19 | Túath Housing Association Ltd |  |  | Stage 3 approved Q1-2024, the scheme is now approved to proceed to tender.
375 | CAS CONSTRUCTION | Cork County | Baile Bhuire, Macroom | 3 | Comhlacht Tithe Soisialta Agus ＆ Forbairt An Tsulain Teoranta | [5 empty] | Q3-2022
376 | CAS CONSTRUCTION | Cork County | Charleville, Church View, Love Lane, Charleville | 9 | Charleville Care Project Ltd | [5 empty] | Q4-2023
377 | CAS CONSTRUCTION | Cork County | St. Michaels, 36 Main Street, Bandon | 6 | Bandon Geriatric ＆ Community Council |  |  |  |  | Q3-2023
378 | CAS CONSTRUCTION | Cork County | Distillery Lane, Distillery Walk, Midleton | 6 | Midleton Lions Clubs Housing Association Limited |  | Stage 2 approved Q2-2024, full design/tender being prepared.
379 | CAS CONSTRUCTION | Cork County | Mardyke, Skibbereen | 8 | The Skibbereen Geriatric Society Limited |  | Stage 2 approved Q1-2023, full design/tender being prepared.
380 | CAS CONSTRUCTION | Cork County | Daniel O’Brien Terrace, Buttevant | 9 | Túath Housing Association Ltd |  |  |  |  | Q1-2022
381 | CAS CONSTRUCTION | Cork County | Millbrook Residential, Millbrook, New Road, Bandon | 19 | Bandon Geriatric ＆ Community Council | Stage 1 approved Q3-2023, outline design and costs being prepared.
382 | SHIP CONSTRUCTION TURNKEY | DLR | Kilternan Close | 22 | *N/A | [5 empty] | Q1-2021
383 | SHIP CONSTRUCTION TURNKEY | DLR | Kilternan Close, Dubin 18 | 17 | *N/A | [5 empty] | Q2-2024
384 | SHIP CONSTRUCTION TURNKEY | DLR | George's Street Upper, Dun Laoghaire, Co. Dublin | 5 | *N/A | [5 empty] | Q1-2021
385 | SHIP CONSTRUCTION TURNKEY | DLR | Hazelbrook Square, Nutgrove, Churchtown | 2 | *N/A | [5 empty] | Q4-2022
386 | SHIP CONSTRUCTION TURNKEY | DLR | Kilternan Close, Dubin 18 | 16 | *N/A |  |  |  |  | Q1-2023
387 | SHIP CONSTRUCTION TURNKEY | DLR | Dun Gaoithe, Sandyford, Dublin 18 | 2 | N/A | [5 empty] | Q4-2023
388 | SHIP CONSTRUCTION SINGLE STAGE | DLR | Corrig Road, Dalkey | 2 | *N/A | [5 empty] | Q4-2023
389 | SHIP CONSTRUCTION DESIGN BUILD | DLR | Rockville Green (Glenamuck Cottages) | 13 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
390 | SHIP CONSTRUCTION DESIGN BUILD | DLR | Ballyogan Square, Ballyogan | 67 | *N/A | [5 empty] | Q2-2023
391 | SHIP CONSTRUCTION DESIGN BUILD | DLR | Shanganagh Castle | 35 | *N/A |  |  |  |  | Q3-2022
392 | SHIP CONSTRUCTION DESIGN BUILD | DLR | Shanganagh Castle | 104 | *N/A |  |  |  |  | Q3-2022
393 | SHIP CONSTRUCTION DESIGN BUILD | DLR | Shanganagh Castle | 61 | *N/A |  |  |  |  | Q3-2022
394 | SHIP CONSTRUCTION DESIGN BUILD | DLR | Blackglen Road, Sandyford, Dublin 18 | 73 | N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
395 | SHIP CONSTRUCTION | DLR | Park House, 66 George's Street, Dun Laoghaire | 4 | *N/A |  |  |  |  | Q3-2022
396 | SHIP CONSTRUCTION | DLR | Broadford Rise | 21 | *N/A | [5 empty] | Q4-2021
397 | SHIP CONSTRUCTION | DLR | Ballyogan Avenue, Ballyogan | 2 | *N/A | [5 empty] | Q2-2021
398 | SHIP CONSTRUCTION | DLR | St. Laurence’s Park, Stillorgan, Co. Dublin | 48 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
399 | SHIP CONSTRUCTION | DLR | Moyola Court, Churchtown Lower, Dublin 14 | 4 | *N/A | [5 empty] | Q1-2024
400 | SHIP CONSTRUCTION | DLR | Ballyogan Rise, Ballyogan | 20 | *N/A |  | Stage 2 approved Q2-2020, full design/tender being prepared.
401 | SHIP CONSTRUCTION | DLR | Site at Roebuck Road, Clonskeagh, Dublin 14 | 4 | *N/A |  |  |  |  | Q1-2024
402 | SHIP CONSTRUCTION | DLR | 37A Rollins Villas, Sallynoggin | 1 | *N/A |  |  |  |  | Q1-2023
403 | SHIP CONSTRUCTION | DLR | Old Coastguard Cottages, Coal Harbour, Harbour Road | 4 | *N/A | [5 empty] | Q4-2023
404 | SHIP CONSTRUCTION | DLR | Cross Avenue, Dún Laoghaire, Co. Dublin | 4 | *N/A |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
405 | SHIP CONSTRUCTION | DLR | Infill Site Adjacent to 4 Rockville Drive, Glenamuck, Co. Dublin | 1 | N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
406 | SHIP Accel MMC | DLR | Ballyman | 150 | *N/A | Stage 1 approved Q2-2023, outline design and costs being prepared.
407 | SHIP Accel MMC | DLR | Lehaunstown | 109 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
408 | SHIP Accel MMC | DLR | Old Connaught | 60 | *N/A | Stage 1 approved Q2-2023, outline design and costs being prepared.
409 | CAS CONSTRUCTION RENEWAL | DLR | 58-59 Patrick Street, Dún Laoghaire, Co. Dublin | 8 | Peter McVerry Trust Ltd | [5 empty] | Q4-2022
410 | CAS CONSTRUCTION | DLR | 30 Obelisk Walk, Blackrock | 4 | St. John of God Housing Association Ltd | [5 empty] | Q4-2021
411 | CAS CONSTRUCTION | DLR | DVR @ Kilcross, Sandyford | 12 | Sonas Domestic Violence Charity Ltd |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
412 | CAS CONSTRUCTION | DLR | Saint Anne's Court, Ballinteer, D16 (CABHRÚ) | 6 | Cabhrú |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
413 | SHIP DIALOG | Donegal | Drumrooske West | 25 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
414 | SHIP DIALOG | Donegal | Brookfield, Donegal Town | 8 | *N/A | [5 empty] | Q1-2022
415 | SHIP DIALOG | Donegal | Meadowfield, Convoy | 11 | *N/A |  |  |  |  | Q1-2024
416 | SHIP DIALOG | Donegal | Donegal Road, Ballybofey | 3 | *N/A |  |  |  |  | Q2-2024
417 | SHIP DIALOG | Donegal | Admiran, Stranorlar | 52 | *N/A |  |  | Stage 3 approved Q4-2019, the scheme is now approved to proceed to tender.
418 | SHIP DIALOG | Donegal | Rockview, Carrickboy, Ballyshannon | 5 | *N/A | [5 empty] | Q4-2022
419 | SHIP DIALOG | Donegal | Brookfield, Donegal Town | 12 | *N/A | [5 empty] | Q4-2022
420 | SHIP DIALOG | Donegal | Brookfield, Donegal Town | 14 | *N/A | [5 empty] | Q4-2022
421 | SHIP DIALOG | Donegal | Meadowfield, Convoy | 13 | *N/A |  |  |  |  | Q1-2024
422 | SHIP DIALOG | Donegal | Magheraclogher, Bunbeg, Gweedore | 11 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
423 | SHIP DIALOG | Donegal | Magheraclogher, Bunbeg, Gweedore | 8 | N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
424 | SHIP DIALOG | Donegal | Drumrooske West | 6 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
425 | SHIP DIALOG | Donegal | Pearse & Paddy Harte Road, Letterkenny | 28 | N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
426 | SHIP DIALOG | Donegal | Windyhall, Letterkenny | 20 | N/A |  |  |  |  | Q3-2024
427 | SHIP DIALOG | Donegal | Donegal Road, Ballybofey | 4 | *N/A |  |  |  |  | Q2-2024
428 | SHIP DIALOG | Donegal | Magheraclogher, Bunbeg, Gweedore | 10 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
429 | SHIP DIALOG | Donegal | College Farm Road, Letterkenny, Donegal | 15 | N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
430 | SHIP DIALOG | Donegal | Donegal Road, Ballybofey | 6 | N/A |  |  |  |  | Q2-2024
431 | SHIP CONSTRUCTION TURNKEY | Donegal | Creeslough | 11 | *N/A |  |  |  |  | Q1-2023
432 | SHIP CONSTRUCTION SINGLE STAGE | Donegal | SRD Loughanure Annagry | 1 | *N/A | [5 empty] | Q3-2022
433 | SHIP CONSTRUCTION SINGLE STAGE | Donegal | SRD Meenderrynasloe, Annagry | 1 | *N/A | [5 empty] | Q3-2022
434 | SHIP CONSTRUCTION SINGLE STAGE | Donegal | SRD, Largymore, Kilcar | 1 | *N/A |  |  |  |  | Q3-2024
435 | SHIP CONSTRUCTION SINGLE STAGE | Donegal | The Meadows, Buncrana | 1 | *N/A | [5 empty] | Q4-2023
436 | SHIP CONSTRUCTION SINGLE STAGE | Donegal | Masiness, Creeslough | 3 | *N/A |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
437 | SHIP CONSTRUCTION SINGLE STAGE | Donegal | Killylastin, Letterkenny | 11 | N/A |  |  |  |  | Q4-2023
438 | SHIP CONSTRUCTION SINGLE STAGE | Donegal | SRD, Cruckakeehan, Annagry, Donegal | 1 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
439 | SHIP CONSTRUCTION RENEWAL | Donegal | 23 & 24 Claredon Drive, Drumlongher, Donegal | 2 | N/A | [5 empty] | Q4-2023
440 | SHIP CONSTRUCTION RENEWAL | Donegal | 17 Ballina Cottages, Falcarragh | 1 | *N/A | [5 empty] | Q3-2023
441 | SHIP CONSTRUCTION RENEWAL | Donegal | Old Garda Station, Malin | 2 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
442 | SHIP CONSTRUCTION RENEWAL | Donegal | Belcruit, Kincasslagh | 1 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
443 | SHIP CONSTRUCTION RENEWAL | Donegal | 213 Ard Baithin, Johnston, Donegal | 1 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
444 | SHIP CONSTRUCTION RENEWAL | Donegal | Letterkenny Road, Convoy | 1 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
445 | SHIP CONSTRUCTION RENEWAL | Donegal | 2 Malin Road, Moville, Donegal | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
446 | SHIP CONSTRUCTION RENEWAL | Donegal | 1 St. Rita's, Malin Road, Moville, Donegal | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
447 | SHIP CONSTRUCTION RENEWAL | Donegal | 65 Croaghan Heights, Lifford, Donegal | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
448 | SHIP CONSTRUCTION DESIGN BUILD | Donegal | Barrick Hill, Carndonagh | 21 | N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
449 | SHIP CONSTRUCTION DESIGN BUILD | Donegal | Radharc na Tra, Breige, Malin - Phase 4 | 9 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
450 | SHIP CONSTRUCTION DESIGN BUILD | Donegal | Carn Road, Gleneely | 10 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
451 | SHIP CONSTRUCTION | Donegal | Meadow Hill, Raphoe | 11 | *N/A |  |  |  |  | Q3-2024
452 | SHIP CONSTRUCTION | Donegal | Long Lane, Letterkenny | 29 | *N/A | [5 empty] | Q2-2021
453 | SHIP CONSTRUCTION | Donegal | Rockytown, Buncrana (Phase 1) | 21 | *N/A | [5 empty] | Q2-2022
454 | SHIP CONSTRUCTION | Donegal | Pound Street, Dunfanaghy | 4 | *N/A | [5 empty] | Q3-2022
455 | SHIP CONSTRUCTION | Donegal | Railway Park, Drumrooske, Donegal Town | 24 | *N/A | [5 empty] | Q2-2021
456 | SHIP CONSTRUCTION | Donegal | Railway Park, Drumrooske, Donegal Town | 24 | *N/A | [5 empty] | Q4-2023
457 | SHIP CONSTRUCTION | Donegal | Trusk Road, Ballybofey | 19 | *N/A |  |  |  |  | Q3-2022
458 | SHIP CONSTRUCTION | Donegal | Crana Crescent, Buncrana | 16 | *N/A |  |  |  |  | Q3-2023
459 | SHIP CONSTRUCTION | Donegal | Drumacrin, Bundoran | 42 | *N/A |  |  |  |  | Q4-2023
460 | SHIP CONSTRUCTION | Donegal | Gallow's Lane, Lifford | 29 | *N/A |  |  |  |  | Q4-2022
461 | SHIP CONSTRUCTION | Donegal | Chapel Road, Dungloe | 43 | *N/A |  |  |  |  | Q3-2024
462 | SHIP CONSTRUCTION | Donegal | Airde Na Buaile, Oran Hill, Kilmacrennan, Letterkenny | 30 | *N/A |  |  |  |  | Q3-2024
463 | SHIP CONSTRUCTION | Donegal | Rockytown, Buncrana (Phase 2) | 54 | *N/A |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
464 | SHIP CONSTRUCTION | Donegal | Phase 3, Cois Abhainn, St. Johnston, Donegal | 30 | N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
465 | SHIP CONSTRUCTION | Donegal | Former Fire Station, Main Street, Stranorlar, Donegal | 8 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
466 | CAS CONSTRUCTION RENEWAL | Donegal | Cois Locha, Dungloe | 11 | Cluid Housing Association | [5 empty] | Q4-2023
467 | CAS CONSTRUCTION RENEWAL | Donegal | Fairhill Lodge, Dungloe | 8 | Respond |  |  |  |  | Q3-2023
468 | CAS CONSTRUCTION | Donegal | Glenrowan House, Drumkeen, Stranorlar | 5 | Apex Housing Association | [5 empty] | Q4-2023
469 | CAS CONSTRUCTION | Donegal | Cois Locha, Meenmore, Dungloe | 15 | County Donegal Parents and Friends Housing Association Ltd | [5 empty] | Q3-2022
470 | CAS CONSTRUCTION | Donegal | Raphoe Road, Castlefinn | 34 | Habinteg Housing Association (Ireland) Ltd |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
471 | SHIP DIALOG | Dublin City | Regen O'Devaney Gardens - SH from Mixed Tenure Project Flat Complex | 164 | *N/A |  |  |  |  | Q1-2023
472 | SHIP DIALOG | Dublin City | Regen O'Devaney Gardens - SH from Mixed Tenure Project Flat Complex | 12 | *N/A |  |  |  |  | Q1-2023
473 | SHIP DIALOG | Dublin City | Regen O'Devaney Gardens - SH from Mixed Tenure Project Flat Complex | 104 | *N/A |  |  |  |  | Q1-2023
474 | SHIP CONSTRUCTION TURNKEY | Dublin City | 88-89 Drimnagh Road Dublin 12 | 24 | *N/A | [5 empty] | Q4-2022
475 | SHIP CONSTRUCTION TURNKEY | Dublin City | St. Pancras, Harolds Cross, Dublin 6 | 4 | *N/A | [5 empty] | Q2-2021
476 | SHIP CONSTRUCTION TURNKEY | Dublin City | Core 4, Block 4 Charlemont Square, Dublin 2 | 15 | *N/A | [5 empty] | Q2-2022
477 | SHIP CONSTRUCTION TURNKEY | Dublin City | Moss Street/Gloucester Street, Dublin 2 | 21 | *N/A | [5 empty] | Q4-2022
478 | SHIP CONSTRUCTION TURNKEY | Dublin City | York Road, Ringsend, Dublin 4 | 26 | *N/A |  |  |  |  | Q1-2023
479 | SHIP CONSTRUCTION TURNKEY | Dublin City | Blocks 46 and 49 Park West Pointe, Dublin 10 | 17 | *N/A |  |  |  | Stage 4 approved Q2-2023, the scheme is fully approved.
480 | SHIP CONSTRUCTION TURNKEY | Dublin City | Clanbrassil Street Upper, Dublin 8 | 27 | *N/A |  |  |  |  | Q1-2023
481 | SHIP CONSTRUCTION TURNKEY | Dublin City | (Block B) Newtown, Malahide Road, Dublin 13 | 100 | *N/A | [5 empty] | Q2-2024
482 | SHIP CONSTRUCTION TURNKEY | Dublin City | 194-198 Clonliffe Road, Drumcondra, Dublin 9 | 33 | *N/A |  |  |  |  | Q2-2024
483 | SHIP CONSTRUCTION TURNKEY | Dublin City | (Block B) Newtown, Malahide Road, Dublin 13 | 22 | *N/A | [5 empty] | Q2-2024
484 | SHIP CONSTRUCTION TURNKEY | Dublin City | (Block B) Newtown, Malahide Road, Dublin 13 | 39 | *N/A | [5 empty] | Q3-2024
485 | SHIP CONSTRUCTION SINGLE STAGE | Dublin City | 31 Croftwood Drive, Cherry Orchard, Dublin 10 | 2 | N/A |  |  |  | Stage 4 approved Q4-2022, the scheme is fully approved.
486 | SHIP CONSTRUCTION SINGLE STAGE | Dublin City | 371-373 North Circular Road, Phibsboro, Dublin 7 | 4 | *N/A |  |  |  | Stage 4 approved Q2-2023, the scheme is fully approved.
487 | SHIP CONSTRUCTION SINGLE STAGE | Dublin City | 114-116 Capel Street, Dublin 1 | 4 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
488 | SHIP CONSTRUCTION RENEWAL | Dublin City | 25 St James's Terrace, Dublin 8 | 1 | *N/A | [5 empty] | Q4-2022
489 | SHIP CONSTRUCTION RENEWAL | Dublin City | 77A The Coombe, Dublin 8 | 1 | *N/A | [5 empty] | Q4-2022
490 | SHIP CONSTRUCTION RENEWAL | Dublin City | 77 The Coombe, Dublin 8 | 1 | *N/A | [5 empty] | Q4-2022
491 | SHIP CONSTRUCTION RENEWAL | Dublin City | 27 Berryfield Road, Finglas, Dublin 11 | 1 | *N/A | [5 empty] | Q4-2022
492 | SHIP CONSTRUCTION RENEWAL | Dublin City | 51 Seville Place, North Dock, Dublin 1 | 1 | *N/A | [5 empty] | Q4-2022
493 | SHIP CONSTRUCTION RENEWAL | Dublin City | 78 The Coombe, Dublin 8 | 1 | *N/A | [5 empty] | Q4-2022
494 | SHIP CONSTRUCTION RENEWAL | Dublin City | 31 Cromcastle Drive, Kilmore West, Dublin 5 | 1 | *N/A |  |  | Stage 3 approved Q4-2022, the scheme is now approved to proceed to tender.
495 | SHIP CONSTRUCTION RENEWAL | Dublin City | Cromwellsfort Road, Walkinstown, Dublin 12 | 2 | N/A |  |  |  |  | TBC
496 | SHIP CONSTRUCTION RENEWAL | Dublin City | Cherry Orchard Grove, Cherry Orchard, Dublin 10 | 1 | *N/A |  |  |  |  | TBC
497 | SHIP CONSTRUCTION RENEWAL | Dublin City | Larkhill Road, Dublin 9 | 1 | *N/A | [5 empty] | Q4-2022
498 | SHIP CONSTRUCTION RENEWAL | Dublin City | Ravensdale Road, East Wall, Dublin 3 | 1 | *N/A | [5 empty] | Q4-2022
499 | SHIP CONSTRUCTION RENEWAL | Dublin City | O'Dwyer Road, Walkinstown, Dublin 12 | 1 | *N/A | [5 empty] | Q4-2022
500 | SHIP CONSTRUCTION RENEWAL | Dublin City | Ratoath Avenue, Finglas South, Dublin 11 | 1 | *N/A | [5 empty] | Q4-2022
501 | SHIP CONSTRUCTION RENEWAL | Dublin City | St. Brendan's Park, Coolock, Dublin 5 | 1 | *N/A | [5 empty] | Q4-2022
502 | SHIP CONSTRUCTION RENEWAL | Dublin City | Montpelier Hill, Stoneybatter, Dublin 7 | 1 | *N/A | [5 empty] | Q4-2022
503 | SHIP CONSTRUCTION RENEWAL | Dublin City | South Circular Road, Dublin 8 | 4 | *N/A | [5 empty] | Q4-2022
504 | SHIP CONSTRUCTION RENEWAL | Dublin City | 11 Annamoe Terrace, Dublin 7 | 1 | *N/A | [5 empty] | Q4-2023
505 | SHIP CONSTRUCTION RENEWAL | Dublin City | 15 Parkview Green, Finglas, Dublin 11 | 1 | *N/A | [5 empty] | Q4-2022
506 | SHIP CONSTRUCTION RENEWAL | Dublin City | 68B St. Brendan's Park, Coolock, Dublin 5 | 1 | *N/A |  |  |  |  | TBC
507 | SHIP CONSTRUCTION RENEWAL | Dublin City | Finglas Park, Finglas, Dublin 11 | 1 | *N/A | [5 empty] | Q4-2022
508 | SHIP CONSTRUCTION RENEWAL | Dublin City | 27A & 29A Clune Road, Finglas | 2 | *N/A |  |  |  |  | TBC
509 | SHIP CONSTRUCTION RENEWAL | Dublin City | Fitzwilliam Quay, Dublin 4 | 15 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
510 | SHIP CONSTRUCTION RENEWAL | Dublin City | 146-146A Bunting Road, Dublin 12 | 2 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
511 | SHIP CONSTRUCTION RENEWAL | Dublin City | 239 Captain's Road, Crumlin, Dublin 12 | 1 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
512 | SHIP CONSTRUCTION RENEWAL | Dublin City | 201 Larkhill Road, Dublin 9 | 1 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
513 | SHIP CONSTRUCTION RENEWAL | Dublin City | 56 Marigold Grove, Darndale, Dublin 17 | 1 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
514 | SHIP CONSTRUCTION RENEWAL | Dublin City | 168 St. Donagh's Road, Dublin 13 | 1 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
515 | SHIP CONSTRUCTION RENEWAL | Dublin City | 66 Clonliffe Road, Drumcondra, Dublin 3 | 1 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
516 | SHIP CONSTRUCTION RENEWAL | Dublin City | 12 Ferguson Road, Drumcondra, Dublin 9 | 1 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
517 | SHIP CONSTRUCTION RENEWAL | Dublin City | 109 Landen Road, Ballyfermot, Dublin 10 | 1 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
518 | SHIP CONSTRUCTION RENEWAL | Dublin City | 11 Rutland Street Lower, Dublin 1 | 1 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
519 | SHIP CONSTRUCTION RENEWAL | Dublin City | 15 / 15A / 15B Ratoath Avenue, Finglas, Dublin 11 | 3 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
520 | SHIP CONSTRUCTION DESIGN BUILD | Dublin City | Bunratty Road | 78 | *N/A | [5 empty] | Q3-2023
521 | SHIP CONSTRUCTION DESIGN BUILD | Dublin City | Bonham Street Dublin 8 | 57 | *N/A | [5 empty] | Q4-2023
522 | SHIP CONSTRUCTION DESIGN BUILD | Dublin City | Cork Street/Chamber Street Dublin 8 | 55 | *N/A | [5 empty] | Q4-2023
523 | SHIP CONSTRUCTION DESIGN BUILD | Dublin City | Springvale Chapelizod Dublin 8 | 71 | *N/A | [5 empty] | Q4-2023
524 | SHIP CONSTRUCTION | Dublin City | Cornamona, Ballyfermot, Dublin 12 | 61 | *N/A | [5 empty] | Q2-2023
525 | SHIP CONSTRUCTION | Dublin City | North King Street, - Sean Foster Place, Dublin 7 | 30 | *N/A | [5 empty] | Q4-2022
526 | SHIP CONSTRUCTION | Dublin City | St. Finbar's Court, Flat Complex | 46 | *N/A |  |  |  |  | Q2-2023
527 | SHIP CONSTRUCTION | Dublin City | Regen Dominick Street East Flat Complex | 72 | *N/A | [5 empty] | Q4-2022
528 | SHIP CONSTRUCTION | Dublin City | Regen O'Devaney Gardens - Phase 1A Flat Complex | 56 | *N/A | [5 empty] | Q4-2022
529 | SHIP CONSTRUCTION | Dublin City | Glin Court, Flat Complex | 32 | *N/A |  |  |  |  | Q2-2023
530 | SHIP CONSTRUCTION | Dublin City | Cromcastle Court & Old Coalyard Site, Flat Complex | 149 | *N/A |  | Stage 2 approved Q3-2023, full design/tender being prepared.
531 | SHIP CONSTRUCTION | Dublin City | Crumlin Road - Rafters Lane, Flat Complex | 38 | *N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
532 | SHIP CONSTRUCTION | Dublin City | Kildonan Road, Finglas, Dublin 11 | 152 | *N/A | Stage 1 approved Q2-2020, outline design and costs being prepared.
533 | SHIP CONSTRUCTION | Dublin City | Regen MT Lands at Emmet Road | 137 | *N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
534 | SHIP CONSTRUCTION | Dublin City | Sarsfield Lands, Sarsfield Road, Ballyfermot, Dublin 10 | 176 | *N/A | Stage 1 approved Q3-2022, outline design and costs being prepared.
535 | SHIP CONSTRUCTION | Dublin City | Regen St. Teresa’s Gardens Donore Project Flat Complex | 154 | *N/A |  | Stage 2 approved Q1-2023, full design/tender being prepared.
536 | SHIP CONSTRUCTION | Dublin City | Regen St. Andrews Court, Flat Complex | 33 | *N/A |  | Stage 2 approved Q3-2023, full design/tender being prepared.
537 | SHIP CONSTRUCTION | Dublin City | Bluebell Waterways, Bluebell Road, Bluebell, Dublin 12 | 155 | *N/A | Stage 1 approved Q2-2021, outline design and costs being prepared.
538 | SHIP CONSTRUCTION | Dublin City | St. Anne's Court, All Saints Drive, Flat Complex | 102 | *N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
539 | SHIP CONSTRUCTION | Dublin City | Grand Canal Basin, Long's Place, Dublin 8 | 108 | N/A | Stage 1 approved Q3-2023, outline design and costs being prepared.
540 | SHIP CONSTRUCTION | Dublin City | Cromcastle Underpass, Coolock, Dublin 5 | 13 | N/A |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
541 | SHIP CONSTRUCTION | Dublin City | 38/39 Bolton Street, Dublin 1 | 6 | *N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
542 | SHIP CONSTRUCTION | Dublin City | Cherry Orchard Point | 161 | *N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
543 | SHIP CONSTRUCTION | Dublin City | Regen Dominick St West, Flat Complex | 75 | N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
544 | SHIP CONSTRUCTION | Dublin City | National Centre for Research and Remembrance, Railway St., D.1 | 18 | N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
545 | SHIP CONSTRUCTION | Dublin City | 43A Montpelier Gardens, Dublin 7 | 2 | *N/A | Stage 1 approved Q1-2023, outline design and costs being prepared.
546 | REGENERATION | Dublin City | Dorset Street, Flat Complex | 163 | *N/A |  |  |  |  | Q2-2024
547 | REGENERATION | Dublin City | Matt Talbot Court, Flat Complex | 92 | *N/A |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
548 | REGENERATION | Dublin City | Constitution Hill, Flat Complex | 46 | *N/A |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
549 | REGENERATION | Dublin City | Pearse House (Blocks L,M,N &P) Flat Complex | 75 | *N/A | Stage 1 approved Q2-2021, outline design and costs being prepared.
550 | REGENERATION | Dublin City | School Street Thomas Court Bawn Flat Complex | 80 | *N/A | Stage 1 approved Q3-2021, outline design and costs being prepared.
551 | REGENERATION | Dublin City | Oliver Bond Social Housing Delivery Flat Complex | 48 | *N/A | Stage 1 approved Q1-2022, outline design and costs being prepared.
552 | REGENERATION | Dublin City | Glovers Court, York Street, Flat Complex | 53 | N/A | Stage 1 approved Q2-2022, outline design and costs being prepared.
553 | REGENERATION | Dublin City | Ballybough House Pilot Amalgamation Project | 1 | *N/A | [5 empty] | Q3-2022
554 | REGENERATION | Dublin City | Constitution Hill, Flat Complex | 76 | *N/A |  | Stage 2 approved Q4-2022, full design/tender being prepared.
555 | REGENERATION | Dublin City | School Street Thomas Court Bawn Flat Complex | 35 | *N/A | Stage 1 approved Q3-2021, outline design and costs being prepared.
556 | CAS CONSTRUCTION TURNKEY | Dublin City | Block 70, The Plaza, Parkwest, Dublin 12 | 43 | Túath Housing Association Ltd | [5 empty] | Q2-2022
557 | CAS CONSTRUCTION TURNKEY | Dublin City | 9-40 Walker Grove, Parkside, Dublin 13 | 32 | Túath Housing Association Ltd | [5 empty] | Q3-2022
558 | CAS CONSTRUCTION TURNKEY | Dublin City | Huband Road, Bluebell, Dublin 12 | 6 | Tiglin Challenge |  |  |  | Stage 4 approved Q4-2022, the scheme is fully approved.
559 | CAS CONSTRUCTION TURNKEY | Dublin City | 64-69 St James Court, Dublin 8 | 6 | Peter McVerry Trust Ltd | [5 empty] | Q4-2022
560 | CAS CONSTRUCTION TURNKEY | Dublin City | 10 Fairview Avenue Lower, Dublin 3 | 4 | Focus Ireland |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
561 | CAS CONSTRUCTION TURNKEY | Dublin City | 54 Nash Street , Inchicore, Dublin 8 | 4 | Simon Community : Dublin Simon | [5 empty] | Q4-2023
562 | CAS CONSTRUCTION TURNKEY | Dublin City | Parkview, Ballymun, Dublin 11 | 32 | Túath Housing Association Ltd |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
563 | CAS CONSTRUCTION TURNKEY | Dublin City | 62A Cardiffbridge Road, Finglas, Dublin 11 | 1 | Peter McVerry Trust Ltd | [5 empty] | Q2-2023
564 | CAS CONSTRUCTION TURNKEY | Dublin City | 59A Inchicore Road, Inchicore, Dublin 8 | 6 | Peter McVerry Trust Ltd | [5 empty] | Q4-2023
565 | CAS CONSTRUCTION SINGLE STAGE | Dublin City | 61 & 63 Rathoath Avenue, Finglas, Dublin 11 | 6 | Arlington Novas Ireland Ltd | [5 empty] | Q4-2022
566 | CAS CONSTRUCTION RENEWAL | Dublin City | Ellis Court, Dublin | 22 | Túath Housing Association Ltd | [5 empty] | Q4-2022
567 | CAS CONSTRUCTION RENEWAL | Dublin City | 190 -192 Moore Haven, Drumcondra Road Upper, Dublin 9. | 8 | DePaul Housing |  |  |  | Stage 4 approved Q1-2022, the scheme is fully approved.
568 | CAS CONSTRUCTION RENEWAL | Dublin City | Unit A - D, 133 Upper Rathmines Road, Dublin 6 | 4 | HAIL |  |  |  |  | Q1-2023
569 | CAS CONSTRUCTION RENEWAL | Dublin City | Units A-D, 14 Walkinstown Green, Dublin 12 | 4 | HAIL |  |  |  |  | Q1-2023
570 | CAS CONSTRUCTION RENEWAL | Dublin City | Unit A-C, 340 Ballyfermot Road, Dublin 10 | 3 | HAIL | [5 empty] | Q2-2024
571 | CAS CONSTRUCTION RENEWAL | Dublin City | Eagle Lodge, Leinster Road West, Dublin 6 | 18 | Peter McVerry Trust Ltd | [5 empty] | Q4-2023
572 | CAS CONSTRUCTION RENEWAL | Dublin City | 22 Claddagh Green, Ballyfermot, Dublin 10 | 1 | Peter McVerry Trust Ltd | [5 empty] | Q1-2023
573 | CAS CONSTRUCTION RENEWAL | Dublin City | Haddington Road, Dublin 4 | 18 | Peter McVerry Trust Ltd | [5 empty] | Q1-2021
574 | CAS CONSTRUCTION RENEWAL | Dublin City | Kings Court, Aughrim St, Dublin 7 | 1 | Simon Community : Dublin Simon | [5 empty] | Q3-2023
575 | CAS CONSTRUCTION RENEWAL | Dublin City | 20 Shanliss Grove, Santry, Dublin 9 | 1 | DePaul Housing |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
576 | CAS CONSTRUCTION RENEWAL | Dublin City | 147 Hardwicke Street, Dublin 7 | 1 | Simon Community : Dublin Simon | [5 empty] | Q4-2023
577 | CAS CONSTRUCTION RENEWAL | Dublin City | 5 Portland Lock, Portland Place, Dublin 1 | 1 | Simon Community : Dublin Simon | [5 empty] | Q4-2023
578 | CAS CONSTRUCTION RENEWAL | Dublin City | Ivy Views, Blackhorse Avenue, Dublin 7 | 6 | DePaul Housing |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
579 | CAS CONSTRUCTION RENEWAL | Dublin City | 25 The Steeples, St. Laurence Road, Dublin 20 | 1 | Simon Community : Dublin Simon | [5 empty] | Q2-2024
580 | CAS CONSTRUCTION | Dublin City | 180-187 Townsend Street, Dublin 2 | 20 | Peter McVerry Trust Ltd |  |  |  |  | Q4-2022
581 | CAS CONSTRUCTION | Dublin City | 26 New Street South, Dublin 8 | 8 | Peter McVerry Trust Ltd | [5 empty] | Q1-2021
582 | CAS CONSTRUCTION | Dublin City | 55B Arbour Hill, Dublin 7 | 14 | Simon Community : Dublin Simon |  |  |  |  | Q3-2023
583 | CAS CONSTRUCTION | Dublin City | St. Michael's Estate, Inchicore, Dublin 8 - Housing Pilot Project | 52 | Circle Voluntary Housing Association Ltd |  |  |  |  | Q3-2022
584 | CAS CONSTRUCTION | Dublin City | Sarsfield Road, Ballyfermot, Dublin 10 | 6 | Respond |  | Stage 2 approved Q1-2022, full design/tender being prepared.
585 | CAS CONSTRUCTION | Dublin City | 25-26 Ushers Island Ushers Quay Dublin 8 | 0 | Simon Community : Dublin Simon |  |  |  |  | Q4-2021
586 | CAS CONSTRUCTION | Dublin City | 378a North Circular Road, Phibsborough, Dublin 7. | 8 | Simon Community : Dublin Simon | Stage 1 approved Q1-2023, outline design and costs being prepared.
587 | CAS CONSTRUCTION | Dublin City | Sean Mc Dermott Street, Dublin 1 | 8 | Simon Community : Dublin Simon |  | Stage 2 approved Q1-2023, full design/tender being prepared.
588 | CAS CONSTRUCTION | Dublin City | 108 Newbrook Avenue, Donaghmede, Dublin 13 | 1 | St. Michael's House |  | Stage 2 approved Q4-2023, full design/tender being prepared.
589 | SHIP DIALOG | Fingal | Ballymastone, Donabate | 19 | *N/A |  |  |  | Stage 4 approved Q4-2021, the scheme is fully approved.
590 | SHIP DIALOG | Fingal | Ballymastone, Donabate | 67 | *N/A |  |  |  | Stage 4 approved Q4-2021, the scheme is fully approved.
591 | SHIP DIALOG | Fingal | Ballymastone, Donabate | 86 | *N/A |  |  |  | Stage 4 approved Q4-2021, the scheme is fully approved.
592 | SHIP DIALOG | Fingal | Ballymastone, Donabate | 64 | *N/A |  |  |  | Stage 4 approved Q4-2021, the scheme is fully approved.
593 | SHIP DIALOG | Fingal | Church Fields, Phase 3A, Mulhuddart, Dublin 15 | 13 | *N/A |  |  |  | Stage 4 approved Q4-2022, the scheme is fully approved.
594 | SHIP DIALOG | Fingal | Church Fields, Phase 3A, Mulhuddart, Dublin 15 | 27 | *N/A |  |  |  | Stage 4 approved Q4-2022, the scheme is fully approved.
595 | SHIP CONSTRUCTION TURNKEY | Fingal | Killhedge Lane, Dun Emer, Lusk | 7 | *N/A | [5 empty] | Q4-2022
596 | SHIP CONSTRUCTION TURNKEY | Fingal | Station Road, Portmarnock | 19 | *N/A | [5 empty] | Q4-2023
597 | SHIP CONSTRUCTION TURNKEY | Fingal | Station Road, Portmarnock | 4 | *N/A | [5 empty] | Q3-2024
598 | SHIP CONSTRUCTION TURNKEY | Fingal | Hayestown, Rush | 8 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
599 | SHIP CONSTRUCTION TURNKEY | Fingal | Hands Lane, Lusk | 12 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
600 | SHIP CONSTRUCTION TURNKEY | Fingal | Kenure, Rush | 80 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
601 | SHIP CONSTRUCTION TURNKEY | Fingal | Hayestown, Rush | 2 | *N/A | [5 empty] | Q4-2023
602 | SHIP CONSTRUCTION TURNKEY | Fingal | Hampton Gardens Close, Balbriggan | 4 | *N/A | [5 empty] | Q4-2023
603 | SHIP CONSTRUCTION TURNKEY | Fingal | Hampton Gardens Close, Balbriggan | 1 | *N/A | [5 empty] | Q3-2024
604 | SHIP CONSTRUCTION TURNKEY | Fingal | Station Road, Portmarnock | 18 | *N/A |  |  |  |  | Q1-2023
605 | SHIP CONSTRUCTION SINGLE STAGE | Fingal | Bowden Court (Outlands), Rathbeale Road, Swords | 11 | *N/A | [5 empty] | Q3-2024
606 | SHIP CONSTRUCTION SINGLE STAGE | Fingal | 50 Sheepmoor Avenue, Blanchardstown, D15 | 1 | *N/A | [5 empty] | Q4-2023
607 | SHIP CONSTRUCTION SINGLE STAGE | Fingal | 169a Clonsilla Road, Blanchardstown, Dublin 15 | 1 | *N/A | [5 empty] | Q4-2023
608 | SHIP CONSTRUCTION RENEWAL | Fingal | St Ita's, Portrane Avenue, Protrane | 5 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
609 | SHIP CONSTRUCTION RENEWAL | Fingal | St Ita's, Portrane Avenue, Protrane | 3 | *N/A | [5 empty] | Q2-2023
610 | SHIP CONSTRUCTION RENEWAL | Fingal | St Ita's, Portrane Avenue, Protrane | 6 | *N/A | [5 empty] | Q4-2023
611 | SHIP CONSTRUCTION DESIGN BUILD | Fingal | Church Fields, Phase 2B, Mulhuddart, Dublin 15 | 49 | *N/A | [5 empty] | Q4-2022
612 | SHIP CONSTRUCTION DESIGN BUILD | Fingal | Church Fields, Phase 2B, Mulhuddart, Dublin 15 | 18 | *N/A | [5 empty] | Q3-2023
613 | SHIP CONSTRUCTION | Fingal | Wellview | 20 | *N/A | [5 empty] | Q4-2022
614 | SHIP CONSTRUCTION | Fingal | Cappaghfinn, Cappagh Road Finglas - Phase 3 | 60 | *N/A | [5 empty] | Q4-2022
615 | SHIP CONSTRUCTION | Fingal | Ballough Place (Leonards Garage), Lusk | 10 | *N/A |  |  |  |  | Q2-2023
616 | SHIP CONSTRUCTION | Fingal | Katie Hunt's Cottage, Church Road, Lusk | 5 | *N/A | [5 empty] | Q3-2024
617 | SHIP CONSTRUCTION | Fingal | 30-32 North Street, Swords | 13 | *N/A |  | Stage 2 approved Q1-2023, full design/tender being prepared.
618 | SHIP CONSTRUCTION | Fingal | Seatown Apartments, Seatown Road, Swords | 36 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
619 | SHIP CONSTRUCTION | Fingal | Cappaghfinn, Cappagh Road Finglas - Phase 3 | 9 | *N/A | [5 empty] | Q3-2023
620 | SHIP CONSTRUCTION | Fingal | Junction of Blakestown Road & Huntstown Way, Mulhuddart | 30 | N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
621 | SHIP CONSTRUCTION | Fingal | Remount, Lusk | 18 | *N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
622 | SHIP CONSTRUCTION | Fingal | Mourne View, Skerries | 14 | *N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
623 | SHIP CONSTRUCTION | Fingal | Woodside, Swords | 24 | *N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
624 | SHIP CONSTRUCTION | Fingal | Park Road, Kenure, Rush | 32 | *N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
625 | SHIP Accel MMC | Fingal | Holywell, Swords | 54 | *N/A |  | Stage 2 approved Q3-2023, full design/tender being prepared.
626 | SHIP Accel MMC | Fingal | Dublin Road, Swords | 32 | *N/A | Stage 1 approved Q2-2023, outline design and costs being prepared.
627 | SHIP Accel MMC | Fingal | Mayestown, Poppintree, Dublin 11 | 62 | *N/A |  | Stage 2 approved Q2-2023, full design/tender being prepared.
628 | SHIP Accel MMC | Fingal | Milton Terrace, Swords | 20 | *N/A | Stage 1 approved Q2-2023, outline design and costs being prepared.
629 | CAS CONSTRUCTION TURNKEY | Fingal | Kilmartin Grove, Hollystown, Dublin 15 | 15 | Túath Housing Association Ltd |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
630 | CAS CONSTRUCTION SINGLE STAGE | Fingal | 63 Hollystown Park, Holystown, Dublin 15 | 5 | Daughters Of Charity Of St Vincent De Paul | [5 empty] | Q4-2021
631 | CAS CONSTRUCTION RENEWAL | Fingal | Alderwood, Hollystown Dublin 15 | 5 | Marillac Housing Association | [5 empty] | Q4-2022
632 | CAS CONSTRUCTION RENEWAL | Fingal | Abbeyglen, 47 Dublin Road, Swords | 5 | Praxis Housing Association | [5 empty] | Q4-2022
633 | CAS CONSTRUCTION | Fingal | Killhedge Lane Dun Emer | 31 | Túath Housing Association Ltd | [5 empty] | Q3-2024
634 | CAS CONSTRUCTION | Fingal | 22 College Street, Baldoyle | 4 | Cluid Housing Association | [5 empty] | Q4-2021
635 | CAS CONSTRUCTION | Fingal | Garristown | 6 | North ＆ East Housing Association Ltd |  |  |  |  | Q3-2023
636 | CAS CONSTRUCTION | Fingal | Kenure Park, Rush | 4 | Prosper Fingal Housing Assocaition Ltd | Stage 1 approved Q3-2022, outline design and costs being prepared.
637 | CAS CONSTRUCTION | Fingal | Marian House, Convent Lane, Balbriggan | 19 | North ＆ East Housing Association Ltd | Stage 1 approved Q4-2022, outline design and costs being prepared.
638 | CAS CONSTRUCTION | Fingal | DVR @ 30 Clonard St., Balbriggan | 13 | Aoibhneas | Stage 1 approved Q4-2023, outline design and costs being prepared.
639 | SHIP CONSTRUCTION TURNKEY | Galway City | Garraí Caol, (Coast Road Site) Dublin Road | 26 | *N/A | [5 empty] | Q4-2022
640 | SHIP CONSTRUCTION TURNKEY | Galway City | Garraí Caol, (Coast Road Site) Dublin Road | 22 | *N/A | [5 empty] | Q4-2023
641 | SHIP CONSTRUCTION TURNKEY | Galway City | Coill Tire, Doughiska | 10 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
642 | SHIP CONSTRUCTION RENEWAL | Galway City | Merchants Road Lower, Galway City | 11 | *N/A |  | Stage 2 approved Q4-2021, full design/tender being prepared.
643 | SHIP CONSTRUCTION | Galway City | An Cliathán, Old Monivea Road, Ballybaan Mór | 15 | *N/A | [5 empty] | Q4-2023
644 | SHIP CONSTRUCTION | Galway City | Garraí Beag, Monivea Road, Ballybaan More | 10 | *N/A | [5 empty] | Q3-2024
645 | SHIP CONSTRUCTION | Galway City | 211 Tirellan Heights, Headford Road | 1 | *N/A | [5 empty] | Q2-2024
646 | SHIP CONSTRUCTION | Galway City | 1 Munster Avenue, Galway city | 4 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
647 | SHIP CONSTRUCTION | Galway City | Terryland Waterworks, Dyke Road, Galway City | 77 | N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
648 | SHIP CONSTRUCTION | Galway City | Garrai Beag, Monivea Road, Ballybaan More | 48 | N/A |  |  |  |  | Q1-2020
649 | SHIP Accel MMC | Galway City | Merlin Woods, Galway City | 18 | *N/A |  | Stage 2 approved Q2-2021, full design/tender being prepared.
650 | SHIP Accel MMC | Galway City | Clybaun Road, Knocknacarra | 30 | N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
651 | SHIP Accel MMC | Galway City | Ballyburke, Knocknacarra, Galway City | 84 | *N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
652 | CAS CONSTRUCTION TURNKEY | Galway City | Clai Mor, Old Monivea Road, Ballybrit | 33 | Túath Housing Association Ltd |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
653 | CAS CONSTRUCTION RENEWAL | Galway City | 36 Glenanail Drive Riverside Galway | 4 | *N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
654 | CAS CONSTRUCTION | Galway City | Cul Garrai, Rahoon | 6 | Peter Triest Housing Association Ltd |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
655 | CAS CONSTRUCTION | Galway City | Doughiska, Galway City | 7 | Respond | Stage 1 approved Q2-2019, outline design and costs being prepared.
656 | CAS CONSTRUCTION | Galway City | 111 Upper Newcastle Road, Galway City | 10 | Simon Community : Galway Simon |  |  |  |  | Q3-2023
657 | SHIP CONSTRUCTION TURNKEY | Galway County | Kylebroughlan, Moycullen | 9 | *N/A | [5 empty] | Q1-2021
658 | SHIP CONSTRUCTION TURNKEY | Galway County | Kylebroughlan, Moycullen | 10 | *N/A | [5 empty] | Q1-2021
659 | SHIP CONSTRUCTION TURNKEY | Galway County | Garraí Mhic Aodha, Tubber Road, Gort | 9 | *N/A | [5 empty] | Q4-2021
660 | SHIP CONSTRUCTION TURNKEY | Galway County | Tullahill, Loughrea | 9 | *N/A | [5 empty] | Q4-2021
661 | SHIP CONSTRUCTION TURNKEY | Galway County | Limehill, Dunlo, Ballinasloe (Corrán Eiscir Riada) | 2 | *N/A | [5 empty] | Q4-2022
662 | SHIP CONSTRUCTION TURNKEY | Galway County | Garraí Mhic Aodha, Tubber Road, Gort | 18 | *N/A | [5 empty] | Q4-2021
663 | SHIP CONSTRUCTION TURNKEY | Galway County | Cullairbaun, Athenry | 14 | *N/A | [5 empty] | Q3-2022
664 | SHIP CONSTRUCTION TURNKEY | Galway County | Limehill, Dunlo, Ballinasloe (Corrán Eiscir Riada) | 15 | *N/A | [5 empty] | Q4-2022
665 | SHIP CONSTRUCTION TURNKEY | Galway County | Garraí Glas, Ballydavid South, Athenry | 7 | N/A | [5 empty] | Q4-2022
666 | SHIP CONSTRUCTION TURNKEY | Galway County | Gort an Choirce, Tubber Road, Gort | 5 | *N/A | [5 empty] | Q2-2022
667 | SHIP CONSTRUCTION TURNKEY | Galway County | Cullairbaun, Athenry | 13 | *N/A | [5 empty] | Q4-2022
668 | SHIP CONSTRUCTION TURNKEY | Galway County | Circular Road & Dublin Road, Tuam | 8 | *N/A | [5 empty] | Q4-2023
669 | SHIP CONSTRUCTION TURNKEY | Galway County | Cullairbaun, Athenry | 15 | *N/A | [5 empty] | Q4-2022
670 | SHIP CONSTRUCTION TURNKEY | Galway County | Cullairbaun, Athenry | 16 | *N/A | [5 empty] | Q4-2023
671 | SHIP CONSTRUCTION TURNKEY | Galway County | Gort Fada, Kilgarve, Ballinasloe - Phase 1A | 20 | *N/A | [5 empty] | Q4-2023
672 | SHIP CONSTRUCTION TURNKEY | Galway County | Limehill, Dunlo, Ballinasloe (Corrán Eiscir Riada) | 15 | *N/A | [5 empty] | Q4-2023
673 | SHIP CONSTRUCTION TURNKEY | Galway County | Circular Road & Dublin Road Tuam | 2 | *N/A | [5 empty] | Q3-2024
674 | SHIP CONSTRUCTION TURNKEY | Galway County | Carraigweir, Tuam | 4 | *N/A | [5 empty] | Q4-2022
675 | SHIP CONSTRUCTION TURNKEY | Galway County | Lough na Carra, Williamstown | 7 | *N/A | [5 empty] | Q4-2022
676 | SHIP CONSTRUCTION TURNKEY | Galway County | Ballydavid South, Athenry | 2 | N/A | [5 empty] | Q2-2023
677 | SHIP CONSTRUCTION TURNKEY | Galway County | Vicors Coral, Tuam | 22 | N/A |  |  |  |  | Q4-2023
678 | SHIP CONSTRUCTION TURNKEY | Galway County | Lakeview, Glenamaddy | 22 | N/A | [5 empty] | Q4-2023
679 | SHIP CONSTRUCTION TURNKEY | Galway County | Caheroyan, Athenry | 2 | N/A | [5 empty] | Q3-2024
680 | SHIP CONSTRUCTION TURNKEY | Galway County | An Choill Fada, Kilgarve, Ballinalsoe - Phase 2 | 30 | *N/A |  |  |  |  | Q4-2023
681 | SHIP CONSTRUCTION TURNKEY | Galway County | Tir an Choir, Tuam | 6 | N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
682 | SHIP CONSTRUCTION TURNKEY | Galway County | Carraigweir, Weir Road, Tuam | 7 | N/A | [5 empty] | Q2-2024
683 | SHIP CONSTRUCTION TURNKEY | Galway County | Phase 1B, Kilgarve, Ballinasloe | 11 | N/A |  |  |  |  | Q3-2022
684 | SHIP CONSTRUCTION TURNKEY | Galway County | Kilcummin Fields, Oughterard | 20 | N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
685 | SHIP CONSTRUCTION TURNKEY | Galway County | Westport Road, Clifden | 27 | N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
686 | SHIP CONSTRUCTION TURNKEY | Galway County | Pairc na Coille, Athenry | 12 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
687 | SHIP CONSTRUCTION TURNKEY | Galway County | Gort Fada, Kilgarve Ballinasloe Phase C | 2 | N/A |  |  |  |  | Q3-2022
688 | SHIP CONSTRUCTION TURNKEY | Galway County | Gort Fada, Kilgarve Ballinasloe Phase D | 1 | N/A |  |  |  |  | Q3-2022
689 | SHIP CONSTRUCTION TURNKEY | Galway County | Bun na Coille | 1 | N/A |  |  |  |  | Q2-2024
690 | SHIP CONSTRUCTION SINGLE STAGE | Galway County | Corralough, Williamstown (SRD) | 1 | *N/A |  |  |  | Stage 4 approved Q2-2021, the scheme is fully approved.
691 | SHIP CONSTRUCTION SINGLE STAGE | Galway County | Parkmore Estate, Tuam | 4 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
692 | SHIP CONSTRUCTION SINGLE STAGE | Galway County | Hillcrest Estate, Loughrea, Co. Galway | 3 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
693 | SHIP CONSTRUCTION SINGLE STAGE | Galway County | Cullairbaun, Athenry | 11 | N/A |  |  |  |  | Q2-2024
694 | SHIP CONSTRUCTION SINGLE STAGE | Galway County | 27 Deerpark Woods | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
695 | SHIP CONSTRUCTION RENEWAL | Galway County | Dunlo Hill, Ballinasloe | 13 | *N/A |  | Stage 2 approved Q2-2023, full design/tender being prepared.
696 | SHIP CONSTRUCTION RENEWAL | Galway County | Main Street, Moylough | 4 | N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
697 | SHIP CONSTRUCTION DESIGN BUILD | Galway County | St. Joseph's Road, Portumna, Co. Galway | 24 | N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
698 | SHIP CONSTRUCTION | Galway County | Weir Road, Tuam | 14 | *N/A |  |  |  |  | Q1-2023
699 | SHIP CONSTRUCTION | Galway County | Gort na gCloch, Hospital Road, Clifden | 18 | *N/A | [5 empty] | Q4-2022
700 | SHIP CONSTRUCTION | Galway County | Bridge Court, Ahascragh, Ballinasloe | 18 | *N/A | [5 empty] | Q4-2023
701 | SHIP CONSTRUCTION | Galway County | Caisleán Raithlín, Ardrahan | 10 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
702 | SHIP CONSTRUCTION | Galway County | Barrack Street, Loughrea | 5 | *N/A | [5 empty] | Q3-2021
703 | SHIP CONSTRUCTION | Galway County | Garraí Ghuaire, Cartron, Kinvara | 10 | *N/A | [5 empty] | Q4-2022
704 | SHIP CONSTRUCTION | Galway County | Fana Bhuí, Tuam | 16 | *N/A | [5 empty] | Q4-2021
705 | SHIP CONSTRUCTION | Galway County | Cnoc na Carraige, Roundstone | 6 | *N/A | [5 empty] | Q1-2021
706 | SHIP CONSTRUCTION | Galway County | Ballyglass, Ardrahan (SRD) | 1 | *N/A | [5 empty] | Q4-2023
707 | SHIP CONSTRUCTION | Galway County | Woodpark, Portumna (SRD) | 1 | *N/A | [5 empty] | Q4-2023
708 | SHIP CONSTRUCTION | Galway County | Carrowmore West, Clontuskert, Ballinasloe (SRD) | 1 | *N/A | [5 empty] | Q4-2023
709 | SHIP CONSTRUCTION | Galway County | Woodfield, Dunmore (SRD) | 1 | *N/A | [5 empty] | Q4-2023
710 | SHIP CONSTRUCTION | Galway County | Knockaloura West, Brownsgrove, Tuam (SRD) | 1 | *N/A | [5 empty] | Q4-2023
711 | SHIP CONSTRUCTION | Galway County | Creggaturlough, Craughwell (SRD) | 1 | *N/A | [5 empty] | Q4-2023
712 | SHIP CONSTRUCTION | Galway County | Gort na gCloch, Hospital Road, Clifden | 8 | *N/A | [5 empty] | Q4-2022
713 | SHIP CONSTRUCTION | Galway County | Fana Bhuí, Tuam | 16 | *N/A | [5 empty] | Q4-2022
714 | SHIP CONSTRUCTION | Galway County | Fana Bhuí, Tuam | 16 | *N/A | [5 empty] | Q4-2022
715 | SHIP CONSTRUCTION | Galway County | Ballymoe | 8 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
716 | SHIP CONSTRUCTION | Galway County | Cosmona, Loughrea | 56 | *N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
717 | SHIP CONSTRUCTION | Galway County | Barkhill, Woodford | 2 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
718 | SHIP CONSTRUCTION | Galway County | St. Joseph's, Ballinasloe | 8 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
719 | SHIP CONSTRUCTION | Galway County | Fire Station Site, High Street, Tuam | 10 | N/A | Stage 1 approved Q2-2023, outline design and costs being prepared.
720 | SHIP CONSTRUCTION | Galway County | Weir Road, Tuam | 15 | N/A |  |  |  |  | Q1-2023
721 | SHIP CONSTRUCTION | Galway County | Farranamartin, Galway Road, Tuam. | 63 | N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
722 | SHIP CONSTRUCTION | Galway County | Gort Mhailor, Athenry Phase 2 | 30 | N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
723 | SHIP CONSTRUCTION | Galway County | Sun Street, Tuam | 40 | N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
724 | SHIP CONSTRUCTION | Galway County | St. Bridget's Portumna | 11 | N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
725 | SHIP Accel MMC | Galway County | Droim na Gaoithe, Baile Chláir (Claregalway) | 45 | *N/A | Stage 1 approved Q3-2021, outline design and costs being prepared.
726 | CAS CONSTRUCTION | Galway County | Letterfrack (Phase 2) | 11 | Cluid Housing Association | [5 empty] | Q1-2022
727 | CAS CONSTRUCTION | Galway County | Rossaveal Cottages, Ros a Mhíl, South Connemara | 8 | Tearmann Eanna Teoranta | Stage 1 approved Q4-2016, outline design and costs being prepared.
728 | CAS CONSTRUCTION | Galway County | Tithe Braiche, Mountbellew | 5 | Túath Housing Association Ltd |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
729 | CAS CONSTRUCTION | Galway County | Springfield, Parkmore, Ballinasloe | 4 | Peter Triest Housing Association Ltd |  | Stage 2 approved Q4-2021, full design/tender being prepared.
730 | CAS CONSTRUCTION | Galway County | Shannon Road, Portumna | 4 | Carraig Dubh Housing Association |  | Stage 2 approved Q1-2021, full design/tender being prepared.
731 | SHIP CONSTRUCTION TURNKEY | Kerry | Cnoc an Cairn, Chapel Lane, Dingle | 2 | *N/A | [5 empty] | Q1-2022
732 | SHIP CONSTRUCTION TURNKEY | Kerry | Main Street, Ballyheigue | 5 | N/A |  |  |  |  | Q3-2022
733 | SHIP CONSTRUCTION TURNKEY | Kerry | Spa Road, Dingle | 11 | N/A | [5 empty] | Q4-2023
734 | SHIP CONSTRUCTION TURNKEY | Kerry | 44A, 44B, 46A Cnoc an Cairn, Dingle | 3 | N/A | [5 empty] | Q3-2023
735 | SHIP CONSTRUCTION TURNKEY | Kerry | Cnoc an Cairn, The Grove, Dingle | 2 | *N/A | [5 empty] | Q4-2023
736 | SHIP CONSTRUCTION TURNKEY | Kerry | Springfield Drive, Ballyoughtragh North, Milltown | 15 | *N/A |  |  |  |  | Q2-2024
737 | SHIP CONSTRUCTION TURNKEY | Kerry | Springfield Drive, Ballyoughtragh North, Milltown | 36 | *N/A |  |  |  |  | Q2-2024
738 | SHIP CONSTRUCTION TURNKEY | Kerry | Springfield Drive, Ballyoughtragh North, Milltown | 10 | *N/A |  |  |  |  | Q2-2024
739 | SHIP CONSTRUCTION TURNKEY | Kerry | Ard an Oir, Sneem | 10 | *N/A |  |  |  |  | Q4-2023
740 | SHIP CONSTRUCTION TURNKEY | Kerry | 15 Lighthouse View, Cahersiveen, Kerry | 1 | N/A |  |  |  |  | Q1-2024
741 | SHIP CONSTRUCTION SINGLE STAGE | Kerry | SRD at Glannagilliagh, Caragh Lake, Killorglin | 1 | *N/A | [5 empty] | Q2-2022
742 | SHIP CONSTRUCTION SINGLE STAGE | Kerry | SRD at Carrigcannon, Lyreacrumpane | 1 | *N/A | [5 empty] | Q2-2024
743 | SHIP CONSTRUCTION SINGLE STAGE | Kerry | Rahinnane, Ventry | 1 | *N/A |  |  |  | Stage 4 approved Q2-2021, the scheme is fully approved.
744 | SHIP CONSTRUCTION RENEWAL | Kerry | 2 Kilrain Gardens, Tralee | 1 | *N/A |  |  |  |  | Q4-2023
745 | SHIP CONSTRUCTION DESIGN BUILD | Kerry | Rathmore/Barraduff | 20 | *N/A | [5 empty] | Q2-2021
746 | SHIP CONSTRUCTION | Kerry | Glenach, Ballybunion | 20 | *N/A | [5 empty] | Q1-2021
747 | SHIP CONSTRUCTION | Kerry | Lohercannon, Tralee | 61 | *N/A | [5 empty] | Q4-2022
748 | SHIP CONSTRUCTION | Kerry | Cullenagh Upper, Beaufort | 1 | *N/A | [5 empty] | Q1-2021
749 | SHIP CONSTRUCTION | Kerry | Farranwilliam, Ardfert | 22 | *N/A | [5 empty] | Q3-2021
750 | SHIP CONSTRUCTION | Kerry | Ballyrickard (Cluain na Geise), Tralee | 21 | *N/A | [5 empty] | Q3-2022
751 | SHIP CONSTRUCTION | Kerry | Croogorts, Tralee (Cruaghoirt) | 30 | *N/A | [5 empty] | Q3-2022
752 | SHIP CONSTRUCTION | Kerry | Rock Rd., Killarney | 10 | *N/A | [5 empty] | Q2-2022
753 | SHIP CONSTRUCTION | Kerry | Gortamullin, Kenmare (Phase 4) | 14 | *N/A | [5 empty] | Q1-2021
754 | SHIP CONSTRUCTION | Kerry | Baile an Gharraí, Lixnaw (Phase 2) | 10 | *N/A | [5 empty] | Q2-2021
755 | SHIP CONSTRUCTION | Kerry | Woodview Place, Tarbert | 22 | *N/A | [5 empty] | Q2-2023
756 | SHIP CONSTRUCTION | Kerry | Marconi South, Ballybunion (Glór na Toinne) | 14 | *N/A | [5 empty] | Q2-2023
757 | SHIP CONSTRUCTION | Kerry | Rahoonane, Tralee (New Site) | 8 | *N/A | [5 empty] | Q3-2022
758 | SHIP CONSTRUCTION | Kerry | Rusheen, Ballylongford (Carraig an Phoill) | 7 | *N/A | [5 empty] | Q2-2023
759 | SHIP CONSTRUCTION | Kerry | Gortamullin (Ard Bhearna), Kenmare - Phase 5 | 14 | *N/A | [5 empty] | Q2-2023
760 | SHIP CONSTRUCTION | Kerry | Aras na Cluana (former Locke's Shop), Mitchel's Rd, Tralee | 8 | *N/A |  |  |  |  | Q3-2024
761 | SHIP CONSTRUCTION | Kerry | Marian Terrace, Ballyheigue | 9 | *N/A | [5 empty] | Q2-2024
762 | SHIP CONSTRUCTION | Kerry | 6 Bridge Road, Abbeydorney | 1 | *N/A |  | Stage 2 approved Q2-2022, full design/tender being prepared.
763 | SHIP CONSTRUCTION | Kerry | Clogharesta Apartments Hawley Park,Tralee | 16 | *N/A |  |  |  |  | Q4-2023
764 | SHIP CONSTRUCTION | Kerry | SRD at Gortadrislig, Lixnaw, Co Kerry | 1 | *N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
765 | SHIP CONSTRUCTION | Kerry | 5 Bridge Road, Abbeydorney | 1 | *N/A |  | Stage 2 approved Q1-2023, full design/tender being prepared.
766 | SHIP Accel MMC | Kerry | Matt Talbot Road, Tralee | 27 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
767 | SHIP Accel MMC | Kerry | Garryruth, Tralee, Co Kerry | 19 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
768 | SHIP Accel MMC | Kerry | Lohercannon Phase 2, Tralee | 89 | *N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
769 | SHIP Accel MMC | Kerry | Ballybeg, Dingle, Co Kerry | 34 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
770 | CAS CONSTRUCTION TURNKEY | Kerry | Firies Hall, Firies | 14 | Peter McVerry Trust Ltd | [5 empty] | Q4-2022
771 | CAS CONSTRUCTION TURNKEY | Kerry | Firies Hall, Firies | 4 | Peter McVerry Trust Ltd | [5 empty] | Q4-2022
772 | CAS CONSTRUCTION RENEWAL | Kerry | Ardmoneel, Killorglin | 4 | St. John of God Housing Association Ltd |  |  |  | Stage 4 approved Q2-2022, the scheme is fully approved.
773 | CAS CONSTRUCTION RENEWAL | Kerry | Knockacullig North, Kilcummin, Killarney | 4 | Newgrove Housing Association Ltd | [5 empty] | Q4-2023
774 | CAS CONSTRUCTION | Kerry | Armagh House, Killarney | 6 | Cluid Housing Association | [5 empty] | Q1-2021
775 | CAS CONSTRUCTION | Kerry | Chamfers Place (Mitchels road, Tralee) | 18 | Cluid Housing Association | [5 empty] | Q3-2023
776 | CAS CONSTRUCTION | Kerry | Mary O'Donoghue Avenue, Cahirciveen | 7 | Caherciveen Social Services (Housing) Ltd |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
777 | CAS CONSTRUCTION | Kerry | The Towers Centre, Sandhill Road, Ballybunion | 13 | Society of Saint Vincent de Paul | Stage 1 approved Q1-2024, outline design and costs being prepared.
778 | CAS CONSTRUCTION | Kerry | DVR @ Killeen Road, Killarney | 13 | ADAPT | Stage 1 approved Q3-2024, outline design and costs being prepared.
779 | SHIP CONSTRUCTION TURNKEY | Kildare | The Willows, Allenwood | 1 | *N/A | [5 empty] | Q2-2021
780 | SHIP CONSTRUCTION TURNKEY | Kildare | Fitzgerald Close, Greenfield, Maynooth | 1 | *N/A | [5 empty] | Q2-2021
781 | SHIP CONSTRUCTION TURNKEY | Kildare | Coolaghknock Green, Kildare Town | 2 | *N/A | [5 empty] | Q1-2021
782 | SHIP CONSTRUCTION TURNKEY | Kildare | Abbotsfield, Clane | 1 | *N/A | [5 empty] | Q2-2021
783 | SHIP CONSTRUCTION TURNKEY | Kildare | Old Mill Race, Monasterevin | 14 | *N/A | [5 empty] | Q4-2022
784 | SHIP CONSTRUCTION TURNKEY | Kildare | Hemmingway Park, Clane | 13 | *N/A | [5 empty] | Q3-2021
785 | SHIP CONSTRUCTION TURNKEY | Kildare | Hemmingway Park, Clane | 10 | *N/A | [5 empty] | Q4-2022
786 | SHIP CONSTRUCTION TURNKEY | Kildare | Coolaghknock Green, Kildare Town | 2 | *N/A | [5 empty] | Q2-2021
787 | SHIP CONSTRUCTION TURNKEY | Kildare | Kildroch Court, Newtown, Ardclough Rd, Celbridge | 26 | *N/A | [5 empty] | Q3-2022
788 | SHIP CONSTRUCTION TURNKEY | Kildare | Kildare Road, Rathangan | 9 | *N/A | [5 empty] | Q2-2023
789 | SHIP CONSTRUCTION TURNKEY | Kildare | Abbotsfield, Clane | 2 | *N/A | [5 empty] | Q3-2021
790 | SHIP CONSTRUCTION TURNKEY | Kildare | The Willows, Allenwood | 1 | *N/A | [5 empty] | Q4-2021
791 | SHIP CONSTRUCTION TURNKEY | Kildare | Fitzgerald Close, Greenfield, Maynooth | 1 | *N/A | [5 empty] | Q4-2021
792 | SHIP CONSTRUCTION TURNKEY | Kildare | Williams Grove, Ardclough | 2 | *N/A | [5 empty] | Q4-2021
793 | SHIP CONSTRUCTION TURNKEY | Kildare | Millstream Court, Kilcullen | 1 | *N/A | [5 empty] | Q4-2021
794 | SHIP CONSTRUCTION TURNKEY | Kildare | Kildroch Court, Newtown, Ardclough Rd, Celbridge | 23 | *N/A | [5 empty] | Q4-2022
795 | SHIP CONSTRUCTION TURNKEY | Kildare | Harristown Drive, Kildangan | 1 | *N/A | [5 empty] | Q4-2022
796 | SHIP CONSTRUCTION TURNKEY | Kildare | Hillfort Drive, Kill | 6 | *N/A | [5 empty] | Q4-2022
797 | SHIP CONSTRUCTION TURNKEY | Kildare | An Lumann, Straffan | 2 | *N/A | [5 empty] | Q4-2022
798 | SHIP CONSTRUCTION TURNKEY | Kildare | The Shraud, Fairview, Kildare Town | 2 | *N/A | [5 empty] | Q1-2024
799 | SHIP CONSTRUCTION TURNKEY | Kildare | Station Walk, Rickardstown, Newbridge | 3 | *N/A | [5 empty] | Q1-2023
800 | SHIP CONSTRUCTION TURNKEY | Kildare | Linden Demesne, Maynooth | 10 | N/A | [5 empty] | Q2-2023
801 | SHIP CONSTRUCTION TURNKEY | Kildare | Harpur Lane, Leixlip | 20 | N/A | [5 empty] | Q3-2023
802 | SHIP CONSTRUCTION TURNKEY | Kildare | Melitta Road, Kildare | 4 | N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
803 | SHIP CONSTRUCTION TURNKEY | Kildare | Aughamore, Kilcock Road, Clane | 4 | N/A | [5 empty] | Q2-2024
804 | SHIP CONSTRUCTION TURNKEY | Kildare | Manor Mill View, Celbridge | 12 | N/A | [5 empty] | Q3-2024
805 | SHIP CONSTRUCTION TURNKEY | Kildare | The Friary, Castledermot, Kildare | 14 | N/A |  |  |  |  | Q1-2022
806 | SHIP CONSTRUCTION TURNKEY | Kildare | Manor Mill View, Celbridge | 31 | *N/A |  |  |  |  | Q3-2023
807 | SHIP CONSTRUCTION SINGLE STAGE | Kildare | Patrician Avenue, Naas | 3 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
808 | SHIP CONSTRUCTION SINGLE STAGE | Kildare | Inniscarra, Athy | 5 | *N/A |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
809 | SHIP CONSTRUCTION SINGLE STAGE | Kildare | Former Garda Station, Ballitore | 6 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
810 | SHIP CONSTRUCTION RENEWAL | Kildare | Carbury | 5 | *N/A | Stage 1 approved Q2-2020, outline design and costs being prepared.
811 | SHIP CONSTRUCTION RENEWAL | Kildare | Castle Park, Athy | 6 | *N/A |  |  | Stage 3 approved Q1-2024, the scheme is now approved to proceed to tender.
812 | SHIP CONSTRUCTION RENEWAL | Kildare | 25 St. Corbans Place, Naas | 1 | *N/A |  |  |  |  | Q3-2023
813 | SHIP CONSTRUCTION RENEWAL | Kildare | Shamrock Stores, Geraldine Rd, Athy | 4 | *N/A |  |  |  | Stage 4 approved Q3-2022, the scheme is fully approved.
814 | SHIP CONSTRUCTION RENEWAL | Kildare | 1 Maddenstown Terrace, The Curragh | 1 | N/A |  |  |  | Stage 4 approved Q4-2022, the scheme is fully approved.
815 | SHIP CONSTRUCTION | Kildare | Athgarvan Village | 18 | *N/A |  |  |  |  | Q1-2023
816 | SHIP CONSTRUCTION | Kildare | Newtown House, Leixlip | 4 | *N/A |  | Stage 2 approved Q2-2020, full design/tender being prepared.
817 | SHIP CONSTRUCTION | Kildare | Coill Dubh | 10 | *N/A | [5 empty] | Q1-2024
818 | SHIP CONSTRUCTION | Kildare | Ardclough Road, Celbridge | 29 | *N/A |  | Stage 2 approved Q1-2022, full design/tender being prepared.
819 | SHIP CONSTRUCTION | Kildare | Skenagun, Castledermot | 2 | *N/A |  | Stage 2 approved Q4-2019, full design/tender being prepared.
820 | SHIP CONSTRUCTION | Kildare | Ambassador Site, Kill | 33 | *N/A |  |  |  |  | Q1-2024
821 | SHIP CONSTRUCTION | Kildare | St. Evins Park Monasterevin | 15 | *N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
822 | SHIP CONSTRUCTION | Kildare | Old Caragh Road, Naas | 58 | *N/A | Stage 1 approved Q4-2021, outline design and costs being prepared.
823 | SHIP CONSTRUCTION | Kildare | Station Road, Kildare Town | 30 | N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
824 | SHIP CONSTRUCTION | Kildare | Craddockstown, Naas, Kildare | 28 | N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
825 | SHIP Accel MMC | Kildare | Old Greenfield Road, Maynooth | 65 | *N/A |  |  |  |  | Q1-2024
826 | CAS CONSTRUCTION RENEWAL | Kildare | El Kantara, Newbridge | 2 | KARE Promoting Inclusion for People with Intellectual Disabilities |  |  |  |  | Q1-2024
827 | CAS CONSTRUCTION RENEWAL | Kildare | Mc Cauley Court, Athy | 10 | Tintean Housing Association Ltd |  |  | Stage 3 approved Q1-2024, the scheme is now approved to proceed to tender.
828 | CAS CONSTRUCTION RENEWAL | Kildare | Moore Wood, Mountrice, Monasterevin, Kildare | 2 | KaARE Promoting Inclusion for People with Intellectual Disabilities |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
829 | CAS CONSTRUCTION | Kildare | Jigginstown House, Naas | 12 | Homeless Care Ltd | [5 empty] | Q2-2021
830 | CAS CONSTRUCTION | Kildare | St. John's Convent, New Street, Rathangan | 27 | Sophia Housing Association Ltd |  | Stage 2 approved Q1-2023, full design/tender being prepared.
831 | CAS CONSTRUCTION | Kildare | Dominican Lands, Athy | 34 | Cluid Housing Association |  | Stage 2 approved Q2-2022, full design/tender being prepared.
832 | CAS CONSTRUCTION | Kildare | Church Street, Kilcock, Kildare | 2 | DePaul Housing |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
833 | CAS CONSTRUCTION | Kildare | Beaufort, Sallins Road, Naas | 45 | Nás na Ríogh | Stage 1 approved Q2-2024, outline design and costs being prepared.
834 | CAS CONSTRUCTION | Kildare | Hillfort-Cheeverstown, Kill | 4 | Co-operative Housing Ireland (Formerly NABCo) | [5 empty] | Q3-2024
835 | SHIP CONSTRUCTION TURNKEY | Kilkenny | New Road, Mooncoin | 4 | *N/A | [5 empty] | Q4-2022
836 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Chapel Street, Mooncoin | 2 | *N/A | [5 empty] | Q4-2022
837 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Pennefeather Court, Hebron Road, Kilkenny | 8 | *N/A | [5 empty] | Q1-2022
838 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Pennefeather Green, Hebron Road, Kilkenny | 26 | *N/A | [5 empty] | Q1-2022
839 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Blackwater Grove, Kilmacow | 14 | *N/A | [5 empty] | Q2-2021
840 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Limegrove, Ferrybank | 5 | *N/A | [5 empty] | Q4-2021
841 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Piltown, Kilkenny | 4 | *N/A | [5 empty] | Q2-2023
842 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Limegrove, Ferrybank | 10 | *N/A | [5 empty] | Q1-2022
843 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Pennefeather Green, Hebron Road, Kilkenny | 26 | *N/A | [5 empty] | Q2-2022
844 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Marnellsmeadows, Callan Road, Kilkenny | 20 | *N/A |  |  |  |  | Q4-2023
845 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Berkely Drive, Mount Sion Road, Ferrybank | 5 | *N/A | [5 empty] | Q4-2022
846 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Old Creamery Site, Kilmacow | 8 | *N/A | [5 empty] | Q2-2023
847 | SHIP CONSTRUCTION TURNKEY | Kilkenny | 19 Village Gardens, Waterford Road, Kilkenny | 1 | *N/A | [5 empty] | Q2-2023
848 | SHIP CONSTRUCTION TURNKEY | Kilkenny | The Crescent, Belmont, Ferrybank, Co. Kilkenny | 11 | *N/A | [5 empty] | Q3-2023
849 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Castleoaks, Breagagh Valley, Kilkenny | 22 | *N/A |  |  |  |  | Q3-2023
850 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Church View, Kilmacow, Co. Kilkenny | 2 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
851 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Abbeymeadows, Abbeygate, Ferrybank, Co. Kilkenny | 15 | *N/A |  |  |  |  | Q4-2023
852 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Castleoaks (Phase 2), Breagagh Valley, Kilkenny | 2 | *N/A |  |  |  |  | Q2-2024
853 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Church View (Phase 2), Kilmacow, Co. Kilkenny | 8 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
854 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Lumper Lane, Urlingford, Co. Kilkenny | 15 | *N/A |  |  |  |  | Q2-2024
855 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Ogenty, Gowran | 13 | *N/A |  |  |  |  | Q1-2023
856 | SHIP CONSTRUCTION TURNKEY | Kilkenny | Barrack Street, Goresbridge, Co. Kilkenny | 11 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
857 | SHIP CONSTRUCTION SINGLE STAGE | Kilkenny | Inchacarron, Mullinavat | 2 | *N/A | [5 empty] | Q4-2022
858 | SHIP CONSTRUCTION SINGLE STAGE | Kilkenny | Shanganny, Jenkinstown | 2 | *N/A | [5 empty] | Q2-2022
859 | SHIP CONSTRUCTION SINGLE STAGE | Kilkenny | Ayrfield, Granges Road, Kilkenny | 6 | *N/A | [5 empty] | Q2-2021
860 | SHIP CONSTRUCTION SINGLE STAGE | Kilkenny | Old Fire Station, Graiguenamanagh | 2 | *N/A | [5 empty] | Q4-2022
861 | SHIP CONSTRUCTION SINGLE STAGE | Kilkenny | Ayrfield, Granges Road, Kilkenny | 2 | *N/A | [5 empty] | Q1-2022
862 | SHIP CONSTRUCTION SINGLE STAGE | Kilkenny | Haggardsgreen, Callan | 1 | *N/A | [5 empty] | Q2-2023
863 | SHIP CONSTRUCTION SINGLE STAGE | Kilkenny | Old Community Centre, Loughboy, Kilkenny | 2 | *N/A |  |  |  |  | Q4-2023
864 | SHIP CONSTRUCTION SINGLE STAGE | Kilkenny | Old Fire Station, Thomastown, Co. Kilkenny | 1 | *N/A |  |  |  |  | Q1-2024
865 | SHIP CONSTRUCTION SINGLE STAGE | Kilkenny | Main Street. Gowran, Co. Kilkenny | 1 | *N/A |  |  |  |  | Q2-2024
866 | SHIP CONSTRUCTION SINGLE STAGE | Kilkenny | 12 Wolfe Tone street, Kilkenny | 1 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
867 | SHIP CONSTRUCTION RENEWAL | Kilkenny | 18 Wolfe Tone Street, Kilkenny | 1 | *N/A | [5 empty] | Q3-2023
868 | SHIP CONSTRUCTION RENEWAL | Kilkenny | Upper Patrick Street, Kilkenny | 5 | *N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
869 | SHIP CONSTRUCTION RENEWAL | Kilkenny | Cloghsgregg, Thomastown | 1 | *N/A | [5 empty] | Q2-2024
870 | SHIP CONSTRUCTION RENEWAL | Kilkenny | 4 Loughboy Park, Kilkenny | 1 | N/A | [5 empty] | Q2-2023
871 | SHIP CONSTRUCTION RENEWAL | Kilkenny | Oldtown, Ballyragget | 1 | *N/A | [5 empty] | Q4-2023
872 | SHIP CONSTRUCTION RENEWAL | Kilkenny | Old Health Centre, Kilmacow | 1 | *N/A | [5 empty] | Q1-2024
873 | SHIP CONSTRUCTION RENEWAL | Kilkenny | Maudlin Street, Thomastown, Co. Kilkenny | 1 | *N/A |  |  |  |  | Q3-2024
874 | SHIP CONSTRUCTION DESIGN BUILD | Kilkenny | Abbey Hill, Thomastown, Co. Kilkenny | 42 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
875 | SHIP CONSTRUCTION DESIGN BUILD | Kilkenny | An Tobar, Freshford, Co. Kilkenny | 20 | *N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
876 | SHIP CONSTRUCTION | Kilkenny | 10 Golf Links Road, Kilkenny | 6 | *N/A | [5 empty] | Q3-2023
877 | SHIP CONSTRUCTION | Kilkenny | Station Road, Ballyragget | 22 | *N/A | [5 empty] | Q2-2021
878 | SHIP CONSTRUCTION | Kilkenny | Donaguile, Castlecomer | 33 | *N/A | [5 empty] | Q2-2021
879 | SHIP CONSTRUCTION | Kilkenny | The Broguemaker, Kilkenny | 18 | *N/A | [5 empty] | Q2-2021
880 | SHIP CONSTRUCTION | Kilkenny | Ladywell, Thomastown | 25 | *N/A | [5 empty] | Q3-2023
881 | SHIP CONSTRUCTION | Kilkenny | Crokers Hill, Kennyswell Road, Kilkenny | 88 | *N/A |  |  |  |  | Q4-2022
882 | SHIP CONSTRUCTION | Kilkenny | Canal Road, Johnstown - Project 1 | 5 | *N/A | Stage 1 approved Q1-2020, outline design and costs being prepared.
883 | SHIP CONSTRUCTION | Kilkenny | Canal Road Johnstow - Project 2 | 2 | *N/A | Stage 1 approved Q1-2020, outline design and costs being prepared.
884 | SHIP CONSTRUCTION | Kilkenny | Canal Road Johnstown - Project 3 | 4 | *N/A | Stage 1 approved Q1-2020, outline design and costs being prepared.
885 | SHIP CONSTRUCTION | Kilkenny | Teach Aimsire, Granges Road, Kilkenny | 6 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
886 | SHIP CONSTRUCTION | Kilkenny | 18/20 Bridge Street, Callan, Co. Kilkenny | 4 | *N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
887 | SHIP CONSTRUCTION | Kilkenny | Kilcreene, Drakelands, Kilkenny City | 40 | N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
888 | SHIP CONSTRUCTION | Kilkenny | Jacob Street, Kilkenny | 4 | *N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
889 | CAS CONSTRUCTION TURNKEY | Kilkenny | Tinnypark, Callan Road, Kilkenny | 6 | SOS Kilkenny Housing Association Ltd | [5 empty] | Q3-2022
890 | CAS CONSTRUCTION TURNKEY | Kilkenny | 70-71 Upper Patrick Street, Kilkenny | 4 | Clanmill Housing Association Ireland |  |  |  |  | Q3-2023
891 | CAS CONSTRUCTION SINGLE STAGE | Kilkenny | Miltown Lodge Phase 2, Johnswell Road, Kilkenny | 1 | SOS Kilkenny Housing Association Ltd | [5 empty] | Q2-2022
892 | CAS CONSTRUCTION SINGLE STAGE | Kilkenny | Group Home Coolnamuck, Inistioge, Co. kilkenny | 4 | Kilkenny Voluntary Housing Association |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
893 | CAS CONSTRUCTION RENEWAL | Kilkenny | Group Home Foulksrath, Callan, Co. Kilkenny | 4 | Kilkenny Voluntary Housing Association | Stage 1 approved Q2-2024, outline design and costs being prepared.
894 | CAS CONSTRUCTION RENEWAL | Kilkenny | Group Home Mountgale, Rathmoyle, Co. Kilkenny | 4 | Kilkenny Voluntary Housing Association | Stage 1 approved Q2-2024, outline design and costs being prepared.
895 | CAS CONSTRUCTION | Kilkenny | Kingsriver, Ennisnag | 2 | Kingsriver Housing Association Limited | [5 empty] | Q2-2022
896 | CAS CONSTRUCTION | Kilkenny | Red Barn, Patrick Street, Ballyragget | 11 | Good Shepherd Services Ltd |  |  |  |  | Q1-2024
897 | CAS CONSTRUCTION | Kilkenny | 8/9 Kilkenny Street, Castlecomer | 3 | Good Shepherd Services Ltd |  |  |  |  | Q3-2023
898 | CAS CONSTRUCTION | Kilkenny | 19/21 Blackmill Street, Kilkenny | 12 | Good Shepherd Services Ltd | [5 empty] | Q2-2023
899 | CAS CONSTRUCTION | Kilkenny | Brother Thomas Place, Church Lane, Kilkenny | 12 | Good Shepherd Services Ltd | [5 empty] | Q3-2022
900 | CAS CONSTRUCTION | Kilkenny | Grennan Villa, Thomastown | 5 | Camphill Communities of Ireland | [5 empty] | Q3-2022
901 | CAS CONSTRUCTION | Kilkenny | St. John of God Convent, College Road, Kilkenny | 20 | Sophia Housing Association Ltd |  | Stage 2 approved Q2-2023, full design/tender being prepared.
902 | CAS CONSTRUCTION | Kilkenny | Mill Street, Callan | 12 | Kilkenny Voluntary Housing Association |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
903 | CAS CONSTRUCTION | Kilkenny | The Roundhouse, Kells, Co. Kilkenny | 6 | SOS Kilkenny Housing Association Ltd | Stage 1 approved Q2-2024, outline design and costs being prepared.
904 | SHIP CONSTRUCTION TURNKEY | Laois | Priory, Borris in Ossory | 5 | *N/A | [5 empty] | Q3-2022
905 | SHIP CONSTRUCTION TURNKEY | Laois | Oakvale Meadows, Church Avenue, Stradbally | 20 | *N/A | [5 empty] | Q4-2023
906 | SHIP CONSTRUCTION TURNKEY | Laois | Bruach Na Habhainn, Killeen, Maganey | 3 | *N/A | [5 empty] | Q1-2022
907 | SHIP CONSTRUCTION TURNKEY | Laois | The Orchard, Ballylynan | 2 | N/A | [5 empty] | Q1-2022
908 | SHIP CONSTRUCTION TURNKEY | Laois | Market Square, Portarlington | 15 | N/A | [5 empty] | Q2-2023
909 | SHIP CONSTRUCTION TURNKEY | Laois | The Orchard, Ballylynan | 2 | *N/A | [5 empty] | Q4-2022
910 | SHIP CONSTRUCTION TURNKEY | Laois | Oakvale Meadows, Church Avenue, Stradbally | 6 | *N/A | [5 empty] | Q2-2024
911 | SHIP CONSTRUCTION TURNKEY | Laois | Bruach Na Habhainn, Killeen, Maganey | 1 | *N/A |  |  |  |  | Q4-2021
912 | SHIP CONSTRUCTION TURNKEY | Laois | The Orchard, Ballylynan | 1 | *N/A |  |  |  |  | Q3-2022
913 | SHIP CONSTRUCTION TURNKEY | Laois | Townparks, Rathdowney Road, Borris in Ossory | 8 | N/A | [5 empty] | Q3-2024
914 | SHIP CONSTRUCTION TURNKEY | Laois | Market Square, Portarlington | 3 | N/A | [5 empty] | Q3-2023
915 | SHIP CONSTRUCTION TURNKEY | Laois | Shannon Street, Mountrath | 16 | N/A |  |  |  |  | Q3-2023
916 | SHIP CONSTRUCTION TURNKEY | Laois | Oakvale Meadows, Church Avenue, Stradbally | 5 | N/A |  |  |  |  | Q4-2021
917 | SHIP CONSTRUCTION TURNKEY | Laois | Townspark, Mountmellick | 41 | N/A |  |  |  |  | Q4-2023
918 | SHIP CONSTRUCTION TURNKEY | Laois | Townparks, Rathdowney Road, Borris in Ossory, | 13 | N/A |  |  |  |  | Q1-2023
919 | SHIP CONSTRUCTION SINGLE STAGE | Laois | Coolroe, Ballybrittas | 1 | *N/A | [5 empty] | Q2-2022
920 | SHIP CONSTRUCTION RENEWAL | Laois | Oldcourt Ballylynan | 1 | N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
921 | SHIP CONSTRUCTION RENEWAL | Laois | 1 New Road Portlaoise | 1 | *N/A |  |  |  |  | Q2-2024
922 | SHIP CONSTRUCTION RENEWAL | Laois | 6 Emmet Terrace, Mountmellick | 1 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
923 | SHIP CONSTRUCTION RENEWAL | Laois | 13 & 14 Lakeglen, Portlaoise | 2 | N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
924 | SHIP CONSTRUCTION RENEWAL | Laois | Maryborough School, Stradbally Road, Portlaoise | 11 | N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
925 | SHIP CONSTRUCTION RENEWAL | Laois | Barrowvilla, Portarlington | 2 | *N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
926 | SHIP CONSTRUCTION | Laois | Moore Street, Rathdowney | 6 | *N/A |  |  |  |  | Q3-2020
927 | SHIP CONSTRUCTION | Laois | Ballymorris Road, Portarlington | 22 | *N/A | [5 empty] | Q2-2021
928 | SHIP CONSTRUCTION | Laois | Gleann na Glaise, Ballyroan | 10 | *N/A | [5 empty] | Q3-2022
929 | SHIP CONSTRUCTION | Laois | Pattison Est. Mountmellick | 10 | *N/A | [5 empty] | Q4-2022
930 | SHIP CONSTRUCTION | Laois | Shannon Street, Mountrath | 6 | *N/A | [5 empty] | Q2-2021
931 | SHIP CONSTRUCTION | Laois | Harbour Court, Mountmellick | 6 | *N/A | [5 empty] | Q4-2023
932 | SHIP CONSTRUCTION | Laois | Mooreville, Rathdowney | 7 | *N/A |  |  |  |  | Q1-2023
933 | SHIP CONSTRUCTION | Laois | Sean Doire, Cork Road, Durrow | 22 | *N/A | [5 empty] | Q4-2022
934 | SHIP CONSTRUCTION | Laois | St Kieran's Park, Errill | 14 | *N/A | [5 empty] | Q4-2023
935 | SHIP CONSTRUCTION | Laois | Clonrooske, Knockmay | 12 | *N/A |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
936 | SHIP CONSTRUCTION | Laois | Carraig Glas, Stradbally | 26 | *N/A |  |  |  |  | Q4-2023
937 | SHIP CONSTRUCTION | Laois | Tyrells Land, Stradbally Road, Portlaoise | 21 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
938 | SHIP CONSTRUCTION | Laois | Iona, Abbeyleix Rd., Portlaoise | 7 | *N/A |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
939 | SHIP CONSTRUCTION | Laois | Ballyadams | 1 | *N/A |  |  |  |  | Q3-2024
940 | SHIP CONSTRUCTION | Laois | Doonane | 12 | N/A |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
941 | SHIP CONSTRUCTION | Laois | Barnhill Wood, Derry Road, Durrow | 24 | *N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
942 | SHIP CONSTRUCTION | Laois | Bracklone Street, Portarlington | 11 | *N/A | Stage 1 approved Q3-2022, outline design and costs being prepared.
943 | SHIP CONSTRUCTION | Laois | Moanbaun, Mountrath | 17 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
944 | SHIP CONSTRUCTION | Laois | Stanhope Street, Ballinakill | 3 | *N/A | Stage 1 approved Q1-2023, outline design and costs being prepared.
945 | SHIP CONSTRUCTION | Laois | Rush Hall, Mountrath | 4 | *N/A | Stage 1 approved Q1-2023, outline design and costs being prepared.
946 | SHIP CONSTRUCTION | Laois | Beladd, Stradbally Road, Portlaoise | 5 | N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
947 | SHIP CONSTRUCTION | Laois | The Maltings, Irishtown, Mountmellick | 40 | N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
948 | CAS CONSTRUCTION | Laois | Presentation Convent & Lands, Portlaoise | 52 | Sophia Housing Association Ltd |  |  |  |  | Q1-2024
949 | SHIP CONSTRUCTION TURNKEY | Leitrim | Church Lane, Ballinamore | 9 | *N/A | [5 empty] | Q4-2021
950 | SHIP CONSTRUCTION TURNKEY | Leitrim | Druminshingore, Newtowngore | 2 | *N/A | [5 empty] | Q4-2021
951 | SHIP CONSTRUCTION TURNKEY | Leitrim | Carraig Breac, Drumshanbo | 5 | *N/A | [5 empty] | Q4-2022
952 | SHIP CONSTRUCTION TURNKEY | Leitrim | Ard na Drise, Mohill | 2 | *N/A | [5 empty] | Q1-2021
953 | SHIP CONSTRUCTION TURNKEY | Leitrim | Lough Meen Estate, Drumkeerin | 2 | *N/A | [5 empty] | Q4-2021
954 | SHIP CONSTRUCTION TURNKEY | Leitrim | Commons Lane, Manorhamilton | 4 | *N/A | [5 empty] | Q4-2022
955 | SHIP CONSTRUCTION TURNKEY | Leitrim | Cluain Oir, Liscara, Carrick on Shannon | 2 | *N/A | [5 empty] | Q2-2021
956 | SHIP CONSTRUCTION TURNKEY | Leitrim | Manorhamilton & Carrigallen | 2 | *N/A | [5 empty] | Q3-2021
957 | SHIP CONSTRUCTION TURNKEY | Leitrim | Druminshingore Td., Newtowngore | 3 | *N/A | [5 empty] | Q2-2022
958 | SHIP CONSTRUCTION TURNKEY | Leitrim | Lisnagot, Carrick on Shannon | 3 | *N/A | [5 empty] | Q4-2022
959 | SHIP CONSTRUCTION TURNKEY | Leitrim | Carraig Breac, Drumshanbo | 8 | *N/A | [5 empty] | Q4-2022
960 | SHIP CONSTRUCTION TURNKEY | Leitrim | Carraig Breac, Drumshanbo | 4 | *N/A | [5 empty] | Q4-2023
961 | SHIP CONSTRUCTION TURNKEY | Leitrim | Oakfield Manor, Kinlough | 6 | *N/A | [5 empty] | Q3-2024
962 | SHIP CONSTRUCTION TURNKEY | Leitrim | Sheena, Drumkeerin | 9 | *N/A |  |  |  |  | Q3-2023
963 | SHIP CONSTRUCTION TURNKEY | Leitrim | Cannaboe Td, Ballinamore | 3 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
964 | SHIP CONSTRUCTION SINGLE STAGE | Leitrim | Breffni Cres., 53 St. Patricks Park Site, Carrick on Shannon | 2 | *N/A | [5 empty] | Q4-2022
965 | SHIP CONSTRUCTION SINGLE STAGE | Leitrim | Dromahair Td., Dromahair | 4 | *N/A | [5 empty] | Q4-2023
966 | SHIP CONSTRUCTION SINGLE STAGE | Leitrim | Sean McDermott St., Manorhamilton | 4 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
967 | SHIP CONSTRUCTION SINGLE STAGE | Leitrim | Main Street, Drumsna | 4 | *N/A |  |  |  |  | Q1-2024
968 | SHIP CONSTRUCTION SINGLE STAGE | Leitrim | Newtowngore Village | 7 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
969 | SHIP CONSTRUCTION SINGLE STAGE | Leitrim | Kiltyclogher Village | 2 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
970 | SHIP CONSTRUCTION SINGLE STAGE | Leitrim | Ballinamore | 4 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
971 | SHIP CONSTRUCTION SINGLE STAGE | Leitrim | Keshcarrigan | 4 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
972 | SHIP CONSTRUCTION | Leitrim | Autumn View, Summerhill, Carrick on Shannon | 27 | *N/A | [5 empty] | Q4-2021
973 | SHIP CONSTRUCTION | Leitrim | Taobh Tire, Manorhamilton (Phase 3) | 5 | *N/A | [5 empty] | Q3-2023
974 | SHIP CONSTRUCTION | Leitrim | Pairceanna an Bhaile, Townparks, Carrick on Shannon | 7 | *N/A | [5 empty] | Q4-2022
975 | SHIP CONSTRUCTION | Leitrim | Lahard, Ballinamore | 10 | *N/A | [5 empty] | Q3-2023
976 | SHIP CONSTRUCTION | Leitrim | Kilboderry Td., Carrick on Shannon | 18 | *N/A |  |  |  |  | Q3-2024
977 | SHIP CONSTRUCTION | Leitrim | Pairceanna an Bhaile, Townparks, Carrick on Shannon | 5 | *N/A | [5 empty] | Q2-2023
978 | SHIP CONSTRUCTION TURNKEY | Limerick | Redgate Close, Old Cratloe Road, Limerick City | 13 | *N/A | [5 empty] | Q3-2022
979 | SHIP CONSTRUCTION TURNKEY | Limerick | Gortboy, Charleville Road, KiImallock | 24 | *N/A | [5 empty] | Q1-2022
980 | SHIP CONSTRUCTION TURNKEY | Limerick | Knocklong | 4 | *N/A | [5 empty] | Q4-2022
981 | SHIP CONSTRUCTION TURNKEY | Limerick | Gortboy, Charleville Road, KiImallock | 9 | *N/A | [5 empty] | Q4-2022
982 | SHIP CONSTRUCTION TURNKEY | Limerick | Broad Street, Limerick | 13 | *N/A | [5 empty] | Q4-2022
983 | SHIP CONSTRUCTION TURNKEY | Limerick | Laurelville, Mill Rd, Corbally | 2 | *N/A | [5 empty] | Q4-2022
984 | SHIP CONSTRUCTION TURNKEY | Limerick | Woodfield Manor, Cloonyscrehane, Newcastlewest | 17 | *N/A | [5 empty] | Q4-2022
985 | SHIP CONSTRUCTION TURNKEY | Limerick | Maypole Crescent, Knocklong, Co Limerick | 1 | N/A | [5 empty] | Q4-2023
986 | SHIP CONSTRUCTION TURNKEY | Limerick | Knocklong | 1 | N/A | [5 empty] | Q4-2023
987 | SHIP CONSTRUCTION TURNKEY | Limerick | Bru na Gruadain | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
988 | SHIP CONSTRUCTION TURNKEY | Limerick | Ballylanders | 5 | N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
989 | SHIP CONSTRUCTION TURNKEY | Limerick | Newtown Meadows, Castletroy, Limerick | 3 | N/A | [5 empty] | Q4-2023
990 | SHIP CONSTRUCTION TURNKEY | Limerick | Turnkey at 52 Johnsgate, Limerick | 1 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
991 | SHIP CONSTRUCTION TURNKEY | Limerick | Turnkey at 35 and 36 Bru na Gruadan, Limerick | 2 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
992 | SHIP CONSTRUCTION SINGLE STAGE | Limerick | Crawford Street, Bruff, Co Limerick | 2 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
993 | SHIP CONSTRUCTION RENEWAL | Limerick | 82, 84, 86 Hyde Road, Prospect, Limerick | 1 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
994 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 9B: Clancy Strand, Limerick | 1 | N/A |  |  | Stage 3 approved Q3-2023, the scheme is now approved to proceed to tender.
995 | SHIP CONSTRUCTION RENEWAL | Limerick | Patrickswell, Limerick | 1 | N/A | Stage 1 approved Q1-2023, outline design and costs being prepared.
996 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 2: Marian Place Janesboro | 1 | N/A | [5 empty] | Q4-2022
997 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 2: Shanabooley Road, Ballynanty Beg, Limerick | 1 | N/A | [5 empty] | Q2-2023
998 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 2: Shanabooley Road, Ballynanty Beg, Limerick | 1 | N/A | [5 empty] | Q2-2023
999 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 2: Bishops Street, St Marys Parish | 1 | N/A | [5 empty] | Q4-2022
1000 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 2: Lenihan Avenue, Prospect, Limerick | 1 | N/A | [5 empty] | Q3-2023
1001 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 2: O' Dwyers Villas Thomondgate, Limerick | 1 | N/A | [5 empty] | Q3-2023
1002 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 2: Downey Street, Killalee, Limerick | 1 | N/A | [5 empty] | Q4-2022
1003 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: Cedar Court , Kennedy Park, Limerick | 1 | *N/A | [5 empty] | Q2-2024
1004 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: Br Cill Mhuire, Garryowen, Limerick | 1 | *N/A | [5 empty] | Q2-2024
1005 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: Quinns Cottages Rosbrien Limerick | 1 | *N/A | [5 empty] | Q4-2023
1006 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: Monabraher Road, Ballynanty Beg, Limerick | 1 | *N/A | [5 empty] | Q4-2023
1007 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: Clarke Avenue, Janesboro, Limerick | 1 | *N/A | [5 empty] | Q4-2023
1008 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: Walnut Court Kennedy Park. Limerick | 1 | *N/A | [5 empty] | Q4-2023
1009 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: Island Road, Limerick | 1 | *N/A | [5 empty] | Q4-2023
1010 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: Oakley Lawn, Caherconlish, County Limerick | 1 | *N/A | [5 empty] | Q4-2023
1011 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: St Mary's Terrace Ballinacurra Road Ballinacurra, Limerick | 1 | *N/A |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
1012 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: Greenhill Rd., Garryowen, Limerick | 1 | *N/A | [5 empty] | Q2-2024
1013 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: Clonconane Road, Ballynanty Beg, Limerick | 1 | *N/A | [5 empty] | Q2-2024
1014 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: Raheen Sq. Ballinacurra Weston, Limerick | 1 | *N/A | [5 empty] | Q4-2023
1015 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: Aster Court, Keyes Park, Limerick | 1 | *N/A |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
1016 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 3: Roseville, Janesboro, Limerick | 1 | *N/A |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
1017 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 5: Churchview Askeaton County Limerick | 1 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1018 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 5: St Marys Park Rathkeale County Limerick | 1 | *N/A | [5 empty] | Q4-2023
1019 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 5: Fairgreen Tce Bruff County Limerick | 1 | *N/A | [5 empty] | Q4-2023
1020 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 5: St Munchins Tce Bruree | 1 | *N/A | [5 empty] | Q4-2023
1021 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 5: Sharwood, Newcastle West, Co Limerick | 1 | *N/A | [5 empty] | Q4-2023
1022 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 5: Kylefea, Croom, Co Limerick | 1 | *N/A | [5 empty] | Q4-2023
1023 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 5: Fairview Cottages, Mulgrave Street, Limerick | 1 | *N/A | [5 empty] | Q4-2023
1024 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 5: Chestnut Court, Kennedy Park, Limerick | 1 | *N/A | [5 empty] | Q4-2023
1025 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 8: Hyde Avenue, Limerick Derelict Sites, Limerick. | 1 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1026 | SHIP CONSTRUCTION RENEWAL | Limerick | 7 Collinstown, Bruff, Co Limerick | 1 | *N/A |  |  | Stage 3 approved Q1-2024, the scheme is now approved to proceed to tender.
1027 | SHIP CONSTRUCTION RENEWAL | Limerick | 13 Cathedral Place, Limerick | 1 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1028 | SHIP CONSTRUCTION RENEWAL | Limerick | Kilfinane | 1 | N/A | [5 empty] | Q2-2024
1029 | SHIP CONSTRUCTION RENEWAL | Limerick | St Mary's Terrace, Askeaton, Co Limerick | 4 | N/A | [5 empty] | Q4-2023
1030 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 14: Marine Cove, Limerick | 1 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1031 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 2: Rosbrien Terrace, Rosbrien, Limerick | 1 | N/A | [5 empty] | Q3-2023
1032 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 2: Cherry Avenue, Caherdavin | 1 | N/A | [5 empty] | Q1-2023
1033 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 2: Good Shepherd Villas, Pennywell, Limerick | 1 | N/A | [5 empty] | Q2-2023
1034 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 3: New Road Court, Thomondgate, Limerick | 1 | N/A | [5 empty] | Q2-2024
1035 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 5: Johnsgate, Limerick | 1 | N/A | [5 empty] | Q4-2023
1036 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 5: Johnsgate | 1 | N/A | [5 empty] | Q4-2023
1037 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 5: Carrig East, Clarina, Limerick | 1 | N/A | [5 empty] | Q3-2024
1038 | SHIP CONSTRUCTION RENEWAL | Limerick | Hyde Road, Prospect, Limerick | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1039 | SHIP CONSTRUCTION RENEWAL | Limerick | Galbally, Co Limerick | 4 | N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
1040 | SHIP CONSTRUCTION RENEWAL | Limerick | Shanagolden, Co Limerick | 3 | N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
1041 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 13B, Lower Maiden Street, Limerick | 1 | N/A |  |  | Stage 3 approved Q3-2023, the scheme is now approved to proceed to tender.
1042 | SHIP CONSTRUCTION RENEWAL | Limerick | Main Street, Oola | 1 | N/A |  |  | Stage 3 approved Q1-2024, the scheme is now approved to proceed to tender.
1043 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 8A: Hyde Road, LImerick | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1044 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 7: Georgian Village, Limerick | 1 | N/A | [5 empty] | Q3-2024
1045 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 7: The Gables, Limerick | 1 | N/A | [5 empty] | Q3-2024
1046 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 6A: O' Callaghan Avenure, Kileely | 1 | N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
1047 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 6: Mullally Lawn, Cappamore, Co Limerick | 1 | N/A | [5 empty] | Q3-2023
1048 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 6: Mullally Lawn, Cappamore, Co Limerick | 1 | N/A | [5 empty] | Q3-2023
1049 | SHIP CONSTRUCTION RENEWAL | Limerick | Lot 6: 5 Hillview Drive, Kiteely | 1 | N/A | [5 empty] | Q4-2023
1050 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 16 - 78 Glasgow Park, Limerick | 1 | *N/A |  |  | Stage 3 approved Q1-2024, the scheme is now approved to proceed to tender.
1051 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 6 - 42 Mullally Lawn, Cappamore, Co Limerick | 1 | N/A | [5 empty] | Q4-2023
1052 | SHIP CONSTRUCTION RENEWAL | Limerick | 16 Main Street, Croom | 1 | N/A |  |  | Stage 3 approved Q1-2024, the scheme is now approved to proceed to tender.
1053 | SHIP CONSTRUCTION RENEWAL | Limerick | LOT 9 - Ballycormack, Shanagolden | 1 | *N/A | [5 empty] | Q4-2023
1054 | SHIP CONSTRUCTION RENEWAL | Limerick | 1 Wolfe Tone Street, Deebert Place, Kilmallock | 1 | N/A |  |  | Stage 3 approved Q1-2024, the scheme is now approved to proceed to tender.
1055 | SHIP CONSTRUCTION RENEWAL | Limerick | 10 and 11 Clare Street, Limerick | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1056 | SHIP CONSTRUCTION RENEWAL | Limerick | 51-52 Sharwood, Newcastle West (Knock through) | 1 | N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
1057 | SHIP CONSTRUCTION RENEWAL | Limerick | 1 Larch Court, Kennedy Park, Limerick | 1 | N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
1058 | SHIP CONSTRUCTION DESIGN BUILD | Limerick | Old Christians Site, Rathbane | 43 | *N/A | [5 empty] | Q2-2021
1059 | SHIP CONSTRUCTION DESIGN BUILD | Limerick | Barnakyle, Patrickswell (Site 2) | 24 | *N/A |  |  |  |  | Q3-2023
1060 | SHIP CONSTRUCTION | Limerick | Ballysimon, Greenhill Road | 14 | *N/A | [5 empty] | Q1-2022
1061 | SHIP CONSTRUCTION | Limerick | Gough Place, Rosbrien Road, Limerick | 17 | *N/A | [5 empty] | Q4-2022
1062 | SHIP CONSTRUCTION | Limerick | Clonmacken, Limerick City | 43 | *N/A |  |  |  |  | Q3-2019
1063 | SHIP CONSTRUCTION | Limerick | Deerpark, Adare | 13 | *N/A |  |  | Stage 3 approved Q4-2023, the scheme is now approved to proceed to tender.
1064 | SHIP CONSTRUCTION | Limerick | Glenview Drive, Hospital | 20 | *N/A | [5 empty] | Q4-2023
1065 | SHIP CONSTRUCTION | Limerick | Clare Street, Limerick City | 7 | *N/A |  |  |  |  | Q1-2022
1066 | SHIP CONSTRUCTION | Limerick | Lower Carey's Road, Limerick City | 11 | *N/A | [5 empty] | Q1-2021
1067 | SHIP CONSTRUCTION | Limerick | Kileely Road, Moyross | 5 | *N/A | [5 empty] | Q2-2021
1068 | SHIP CONSTRUCTION | Limerick | Station Close, Knocklong | 12 | *N/A | [5 empty] | Q4-2022
1069 | SHIP CONSTRUCTION | Limerick | St. Michael's Court, Watergate Flats, | 9 | *N/A | Stage 1 approved Q1-2018, outline design and costs being prepared.
1070 | SHIP CONSTRUCTION | Limerick | Ballysimon, Greenhills Road | 3 | *N/A | [5 empty] | Q1-2022
1071 | SHIP CONSTRUCTION | Limerick | Clueing Dara, Broadford | 11 | *N/A |  |  | Stage 3 approved Q1-2024, the scheme is now approved to proceed to tender.
1072 | SHIP CONSTRUCTION | Limerick | Sycamore Crescent, Newcastle West, Co Limerick | 31 | *N/A |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
1073 | SHIP CONSTRUCTION | Limerick | Radharc an Ghleanna, Mountcollins | 4 | *N/A |  |  |  |  | Q3-2023
1074 | SHIP CONSTRUCTION | Limerick | O’Connor Park, Ardagh, Co. Limerick | 10 | *N/A |  |  |  |  | Q1-2023
1075 | SHIP CONSTRUCTION | Limerick | Church Glen, Ballylanders, Co. Limerick | 9 | *N/A |  |  | Stage 3 approved Q1-2024, the scheme is now approved to proceed to tender.
1076 | SHIP CONSTRUCTION | Limerick | Radharc Cillin, Kilfinane, Co. Limerick | 10 | *N/A |  |  |  |  | Q2-2023
1077 | SHIP CONSTRUCTION | Limerick | Brugh na Deise, Bruff, Co Limerick | 18 | *N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
1078 | SHIP CONSTRUCTION | Limerick | New Road, Thomondgate, Limerick | 6 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
1079 | SHIP CONSTRUCTION | Limerick | Deerpark, Adare | 18 | *N/A |  | Stage 2 approved Q4-2020, full design/tender being prepared.
1080 | SHIP CONSTRUCTION | Limerick | Meadowbrook, Mill Rd, Limerick | 7 | *N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
1081 | SHIP CONSTRUCTION | Limerick | Cliona Park Phase 4 | 20 | *N/A | Stage 1 approved Q2-2022, outline design and costs being prepared.
1082 | SHIP CONSTRUCTION | Limerick | Mulcaire Drive, Annacotty, Co Limerick. | 6 | N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
1083 | SHIP CONSTRUCTION | Limerick | Clueing Dara, Broadford | 7 | N/A |  | Stage 2 approved Q1-2021, full design/tender being prepared.
1084 | SHIP CONSTRUCTION | Limerick | Bridge Street, Kings Island, Limerick | 6 | N/A | Stage 1 approved Q3-2023, outline design and costs being prepared.
1085 | SHIP CONSTRUCTION | Limerick | Regen - Pineview Garden Infills, Moyross | 24 | N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
1086 | SHIP CONSTRUCTION | Limerick | Ros Mor, Crossagalla, Kilmallock Road, Limerick | 8 | N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
1087 | SHIP CONSTRUCTION | Limerick | Regen - Pineview Garden Infills, Moyross | 19 | N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
1088 | SHIP CONSTRUCTION | Limerick | Regen - Pineview Garden Infills, Moyross | 13 | N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
1089 | SHIP CONSTRUCTION | Limerick | Scout Hall, Bawnmore Road, Kennedy Park, Limerick | 6 | N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
1090 | SHIP CONSTRUCTION | Limerick | Upper William Street, Limerick | 7 | N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
1091 | SHIP CONSTRUCTION | Limerick | Meat Market Lane, Limerick | 8 | N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
1092 | SHIP Accel MMC | Limerick | Ballycummin Road, Raheen, Co. Limerick | 26 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
1093 | REGENERATION | Limerick | Sheep / Athlunkards Street | 8 | N/A |  |  |  |  | Q4-2022
1094 | REGENERATION | Limerick | Churchfield Phase 2 | 11 | N/A | [5 empty] | Q4-2023
1095 | REGENERATION | Limerick | Dalgaish Park and Cosgrave Park | 6 | *N/A | [5 empty] | Q4-2023
1096 | REGENERATION | Limerick | Orchard Site | 27 | Oaklee Housing Trust |  |  | Stage 3 approved Q2-2021, the scheme is now approved to proceed to tender.
1097 | REGENERATION | Limerick | Cliona Park Phase 3 | 18 | N/A | [5 empty] | Q4-2023
1098 | REGENERATION | Limerick | 45A-46A Cliona Park | 2 | *N/A | [5 empty] | Q3-2021
1099 | REGENERATION | Limerick | Dalgaish Park and Cosgrave Park | 7 | *N/A | [5 empty] | Q4-2023
1100 | REGENERATION | Limerick | Infills Carew Park, Southhill and Moyross | 24 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1101 | REGENERATION | Limerick | Lot 4A: 1 Collins Avenue, Kincora Park, Limerick | 1 | *N/A | [5 empty] | Q3-2024
1102 | REGENERATION | Limerick | Lot 4A: 14 Lenihan Avenue Prospect, Limerick Derelict Sites, Limerick, | 1 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1103 | REGENERATION | Limerick | Lot 4A: 25 Lenihan Avenue Prospect, Limerick | 1 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1104 | REGENERATION | Limerick | Lot 4A: 28 Crecora Avenue Ballinacurra Weston, Limerick | 1 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1105 | REGENERATION | Limerick | Lot 4A: 57 Ash Avenue John Carew Park, Limerick Derelict Sites, Limerick, | 1 | *N/A | [5 empty] | Q3-2024
1106 | REGENERATION | Limerick | Lot 4A: 108 Cosgrave Park, Moyross, Limerick Derelict Sites, Limerick, | 1 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1107 | REGENERATION | Limerick | Lot 4A: 11 St Colmcille Street St Marys Park. Limerick | 1 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1108 | REGENERATION | Limerick | Lot 4A: 9 St Colmcille Street St Marys Park, Limerick | 1 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1109 | REGENERATION | Limerick | Lot 4A: 11 Aster Court, Limerick | 1 | *N/A |  |  |  |  | Q1-2024
1110 | REGENERATION | Limerick | Churchfield Phase 2 | 13 | N/A |  |  |  |  | Q1-2022
1111 | REGENERATION | Limerick | Churchfield Phase 2 Block 5 | 13 | N/A | [5 empty] | Q4-2023
1112 | REGENERATION | Limerick | Dalgaish Park and Cosgrave Park | 15 | N/A | [5 empty] | Q2-2024
1113 | REGENERATION | Limerick | Dalgaish Park and Cosgrave Park | 20 | N/A |  |  |  |  | Q1-2022
1114 | REGENERATION | Limerick | Dalgaish Park and Cosgrave Park | 4 | N/A | [5 empty] | Q4-2023
1115 | REGENERATION | Limerick | Dalgaish Park and Cosgrave Park | 5 | N/A | [5 empty] | Q4-2023
1116 | REGENERATION | Limerick | LOT 4B - St Munchin Street, St Mary's Park, Limerick | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1117 | REGENERATION | Limerick | LOT 4B - St Ita's Street, St Mary's Park, Limerick | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1118 | REGENERATION | Limerick | LOT 4B - St Ita's Street, St Mary's Park, Limerick | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1119 | REGENERATION | Limerick | LOT 4B - Bridget's Avenue, St Mary's Park, Limerick | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1120 | REGENERATION | Limerick | LOT 4B - St Senan's Street, St Mary's Park, Limerick | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1121 | REGENERATION | Limerick | LOT 4B - Markievicz Kincora Park, Limerick | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1122 | REGENERATION | Limerick | LOT 4B Markievicz Kincora Park, Limerick | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1123 | REGENERATION | Limerick | Lot 4B: 6 Aster Court, Limerick | 1 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1124 | CAS CONSTRUCTION TURNKEY | Limerick | Knocklong, Co Limerick | 4 | St Joseph's Foundation Charleville ＆ District Mentally Handicapped Childrens Association |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1125 | CAS CONSTRUCTION TURNKEY | Limerick | 67-68 Newtown Meadows, Castletroy (Group Homes X 2) | 7 | Thomond Housing Association Ltd | [5 empty] | Q4-2023
1126 | CAS CONSTRUCTION TURNKEY | Limerick | Kilmurry Court, Garryowen, Limerick | 1 | Focus Ireland | [5 empty] | Q4-2023
1127 | CAS CONSTRUCTION TURNKEY | Limerick | Kilmurry Court, Garryowen, Limerick | 1 | Focus Ireland | [5 empty] | Q4-2023
1128 | CAS CONSTRUCTION TURNKEY | Limerick | 6 and 7 Newenham Street, Limerick | 8 | Arlington Novas Ireland Ltd | [5 empty] | Q4-2023
1129 | CAS CONSTRUCTION TURNKEY | Limerick | Cecil Street, Limerick | 5 | Arlington Novas Ireland Ltd | [5 empty] | Q4-2023
1130 | CAS CONSTRUCTION TURNKEY | Limerick | 7 Lower Mallow Street, Limerick | 5 | Arlington Novas Ireland Ltd | [5 empty] | Q4-2023
1131 | CAS CONSTRUCTION TURNKEY | Limerick | 1-4 Corner House, Main Street, Bruff | 4 | Arlington Novas Ireland Ltd | [5 empty] | Q3-2024
1132 | CAS CONSTRUCTION TURNKEY | Limerick | 1-6 Shannon View, New Road, Thomondgate, Limerick | 6 | Focus Ireland |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1133 | CAS CONSTRUCTION TURNKEY | Limerick | 9 Maypole Crescent, Knocklong, Limerick | 4 | St Joseph's Foundation Charleville ＆ District Mentally Handicapped Childrens Association |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1134 | CAS CONSTRUCTION TURNKEY | Limerick | Turnkey at 55 The Park, Ros Mor, Crossagalla, Limerick | 1 | Arlington Novas Ireland Ltd | [5 empty] | Q3-2024
1135 | CAS CONSTRUCTION TURNKEY | Limerick | 21-23 Old Clare Street, Limerick | 4 | Focus Ireland |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1136 | CAS CONSTRUCTION TURNKEY | Limerick | 30 Roches Street, Limerick | 3 | Simon Community : Midwest Simon |  |  |  |  | TBC
1137 | CAS CONSTRUCTION RENEWAL | Limerick | North Road, Dromcollogher | 1 | Focus Ireland |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
1138 | CAS CONSTRUCTION RENEWAL | Limerick | Bengal Terrace, Old Cork Road | 1 | Arlington Novas Ireland Ltd | [5 empty] | Q4-2023
1139 | CAS CONSTRUCTION RENEWAL | Limerick | Hyde Road, Prospect | 1 | Arlington Novas Ireland Ltd | [5 empty] | Q4-2023
1140 | CAS CONSTRUCTION RENEWAL | Limerick | Doon, Co Limerick | 4 | Thomond Housing Association Ltd |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1141 | CAS CONSTRUCTION RENEWAL | Limerick | Roma, Shelbourne Road, Limerick | 3 | HAIL | [5 empty] | Q4-2023
1142 | CAS CONSTRUCTION | Limerick | Towerfield Crescent, Croom | 16 | Croom Voluntary Housing Association Ltd |  |  |  |  | Q2-2023
1143 | CAS CONSTRUCTION | Limerick | Cappamore (Creamery Site) | 10 | Cappamore Housing Association Ltd |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1144 | CAS CONSTRUCTION | Limerick | Mirth, Thomondgate | 18 | Associated Charities Trust Ltd |  |  |  |  | Q3-2022
1145 | CAS CONSTRUCTION | Limerick | 2-3 Mallow Street | 12 | Peter McVerry Trust Ltd |  |  |  |  | Q1-2023
1146 | CAS CONSTRUCTION | Limerick | St. Pauls Convent, Kilfinane | 9 | Sophia Housing Association Ltd |  |  |  |  | Q4-2023
1147 | CAS CONSTRUCTION | Limerick | McGarry House, 7 Alphonsus Street | 8 | Arlington Novas Ireland Ltd |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
1148 | CAS CONSTRUCTION | Limerick | Main Street, Croom, Limerick | 5 | Croom Voluntary Housing Association Ltd |  |  |  |  | Q1-2023
1149 | CAS CONSTRUCTION | Limerick | Henry Street, Limerick | 5 | Simon Community : Midwest Simon |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
1150 | CAS CONSTRUCTION | Limerick | Infills Carew Park, Southhill and Moyross | 14 | Peter McVerry Trust Ltd | [5 empty] | Q4-2022
1151 | CAS CONSTRUCTION | Limerick | Nunan's Corner, Tullaha, Broadford, Co Limerick | 7 | Broadford Voluntary Housing and Community Childcare CLG |  | Stage 2 approved Q4-2023, full design/tender being prepared.
1152 | CAS CONSTRUCTION | Limerick | Cuan Mhuire, Bruree, Co Limerick | 10 | Cuan Mhuire Teoranta | [5 empty] | Q3-2023
1153 | CAS CONSTRUCTION | Limerick | Sisters Of Mercy Convent, Doon, Co Limerick | 23 | Ballyhoura Rural Services CLG |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
1154 | CAS CONSTRUCTION | Limerick | Athea, Galeside | 4 | Athea Voluntary Housing CLG |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
1155 | CAS CONSTRUCTION | Limerick | Cloverfield, Glin, Co Limerick | 10 | Glin Homes for the Elderly Ltd |  | Stage 2 approved Q4-2023, full design/tender being prepared.
1156 | CAS CONSTRUCTION | Limerick | Gortmore, Feenagh, Co Limerick | 8 | Corran – Deel Voluntary Housing Association Ltd |  | Stage 2 approved Q3-2024, full design/tender being prepared.
1157 | CAS CONSTRUCTION | Limerick | Toher Close, Doon | 3 | N/A |  | Stage 2 approved Q2-2023, full design/tender being prepared.
1158 | CAS CONSTRUCTION | Limerick | Cuan Mhuire, Bruree, Co Limerick | 16 | Cuan Mhuire Teoranta |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1159 | CAS CONSTRUCTION | Limerick | Cuan Mhuire, Bruree | 10 | Cuan Mhuire Teoranta | [5 empty] | Q2-2024
1160 | SHIP CONSTRUCTION TURNKEY | Longford | Slí Corglass, Legga | 4 | *N/A | [5 empty] | Q1-2021
1161 | SHIP CONSTRUCTION TURNKEY | Longford | Richmond St., Longford Town | 3 | *N/A | [5 empty] | Q1-2024
1162 | SHIP CONSTRUCTION TURNKEY | Longford | Farnagh Hill, Longford Town | 8 | *N/A | [5 empty] | Q1-2021
1163 | SHIP CONSTRUCTION TURNKEY | Longford | Campbell’s Lane | 6 | *N/A | [5 empty] | Q3-2021
1164 | SHIP CONSTRUCTION TURNKEY | Longford | O'Hara Site, (St Michael's Court) Connaught Rd.,Longford | 14 | *N/A | [5 empty] | Q4-2022
1165 | SHIP CONSTRUCTION TURNKEY | Longford | Alder Field, Farnagh Hill | 4 | *N/A | [5 empty] | Q4-2021
1166 | SHIP CONSTRUCTION TURNKEY | Longford | Slí Corglass, Legga | 4 | *N/A | [5 empty] | Q2-2021
1167 | SHIP CONSTRUCTION TURNKEY | Longford | Campbell’s Lane | 4 | *N/A | [5 empty] | Q2-2021
1168 | SHIP CONSTRUCTION TURNKEY | Longford | Slí Corglass, Legga | 1 | *N/A | [5 empty] | Q3-2021
1169 | SHIP CONSTRUCTION TURNKEY | Longford | Campbell’s Lane | 5 | *N/A | [5 empty] | Q2-2021
1170 | SHIP CONSTRUCTION TURNKEY | Longford | St. Patricks Ct., Ballinamuck | 8 | *N/A | [5 empty] | Q4-2022
1171 | SHIP CONSTRUCTION TURNKEY | Longford | Alder Field, Farnagh Hill | 12 | N/A | [5 empty] | Q3-2021
1172 | SHIP CONSTRUCTION TURNKEY | Longford | Campbell’s Lane | 6 | N/A | [5 empty] | Q4-2021
1173 | SHIP CONSTRUCTION TURNKEY | Longford | Alder Field, Farnagh Hill | 4 | N/A | [5 empty] | Q4-2021
1174 | SHIP CONSTRUCTION TURNKEY | Longford | Alder Field, Farnagh Hill | 3 | N/A | [5 empty] | Q4-2021
1175 | SHIP CONSTRUCTION TURNKEY | Longford | Alder Field, Farnagh Hill | 1 | N/A | [5 empty] | Q4-2022
1176 | SHIP CONSTRUCTION TURNKEY | Longford | Campbell’s Lane, Longford Town | 2 | N/A | [5 empty] | Q4-2022
1177 | SHIP CONSTRUCTION TURNKEY | Longford | Caislean Breac, Newtownforbes | 2 | *N/A | [5 empty] | Q3-2022
1178 | SHIP CONSTRUCTION TURNKEY | Longford | Forthill, Aughnacliffe | 4 | N/A | [5 empty] | Q4-2023
1179 | SHIP CONSTRUCTION TURNKEY | Longford | Woodlawn Path, Keenagh | 2 | N/A | [5 empty] | Q1-2023
1180 | SHIP CONSTRUCTION TURNKEY | Longford | Longford Rd., Ballinalee | 7 | N/A |  |  |  | Stage 4 approved Q4-2022, the scheme is fully approved.
1181 | SHIP CONSTRUCTION TURNKEY | Longford | Cluain Rí, Ballymahon | 4 | N/A | [5 empty] | Q4-2023
1182 | SHIP CONSTRUCTION TURNKEY | Longford | Abhainn Glas, Edgeworthstown | 2 | N/A | [5 empty] | Q4-2023
1183 | SHIP CONSTRUCTION TURNKEY | Longford | 6A Park Road, Longford Town | 1 | N/A | [5 empty] | Q2-2023
1184 | SHIP CONSTRUCTION TURNKEY | Longford | Woodlawn Path, Keenagh | 3 | N/A | [5 empty] | Q2-2023
1185 | SHIP CONSTRUCTION TURNKEY | Longford | Creevaghbui, Creevaghbeg, Ballymahon | 4 | N/A | [5 empty] | Q4-2023
1186 | SHIP CONSTRUCTION TURNKEY | Longford | Market Square, Longford Town | 1 | N/A | [5 empty] | Q3-2024
1187 | SHIP CONSTRUCTION TURNKEY | Longford | Silver Birches, Stonepark | 4 | N/A | [5 empty] | Q4-2023
1188 | SHIP CONSTRUCTION TURNKEY | Longford | Silver Birches, Stonepark | 4 | N/A | [5 empty] | Q4-2023
1189 | SHIP CONSTRUCTION TURNKEY | Longford | Cluai Rí, Ballymahon | 4 | N/A | [5 empty] | Q3-2023
1190 | SHIP CONSTRUCTION TURNKEY | Longford | Richmond Street, Longford Town | 7 | N/A | [5 empty] | Q3-2023
1191 | SHIP CONSTRUCTION TURNKEY | Longford | Richmond Street, Longford Town | 7 | N/A | [5 empty] | Q4-2023
1192 | SHIP CONSTRUCTION TURNKEY | Longford | Cluain Rí, Ballymahon | 4 | N/A | [5 empty] | Q3-2023
1193 | SHIP CONSTRUCTION TURNKEY | Longford | Richmond Street, Longford Town | 4 | N/A | [5 empty] | Q4-2023
1194 | SHIP CONSTRUCTION TURNKEY | Longford | Forthill, Aughnacliffe | 2 | N/A | [5 empty] | Q4-2023
1195 | SHIP CONSTRUCTION TURNKEY | Longford | Forthill, Aughnacliffe | 4 | N/A | [5 empty] | Q1-2024
1196 | SHIP CONSTRUCTION TURNKEY | Longford | Market Square, Longford Town | 1 | N/A |  |  |  |  | Q3-2023
1197 | SHIP CONSTRUCTION TURNKEY | Longford | Cluain Rí, Ballymahon | 4 | N/A | [5 empty] | Q1-2024
1198 | SHIP CONSTRUCTION TURNKEY | Longford | Abhainn Glas, Edgeworthstown | 2 | N/A | [5 empty] | Q4-2023
1199 | SHIP CONSTRUCTION TURNKEY | Longford | Silver Birches, Stonepark | 4 | N/A | [5 empty] | Q4-2023
1200 | SHIP CONSTRUCTION TURNKEY | Longford | Longford Rd., Ballinalee | 7 | N/A |  |  |  | Stage 4 approved Q4-2022, the scheme is fully approved.
1201 | SHIP CONSTRUCTION TURNKEY | Longford | Richmond Street, Longford Town | 1 | N/A | [5 empty] | Q3-2024
1202 | SHIP CONSTRUCTION TURNKEY | Longford | Forthill, Aughnacliffe | 3 | N/A | [5 empty] | Q2-2024
1203 | SHIP CONSTRUCTION TURNKEY | Longford | Forthill, Aughnacliffe | 4 | N/A |  |  |  |  | Q1-2023
1204 | SHIP CONSTRUCTION TURNKEY | Longford | Richmond Street, Longford Town | 1 | N/A |  |  |  |  | Q2-2022
1205 | SHIP CONSTRUCTION SINGLE STAGE | Longford | 2 Legion Terrace, Longford | 4 | N/A |  |  |  |  | Q2-2023
1206 | SHIP CONSTRUCTION SINGLE STAGE | Longford | Woodview, Newtownforbes | 2 | N/A | [5 empty] | Q4-2023
1207 | SHIP CONSTRUCTION | Longford | 'Rose Cottage', Ballinalee | 6 | *N/A | [5 empty] | Q4-2021
1208 | SHIP CONSTRUCTION | Longford | St.Rita's, Park Road, Longford | 6 | *N/A |  | Stage 2 approved Q1-2020, full design/tender being prepared.
1209 | SHIP CONSTRUCTION | Longford | Fairgreen View, Longford Town | 1 | *N/A | [5 empty] | Q2-2021
1210 | SHIP CONSTRUCTION | Longford | Cranleymore, Abbeylara | 3 | *N/A |  |  | Stage 3 approved Q1-2020, the scheme is now approved to proceed to tender.
1211 | SHIP CONSTRUCTION | Longford | Cloonahard, Edgeworthstown | 1 | *N/A | [5 empty] | Q2-2021
1212 | SHIP CONSTRUCTION | Longford | Woodlands Path, Keenagh | 4 | *N/A | [5 empty] | Q4-2023
1213 | SHIP CONSTRUCTION | Longford | Clough Dillons, Keenagh | 4 | N/A | Stage 1 approved Q3-2021, outline design and costs being prepared.
1214 | SHIP CONSTRUCTION | Longford | Radharc Na Muileann, Lanesborough | 13 | N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
1215 | SHIP CONSTRUCTION | Longford | Drynan, Ballymahon | 12 | N/A | Stage 1 approved Q4-2021, outline design and costs being prepared.
1216 | SHIP CONSTRUCTION | Longford | 24B Congress Terrace, Longford | 2 | N/A | [5 empty] | Q4-2023
1217 | SHIP CONSTRUCTION | Longford | Cnoc Na Gréine, Granard | 7 | N/A | Stage 1 approved Q4-2021, outline design and costs being prepared.
1218 | SHIP CONSTRUCTION | Longford | Radharc Na Muileann, Lanesborough | 9 | N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
1219 | SHIP CONSTRUCTION | Longford | Lamagh, Newtownforbes | 6 | N/A |  | Stage 2 approved Q4-2022, full design/tender being prepared.
1220 | SHIP CONSTRUCTION | Longford | Corneddan, Ballinalee | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1221 | SHIP CONSTRUCTION | Longford | Casey Court, Keenagh | 2 | N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
1222 | SHIP CONSTRUCTION | Longford | Aughaboy, Killoe | 4 | N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
1223 | CAS CONSTRUCTION RENEWAL | Longford | Comcille Terrace, Granard | 6 | Túath Housing Association Ltd | [5 empty] | Q2-2024
1224 | CAS CONSTRUCTION RENEWAL | Longford | Colmcille Terrace, Granard | 4 | Túath Housing Association Ltd | [5 empty] | Q4-2023
1225 | CAS CONSTRUCTION RENEWAL | Longford | Colmcille Terrace, Granard | 1 | Túath Housing Association Ltd | [5 empty] | Q1-2024
1226 | CAS CONSTRUCTION | Longford | Colmcille Terrace, Granard | 8 | Túath Housing Association Ltd |  |  |  |  | Q2-2023
1227 | SHIP CONSTRUCTION TURNKEY | Louth | ‘Gort Bui’, Ballymakenny Road, Drogheda | 10 | *N/A | [5 empty] | Q1-2021
1228 | SHIP CONSTRUCTION TURNKEY | Louth | ‘Gort Bui’, Ballymakenny Road, Drogheda | 9 | *N/A | [5 empty] | Q2-2021
1229 | SHIP CONSTRUCTION TURNKEY | Louth | ‘Gort Bui’, Ballymakenny Road, Drogheda | 8 | *N/A | [5 empty] | Q2-2021
1230 | SHIP CONSTRUCTION TURNKEY | Louth | Glyde View, Tallanstown | 2 | *N/A | [5 empty] | Q2-2021
1231 | SHIP CONSTRUCTION TURNKEY | Louth | Termon River, Termonfeckin | 1 | *N/A | [5 empty] | Q4-2021
1232 | SHIP CONSTRUCTION TURNKEY | Louth | Ellwood, Ballymakenny Road, Drogheda | 8 | *N/A | [5 empty] | Q4-2022
1233 | SHIP CONSTRUCTION TURNKEY | Louth | Ellwood, Ballymakenny Road, Drogheda | 4 | *N/A | [5 empty] | Q4-2023
1234 | SHIP CONSTRUCTION TURNKEY | Louth | Ellwood, Ballymakenny Road, Drogheda | 6 | *N/A | [5 empty] | Q4-2023
1235 | SHIP CONSTRUCTION TURNKEY | Louth | Ellwood, Ballymakenny Road, Drogheda | 6 | *N/A | [5 empty] | Q4-2023
1236 | SHIP CONSTRUCTION TURNKEY | Louth | Tullybrook Place, Slane Road, Drogheda | 3 | *N/A | [5 empty] | Q4-2022
1237 | SHIP CONSTRUCTION TURNKEY | Louth | Cuirt Na Gcloch, Stoneylane, Ardee | 14 | *N/A | [5 empty] | Q4-2022
1238 | SHIP CONSTRUCTION TURNKEY | Louth | Park Green, Coulter Place, Armagh Road, Dundalk | 24 | N/A | [5 empty] | Q4-2022
1239 | SHIP CONSTRUCTION TURNKEY | Louth | San Giovanni, Drogheda Road, Clogherhead, Co. Louth | 4 | N/A |  |  |  |  | Q3-2023
1240 | SHIP CONSTRUCTION TURNKEY | Louth | Clos Emer, Saltown, Dundalk | 5 | N/A | [5 empty] | Q4-2023
1241 | SHIP CONSTRUCTION TURNKEY | Louth | Medebawn Close, Avenue Road, Dundalk | 4 | N/A | [5 empty] | Q4-2023
1242 | SHIP CONSTRUCTION TURNKEY | Louth | Knockshee, Old Golf Links Road, Blackrock | 12 | N/A |  |  |  |  | Q3-2023
1243 | SHIP CONSTRUCTION TURNKEY | Louth | Ferrard Park, The Twenties, Drogheda | 6 | N/A | [5 empty] | Q3-2024
1244 | SHIP CONSTRUCTION TURNKEY | Louth | Quarry Court, John Street / Stoney Lane, Ardee, Co. Louth | 18 | N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
1245 | SHIP CONSTRUCTION TURNKEY | Louth | Ellwood Ballymackenny Road, Drogheda | 6 | N/A | [5 empty] | Q4-2023
1246 | SHIP CONSTRUCTION TURNKEY | Louth | Ellwood Ballymackenny Road, Drogheda | 6 | N/A | [5 empty] | Q4-2023
1247 | SHIP CONSTRUCTION TURNKEY | Louth | San Giovanni, Drogheda Road, Clogherhead, Co. Louth | 4 | N/A |  |  |  |  | Q3-2023
1248 | SHIP CONSTRUCTION TURNKEY | Louth | San Giovanni, Drogheda Road, Clogherhead, Co. Louth | 4 | N/A |  |  |  |  | Q3-2023
1249 | SHIP CONSTRUCTION TURNKEY | Louth | Ferrard Park, The Twenties, Drogheda | 12 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
1250 | SHIP CONSTRUCTION SINGLE STAGE | Louth | Gort Uaine, Clogherhead | 1 | *N/A | [5 empty] | Q2-2024
1251 | SHIP CONSTRUCTION SINGLE STAGE | Louth | School Lane, Dunleer | 1 | *N/A | [5 empty] | Q2-2024
1252 | SHIP CONSTRUCTION SINGLE STAGE | Louth | Doire Beag, Collon | 6 | *N/A | [5 empty] | Q3-2023
1253 | SHIP CONSTRUCTION RENEWAL | Louth | CPO Bundle 6 - 2 Willow Brook, Dromiskin | 1 | *N/A | [5 empty] | Q1-2024
1254 | SHIP CONSTRUCTION RENEWAL | Louth | CPO Bundle 6 - 1 Willow Brook, Dromiskin | 1 | *N/A | [5 empty] | Q1-2024
1255 | SHIP CONSTRUCTION RENEWAL | Louth | CPO Bundle 5 - Dundalk | 1 | *N/A | [5 empty] | Q1-2021
1256 | SHIP CONSTRUCTION RENEWAL | Louth | CPO Bundle 5 - St Clement's Park, Dundalk | 1 | *N/A | [5 empty] | Q4-2023
1257 | SHIP CONSTRUCTION RENEWAL | Louth | CPO Bundle 6 | 1 | *N/A | [5 empty] | Q1-2021
1258 | SHIP CONSTRUCTION RENEWAL | Louth | CPO Bundle 7 | 3 | N/A | [5 empty] | Q1-2023
1259 | SHIP CONSTRUCTION | Louth | Boice Court (Phase 2), Drogheda | 72 | *N/A |  |  |  |  | Q2-2023
1260 | SHIP CONSTRUCTION | Louth | Father Finn Park (Phase 2) | 17 | *N/A | [5 empty] | Q2-2021
1261 | SHIP CONSTRUCTION | Louth | Mount Avenue, Dundalk | 93 | *N/A |  |  |  |  | Q3-2023
1262 | SHIP CONSTRUCTION | Louth | Muirhevnamor, Dundalk (Phase 1) | 11 | *N/A |  |  |  |  | Q3-2023
1263 | SHIP CONSTRUCTION | Louth | Rathmullen Park, Drogheda | 6 | *N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
1264 | SHIP CONSTRUCTION | Louth | 65/64 Anne Street, Dundalk, Co Louth | 16 | N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
1265 | SHIP Accel MMC | Louth | Lands at Lower Point Road, Dundalk, Co. Louth | 49 | N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
1266 | SHIP Accel MMC | Louth | Lands at Dunleer, Co. Louth | 72 | N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
1267 | SHIP Accel MMC | Louth | Lands at Ballymakenny West, Ballymakenny Road Drogheda | 117 | N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
1268 | SHIP Accel MMC | Louth | Lands at Mullavalley, Louth Village, Co Louth | 43 | N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
1269 | SHIP Accel MMC | Louth | Lands at Greenhill's Drogheda Co Louth | 20 | N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
1270 | REGENERATION | Louth | Cox's Demesne Phase 2b | 22 | *N/A | [5 empty] | Q3-2022
1271 | CAS CONSTRUCTION TURNKEY | Louth | Liscorrie, Bog Road, Drogheda | 12 | Túath Housing Association Ltd | [5 empty] | Q2-2021
1272 | CAS CONSTRUCTION RENEWAL | Louth | 5 Coopers Cross, Castlebellingham | 4 | St. John of God Housing Association Ltd |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1273 | CAS CONSTRUCTION | Louth | 5 Slieveroe Crescent, Dundalk | 1 | Cluid Housing Association | [5 empty] | Q4-2021
1274 | CAS CONSTRUCTION | Louth | Barrack Street, Dundalk | 30 | Simon Community : Dundalk Simon |  | Stage 2 approved Q4-2022, full design/tender being prepared.
1275 | CAS CONSTRUCTION | Louth | Coulter Park, Dundalk | 10 | Túath Housing Association Ltd |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
1276 | CAS CONSTRUCTION | Louth | Four Winds, Mullacapple, Collon | 4 | St. John of God Housing Association Ltd | [5 empty] | Q3-2022
1277 | CAS CONSTRUCTION | Louth | Riverwell Close, Dundalk | 1 | Respond |  | Stage 2 approved Q4-2022, full design/tender being prepared.
1278 | CAS CONSTRUCTION | Louth | DVR @ Highfield, Newry Road, Dundalk | 12 | Women's Aid (Dundalk) CLG |  | Stage 2 approved Q3-2023, full design/tender being prepared.
1279 | SHIP CONSTRUCTION TURNKEY | Mayo | Bunree, Ballina | 3 | *N/A | [5 empty] | Q4-2022
1280 | SHIP CONSTRUCTION TURNKEY | Mayo | Silver Springs, Claremorris | 20 | *N/A | [5 empty] | Q4-2022
1281 | SHIP CONSTRUCTION TURNKEY | Mayo | Main St., Charlestown | 2 | *N/A | [5 empty] | Q4-2021
1282 | SHIP CONSTRUCTION TURNKEY | Mayo | Aidan St., Kiltimagh | 2 | N/A | [5 empty] | Q4-2022
1283 | SHIP CONSTRUCTION TURNKEY | Mayo | Mark C. Henry Lane, Charlestown | 5 | N/A |  |  |  |  | Q3-2023
1284 | SHIP CONSTRUCTION TURNKEY | Mayo | Market Place, Kilkelly | 4 | N/A |  |  |  |  | Q2-2023
1285 | SHIP CONSTRUCTION TURNKEY | Mayo | Abbey St., Ballina | 3 | N/A | [5 empty] | Q4-2023
1286 | SHIP CONSTRUCTION TURNKEY | Mayo | Carter Square, Belmullet | 4 | N/A |  |  |  |  | Q4-2023
1287 | SHIP CONSTRUCTION TURNKEY | Mayo | Ballagh St., Charlestown | 2 | N/A | [5 empty] | Q4-2023
1288 | SHIP CONSTRUCTION TURNKEY | Mayo | Bridge St., Kilkelly | 1 | N/A | [5 empty] | Q4-2023
1289 | SHIP CONSTRUCTION TURNKEY | Mayo | Barrack St., Belmullet | 8 | N/A |  |  |  |  | Q3-2023
1290 | SHIP CONSTRUCTION TURNKEY | Mayo | Chestnut Grove, Castlebar | 4 | N/A | [5 empty] | Q4-2023
1291 | SHIP CONSTRUCTION TURNKEY | Mayo | Cois Na hAbhainn, Bonniconlon | 4 | N/A |  |  |  |  | Q3-2023
1292 | SHIP CONSTRUCTION TURNKEY | Mayo | Acha Mhara, Shore Road, Belmullet | 8 | N/A |  |  |  |  | Q3-2023
1293 | SHIP CONSTRUCTION TURNKEY | Mayo | Turlough Road, Castlebar | 33 | N/A |  |  |  |  | Q3-2024
1294 | SHIP CONSTRUCTION TURNKEY | Mayo | Lower Barrack Street, Belmullet | 1 | N/A |  |  |  |  | Q4-2022
1295 | SHIP CONSTRUCTION TURNKEY | Mayo | Chestnut Grove, Castlebar | 4 | N/A |  |  |  |  | Q3-2023
1296 | SHIP CONSTRUCTION TURNKEY | Mayo | Fr. Mulhern Crescent, Belmullet | 3 | N/A |  |  |  |  | Q1-2024
1297 | SHIP CONSTRUCTION TURNKEY | Mayo | 37 St. Patrick's Ave., Castlebar | 1 | N/A |  |  |  |  | Q4-2022
1298 | SHIP CONSTRUCTION TURNKEY | Mayo | Acha Mhara,Belmullet (Phase 2) | 4 | N/A |  |  |  |  | Q2-2024
1299 | SHIP CONSTRUCTION TURNKEY | Mayo | Broadhaven View, Belmullet | 4 | N/A |  |  |  |  | Q1-2024
1300 | SHIP CONSTRUCTION TURNKEY | Mayo | Lugalisheen North, Ballindine | 5 | N/A |  |  |  |  | Q2-2024
1301 | SHIP CONSTRUCTION SINGLE STAGE | Mayo | Market Street, Swinford | 3 | *N/A |  |  |  | Stage 4 approved Q1-2022, the scheme is fully approved.
1302 | SHIP CONSTRUCTION SINGLE STAGE | Mayo | The Boreen, Crossmolina | 3 | *N/A | [5 empty] | Q4-2021
1303 | SHIP CONSTRUCTION SINGLE STAGE | Mayo | Deel Court, Crossmolina | 3 | *N/A | [5 empty] | Q4-2021
1304 | SHIP CONSTRUCTION SINGLE STAGE | Mayo | Knockroe, Moygownagh | 3 | *N/A | [5 empty] | Q4-2021
1305 | SHIP CONSTRUCTION SINGLE STAGE | Mayo | Low Park, Charlestown | 3 | *N/A | [5 empty] | Q4-2021
1306 | SHIP CONSTRUCTION SINGLE STAGE | Mayo | Church Manor, Ballina | 3 | N/A |  |  |  |  | Q2-2024
1307 | SHIP CONSTRUCTION SINGLE STAGE | Mayo | Mount St., Claremorris | 6 | N/A |  |  |  |  | Q2-2024
1308 | SHIP CONSTRUCTION SINGLE STAGE | Mayo | Lower Charles St., Castlebar | 4 | N/A |  |  |  |  | Q3-2024
1309 | SHIP CONSTRUCTION SINGLE STAGE | Mayo | Market St., Killala | 4 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1310 | SHIP CONSTRUCTION SINGLE STAGE | Mayo | Cum, Lahardane, Ballina | 19 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1311 | SHIP CONSTRUCTION SINGLE STAGE | Mayo | Ard Caher, Louisburgh | 13 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1312 | SHIP CONSTRUCTION RENEWAL | Mayo | Main St., Hollymount | 1 | N/A | [5 empty] | Q4-2022
1313 | SHIP CONSTRUCTION RENEWAL | Mayo | Bridge St., Kilkelly | 1 | N/A |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
1314 | SHIP CONSTRUCTION RENEWAL | Mayo | 59 Riverdale Court, Castlebar | 1 | N/A |  |  |  |  | Q3-2024
1315 | SHIP CONSTRUCTION RENEWAL | Mayo | 95 St. Patrick's Estate, Ballina | 1 | N/A | [5 empty] | Q3-2023
1316 | SHIP CONSTRUCTION RENEWAL | Mayo | Convent Rd., Ballinrobe | 3 | N/A | Stage 1 approved Q3-2023, outline design and costs being prepared.
1317 | SHIP CONSTRUCTION RENEWAL | Mayo | Castlebar Rd., Ballinrobe | 5 | N/A | Stage 1 approved Q3-2023, outline design and costs being prepared.
1318 | SHIP CONSTRUCTION RENEWAL | Mayo | Creagh Rd., Ballinrobe | 3 | N/A | Stage 1 approved Q3-2023, outline design and costs being prepared.
1319 | SHIP CONSTRUCTION RENEWAL | Mayo | Main St., Ballinrobe | 3 | N/A | Stage 1 approved Q3-2023, outline design and costs being prepared.
1320 | SHIP CONSTRUCTION RENEWAL | Mayo | Rosario, Lowpark, Charlestown | 2 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1321 | SHIP CONSTRUCTION RENEWAL | Mayo | 68 Lowpark, Charlestown | 3 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1322 | SHIP CONSTRUCTION RENEWAL | Mayo | 151 Greenhills Estate, Ballina | 1 | N/A |  |  |  |  | Q3-2024
1323 | SHIP CONSTRUCTION RENEWAL | Mayo | 105 St. Patrick's Estate, Ballina | 1 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1324 | SHIP CONSTRUCTION RENEWAL | Mayo | 4 Tyrawley Terrace | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1325 | SHIP CONSTRUCTION RENEWAL | Mayo | 10 Tyrawley Terrace, Ballina | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1326 | SHIP CONSTRUCTION RENEWAL | Mayo | 3 Woodlands, Balla | 1 | N/A |  |  |  |  | Q3-2024
1327 | SHIP CONSTRUCTION RENEWAL | Mayo | 88 Lord Edward Street, Ballina | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1328 | SHIP CONSTRUCTION RENEWAL | Mayo | 130 Greenhills Estate, Ballina | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1329 | SHIP CONSTRUCTION RENEWAL | Mayo | 53 Lord Edward St., Ballina | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1330 | SHIP CONSTRUCTION RENEWAL | Mayo | 26 Roches Terrace, Ballina | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1331 | SHIP CONSTRUCTION RENEWAL | Mayo | Blackoak, Barrack Hill, Newport | 9 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1332 | SHIP CONSTRUCTION RENEWAL | Mayo | 47 Tyrawley Terrace , Ballina | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1333 | SHIP CONSTRUCTION RENEWAL | Mayo | 48 Tyrawley Terrace , Ballina | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1334 | SHIP CONSTRUCTION RENEWAL | Mayo | 26 Clareville, Claremorris | 1 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1335 | SHIP CONSTRUCTION RENEWAL | Mayo | James St., Kiltimagh | 2 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1336 | SHIP CONSTRUCTION DESIGN BUILD | Mayo | Murrevagh, Mulranny | 16 | *N/A |  |  |  |  | Q2-2023
1337 | SHIP CONSTRUCTION | Mayo | Lios na Circa, Saleen, Castlebar - Phase 2 | 22 | *N/A | [5 empty] | Q4-2023
1338 | SHIP CONSTRUCTION | Mayo | Cross | 8 | *N/A |  |  |  |  | Q1-2024
1339 | SHIP CONSTRUCTION | Mayo | Bonniconlon | 5 | *N/A | [5 empty] | Q4-2021
1340 | SHIP CONSTRUCTION | Mayo | Cloonkeadagh Road, Kiltimagh | 21 | *N/A |  |  |  |  | Q4-2022
1341 | SHIP CONSTRUCTION | Mayo | Rehins Fort, Ballina | 32 | *N/A | [5 empty] | Q4-2022
1342 | SHIP CONSTRUCTION | Mayo | Golf Course Road, Westport | 45 | *N/A |  |  |  |  | Q4-2022
1343 | SHIP CONSTRUCTION | Mayo | Ballyglass, Carnacon, Claremorris | 9 | *N/A |  |  |  |  | Q4-2023
1344 | SHIP CONSTRUCTION | Mayo | Atlantic Drive ,Belmullet | 4 | *N/A | [5 empty] | Q4-2023
1345 | SHIP CONSTRUCTION | Mayo | Liskilleen, Ballinrobe, | 1 | *N/A | [5 empty] | Q4-2022
1346 | SHIP CONSTRUCTION | Mayo | Main Street, Ballyvary | 12 | *N/A |  |  |  |  | Q4-2023
1347 | SHIP CONSTRUCTION | Mayo | Rehins Fort, Ballina | 18 | *N/A | [5 empty] | Q4-2023
1348 | SHIP CONSTRUCTION | Mayo | Polranny, Achill Sound | 20 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1349 | SHIP CONSTRUCTION | Mayo | Lios Na Circa, Saleen, Castlebar | 36 | N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
1350 | SHIP CONSTRUCTION | Mayo | Ellison Street Castlebar | 10 | N/A | Stage 1 approved Q3-2023, outline design and costs being prepared.
1351 | SHIP CONSTRUCTION | Mayo | Cheshire Home Site, Ballina, Co. Mayo | 69 | *N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
1352 | SHIP CONSTRUCTION | Mayo | Meadows Site, Ballina, Co. Mayo | 15 | *N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
1353 | SHIP CONSTRUCTION | Mayo | Duffy's Bakery, Ballina, Co. Mayo | 34 | *N/A | Stage 1 approved Q3-2023, outline design and costs being prepared.
1354 | SHIP CONSTRUCTION | Mayo | Abbeyquarter Phase 2, Ballyhaunis | 28 | N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
1355 | CAS CONSTRUCTION TURNKEY | Mayo | Apt 1-8 Tone Street, Ballina | 8 | Peter McVerry Trust Ltd | [5 empty] | Q4-2022
1356 | CAS CONSTRUCTION RENEWAL | Mayo | 20 NewLine , Castlebar | 2 | Mayo Mental Health Association |  |  |  |  | Q3-2022
1357 | CAS CONSTRUCTION RENEWAL | Mayo | Tullysleva, Ballina | 1 | Western Care Association | [5 empty] | Q2-2024
1358 | CAS CONSTRUCTION RENEWAL | Mayo | 27 Clareville, Claremorris | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1359 | CAS CONSTRUCTION RENEWAL | Mayo | 4 Spencer St., Castlebar | 2 | Mayo Mental Health Association |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1360 | CAS CONSTRUCTION | Mayo | Group Home Kilbride, Swinford | 4 | Sophia Housing Association Ltd |  |  | Stage 3 approved Q4-2023, the scheme is now approved to proceed to tender.
1361 | CAS CONSTRUCTION | Mayo | Mount St Mary's Convent, Westport | 18 | Túath Housing Association Ltd |  | Stage 2 approved Q3-2023, full design/tender being prepared.
1362 | CAS CONSTRUCTION | Mayo | Chapel Road, Ballinrobe | 5 | Sophia Housing Association Ltd | Stage 1 approved Q3-2022, outline design and costs being prepared.
1363 | CAS CONSTRUCTION | Mayo | Knockphunta, Mount Gordon, Castlebar | 4 | Sophia Housing Association Ltd | Stage 1 approved Q2-2023, outline design and costs being prepared.
1364 | SHIP CONSTRUCTION TURNKEY | Meath | The Brambles, Longford Rd., Duleek | 13 | *N/A | [5 empty] | Q3-2022
1365 | SHIP CONSTRUCTION TURNKEY | Meath | Connaught Street, Athboy | 5 | *N/A | [5 empty] | Q4-2022
1366 | SHIP CONSTRUCTION TURNKEY | Meath | Lynfield, Town Parks, Oldcastle Road, Kells | 6 | *N/A | [5 empty] | Q1-2023
1367 | SHIP CONSTRUCTION TURNKEY | Meath | Connaught Street, Athboy | 2 | *N/A | [5 empty] | Q2-2022
1368 | SHIP CONSTRUCTION TURNKEY | Meath | 23-24 Dunville Avenue, Navan | 2 | *N/A | [5 empty] | Q4-2022
1369 | SHIP CONSTRUCTION TURNKEY | Meath | Bakery Lane, Navan | 4 | *N/A | [5 empty] | Q1-2024
1370 | SHIP CONSTRUCTION TURNKEY | Meath | The Brambles, Longford Rd., Duleek | 3 | *N/A | [5 empty] | Q4-2022
1371 | SHIP CONSTRUCTION TURNKEY | Meath | Lynfield, Town Parks, Oldcastle Road, Kells | 6 | *N/A | [5 empty] | Q2-2023
1372 | SHIP CONSTRUCTION TURNKEY | Meath | Donacarney Village Square, Donacarney | 12 | N/A | [5 empty] | Q2-2023
1373 | SHIP CONSTRUCTION TURNKEY | Meath | The Glebe, Rathmolyon | 1 | *N/A | [5 empty] | Q4-2022
1374 | SHIP CONSTRUCTION TURNKEY | Meath | Avourwen, Drogheda, Co. Meath | 30 | *N/A |  |  |  |  | Q2-2024
1375 | SHIP CONSTRUCTION TURNKEY | Meath | Sanderling Park, Narroways, Bettystown | 12 | *N/A | [5 empty] | Q2-2024
1376 | SHIP CONSTRUCTION TURNKEY | Meath | Donacarney Village Square, Donacarney | 11 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1377 | SHIP CONSTRUCTION TURNKEY | Meath | Sycamore Abbey, Flower Hill, Navan, Co. Meath | 14 | N/A |  |  |  |  | Q1-2022
1378 | SHIP CONSTRUCTION TURNKEY | Meath | Clos Na Croise, Ballivor, Co Meath | 8 | N/A |  |  |  |  | Q3-2022
1379 | SHIP CONSTRUCTION TURNKEY | Meath | Donacarney Village Square, Donacarney, Co. Meath | 5 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1380 | SHIP CONSTRUCTION TURNKEY | Meath | Stonebridge View, Kells | 1 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1381 | SHIP CONSTRUCTION TURNKEY | Meath | Sanderling Park, Narroways, Bettystown | 20 | *N/A | [5 empty] | Q3-2024
1382 | SHIP CONSTRUCTION TURNKEY | Meath | Sanderling Park, Narroways, Bettystown | 44 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
1383 | SHIP CONSTRUCTION TURNKEY | Meath | Aylesbury House, Clonee | 37 | *N/A |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
1384 | SHIP CONSTRUCTION TURNKEY | Meath | Aylesbury House, Clonee | 29 | *N/A |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
1385 | SHIP CONSTRUCTION SINGLE STAGE | Meath | Ivy Cottage, New Lands, | 1 | *N/A |  |  |  |  | Q3-2024
1386 | SHIP CONSTRUCTION RENEWAL | Meath | Carrick St., Kells | 47 | *N/A |  | Stage 2 approved Q4-2022, full design/tender being prepared.
1387 | SHIP CONSTRUCTION RENEWAL | Meath | Broville, Corballis, Laytown | 1 | *N/A | [5 empty] | Q4-2022
1388 | SHIP CONSTRUCTION RENEWAL | Meath | Glenidan Court, Enfield | 1 | *N/A | [5 empty] | Q1-2022
1389 | SHIP CONSTRUCTION RENEWAL | Meath | Carrick Street, Kells | 1 | *N/A | [5 empty] | Q3-2022
1390 | SHIP CONSTRUCTION RENEWAL | Meath | Mornington Heights, Trim | 1 | *N/A | [5 empty] | Q2-2024
1391 | SHIP CONSTRUCTION RENEWAL | Meath | Churchlands, Slane | 1 | N/A | [5 empty] | Q3-2023
1392 | SHIP CONSTRUCTION RENEWAL | Meath | Alverno Heights, Laytown | 1 | N/A | [5 empty] | Q4-2023
1393 | SHIP CONSTRUCTION RENEWAL | Meath | Woodview Heights, Dunboyne, Co. Meath | 2 | N/A |  |  |  |  | Q3-2024
1394 | SHIP CONSTRUCTION RENEWAL | Meath | The Drive, Athlumney Abbey, Navan | 1 | *N/A | [5 empty] | Q3-2023
1395 | SHIP CONSTRUCTION RENEWAL | Meath | Magdeline Court, Kells | 1 | N/A | [5 empty] | Q4-2023
1396 | SHIP CONSTRUCTION RENEWAL | Meath | O'Carolan Park, Nobber | 1 | N/A | [5 empty] | Q4-2023
1397 | SHIP CONSTRUCTION RENEWAL | Meath | The Belfry, Athboy Road, Trim | 1 | N/A | [5 empty] | Q1-2024
1398 | SHIP CONSTRUCTION RENEWAL | Meath | Bourne Avenue, Ashbourne | 1 | N/A | [5 empty] | Q4-2023
1399 | SHIP CONSTRUCTION RENEWAL | Meath | Headford Grove, Kells | 1 | N/A | [5 empty] | Q3-2023
1400 | SHIP CONSTRUCTION RENEWAL | Meath | Reask Green, Navan | 1 | N/A | [5 empty] | Q2-2024
1401 | SHIP CONSTRUCTION RENEWAL | Meath | Troytown Heights, Navan | 1 | N/A | [5 empty] | Q2-2024
1402 | SHIP CONSTRUCTION RENEWAL | Meath | Cherryhill Green, Kells, | 1 | N/A | [5 empty] | Q2-2024
1403 | SHIP CONSTRUCTION | Meath | Staleen Park, Donore | 21 | *N/A | [5 empty] | Q4-2022
1404 | SHIP CONSTRUCTION | Meath | Dunshaughlin | 26 | *N/A | [5 empty] | Q4-2021
1405 | SHIP CONSTRUCTION | Meath | Gort na Glaise, Farganstown, Navan | 84 | *N/A |  |  |  |  | Q1-2023
1406 | SHIP CONSTRUCTION | Meath | Blackhill Crescent, Donacarney, Co. Meath | 2 | *N/A |  |  | Stage 3 approved Q4-2022, the scheme is now approved to proceed to tender.
1407 | SHIP CONSTRUCTION | Meath | Archdeaconary Glebe, Kells | 22 | *N/A |  | Stage 2 approved Q1-2020, full design/tender being prepared.
1408 | SHIP CONSTRUCTION | Meath | Nangle Court, Navan | 15 | *N/A |  | Stage 2 approved Q1-2021, full design/tender being prepared.
1409 | SHIP CONSTRUCTION | Meath | Castle Street, Ashbourne | 74 | *N/A |  |  |  |  | Q4-2022
1410 | SHIP CONSTRUCTION | Meath | Church View, Rathmolyon | 22 | *N/A |  |  | Stage 3 approved Q4-2022, the scheme is now approved to proceed to tender.
1411 | SHIP CONSTRUCTION | Meath | Haggard Street, Trim | 4 | *N/A |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
1412 | SHIP CONSTRUCTION | Meath | Pitcher Lane, Kells, Co. Meath | 5 | *N/A |  |  |  |  | Q2-2024
1413 | SHIP CONSTRUCTION | Meath | Swan Lane, Balreask | 6 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
1414 | SHIP CONSTRUCTION | Meath | Lagore, Dunshaughlin | 42 | *N/A | [5 empty] | Q4-2023
1415 | SHIP CONSTRUCTION | Meath | Convent Lands, Kildalkey, Athboy | 28 | *N/A | [5 empty] | Q3-2024
1416 | SHIP CONSTRUCTION | Meath | Ratholdren Court, Navan | 27 | *N/A |  |  | Stage 3 approved Q3-2023, the scheme is now approved to proceed to tender.
1417 | SHIP CONSTRUCTION | Meath | Brews Hill, Navan, Co.Meath | 12 | *N/A |  |  |  |  | Q1-2024
1418 | SHIP CONSTRUCTION | Meath | Newtown, Drumconrath, Co. Meath | 1 | *N/A |  |  |  |  | Q3-2024
1419 | SHIP CONSTRUCTION | Meath | New Lane, Abbey Lands, Navan | 6 | *N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
1420 | SHIP CONSTRUCTION | Meath | Archers Glen, Ashewood, Ashbourne | 79 | *N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
1421 | SHIP Accel MMC | Meath | Connaught Grove, Athboy (Phase 2) | 47 | *N/A |  |  |  |  | Q3-2024
1422 | CAS CONSTRUCTION TURNKEY | Meath | Gainsfield, (Gort Fionnbarra) Commons Road, Navan | 6 | Túath Housing Association Ltd | [5 empty] | Q2-2021
1423 | CAS CONSTRUCTION TURNKEY | Meath | 6-7 Knightsbrook Close, Iffernock, Trim | 2 | Túath Housing Association Ltd | [5 empty] | Q4-2021
1424 | CAS CONSTRUCTION TURNKEY | Meath | 4-5 Oak Hall, Carlanstown | 2 | Túath Housing Association Ltd | [5 empty] | Q4-2022
1425 | CAS CONSTRUCTION TURNKEY | Meath | Flowerhill Lodge, Navan, Co Meath | 5 | North ＆ East Housing Association Ltd |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1426 | CAS CONSTRUCTION RENEWAL | Meath | Painestown, Kilmoon, Dunshaughlin | 1 | Marillac Housing Association |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1427 | CAS CONSTRUCTION | Meath | DVR @ Tailteann Drive, Windtown, Navan | 8 | Meath Women’s Housing Association CLG | Stage 1 approved Q2-2020, outline design and costs being prepared.
1428 | CAS CONSTRUCTION | Meath | St. Lomans Street, Trim | 4 | Society of Saint Vincent de Paul | Stage 1 approved Q3-2022, outline design and costs being prepared.
1429 | CAS CONSTRUCTION | Meath | Park Avenue, Church Street, Oldcastle | 5 | Society of Saint Vincent de Paul | Stage 1 approved Q3-2021, outline design and costs being prepared.
1430 | CAS CONSTRUCTION | Meath | Donaghmore Road, Blackcastle, Navan | 1 | Tabor Lodge Addiction ＆ Housing Services Ltd | Stage 1 approved Q3-2024, outline design and costs being prepared.
1431 | SHIP CONSTRUCTION TURNKEY | Monaghan | Ard an Radhairc Carrickmacross | 6 | *N/A | [5 empty] | Q4-2021
1432 | SHIP CONSTRUCTION TURNKEY | Monaghan | Coill Darach, Bree, Castleblayney | 16 | *N/A | [5 empty] | Q4-2022
1433 | SHIP CONSTRUCTION TURNKEY | Monaghan | Coill an Ri, Carrickmacross | 4 | *N/A |  |  |  |  | Q3-2023
1434 | SHIP CONSTRUCTION TURNKEY | Monaghan | Knockcarrick, Annyalla | 12 | *N/A | [5 empty] | Q1-2024
1435 | SHIP CONSTRUCTION TURNKEY | Monaghan | Ard an Radhairc Carrickmacross | 28 | *N/A | [5 empty] | Q3-2022
1436 | SHIP CONSTRUCTION TURNKEY | Monaghan | Ballinode | 10 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
1437 | SHIP CONSTRUCTION TURNKEY | Monaghan | Ard an Radhairc Carrickmacross | 7 | *N/A | [5 empty] | Q4-2022
1438 | SHIP CONSTRUCTION TURNKEY | Monaghan | Coill Darach, Castleblayney | 14 | *N/A | [5 empty] | Q4-2022
1439 | SHIP CONSTRUCTION TURNKEY | Monaghan | Cnoc na Gréine, Tydavnet | 4 | *N/A | [5 empty] | Q4-2023
1440 | SHIP CONSTRUCTION TURNKEY | Monaghan | Coill an Rí, Carrickmacross | 9 | *N/A | [5 empty] | Q3-2024
1441 | SHIP CONSTRUCTION TURNKEY | Monaghan | Coill an Rí, Carrickmacross | 7 | *N/A |  |  |  |  | Q3-2023
1442 | SHIP CONSTRUCTION TURNKEY | Monaghan | Coill an Rí, Carrickmacross | 10 | *N/A |  |  |  |  | Q3-2023
1443 | SHIP CONSTRUCTION TURNKEY | Monaghan | Knockcarrick, Annyalla | 8 | *N/A | [5 empty] | Q2-2024
1444 | SHIP CONSTRUCTION TURNKEY | Monaghan | Knockcarrick, Annyalla | 10 | *N/A | [5 empty] | Q3-2024
1445 | SHIP CONSTRUCTION TURNKEY | Monaghan | Station View, Monaghan Town | 18 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1446 | SHIP CONSTRUCTION TURNKEY | Monaghan | Knockcarrick, Annyalla, Caslteblaney | 10 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1447 | SHIP CONSTRUCTION TURNKEY | Monaghan | Cois Abhainn, Ballinode | 12 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
1448 | SHIP CONSTRUCTION SINGLE STAGE | Monaghan | Folly Court, Ballybay | 6 | *N/A | [5 empty] | Q4-2021
1449 | SHIP CONSTRUCTION RENEWAL | Monaghan | 82 & 83 Fermanagh St., Clones | 3 | *N/A | [5 empty] | Q3-2022
1450 | SHIP CONSTRUCTION RENEWAL | Monaghan | An Bonnan Bui & Flower Shop, Fermanagh St., Clones | 6 | *N/A | [5 empty] | Q2-2022
1451 | SHIP CONSTRUCTION RENEWAL | Monaghan | 2a & 3 Analore St., Clones | 2 | *N/A | [5 empty] | Q4-2022
1452 | SHIP CONSTRUCTION RENEWAL | Monaghan | Abbey Gatehouse, Analore St., Clones | 4 | *N/A | [5 empty] | Q4-2022
1453 | SHIP CONSTRUCTION RENEWAL | Monaghan | 63 Fermanagh St., Clones | 3 | *N/A | [5 empty] | Q2-2022
1454 | SHIP CONSTRUCTION DESIGN BUILD | Monaghan | Latlorcan Monaghan Town | 51 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
1455 | SHIP CONSTRUCTION DESIGN BUILD | Monaghan | Slí NaCoille, Mullaghmatt, Monaghan | 21 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
1456 | SHIP CONSTRUCTION | Monaghan | Lui Na Greine, Scotstown | 6 | *N/A | [5 empty] | Q4-2021
1457 | SHIP CONSTRUCTION | Monaghan | 12 Church St., Ballybay | 2 | *N/A | [5 empty] | Q4-2022
1458 | SHIP CONSTRUCTION | Monaghan | Church Hill, Clones | 2 | *N/A | [5 empty] | Q4-2022
1459 | SHIP CONSTRUCTION | Monaghan | 13 McCurtain Street, Clones | 1 | *N/A | [5 empty] | Q4-2023
1460 | SHIP CONSTRUCTION | Monaghan | Lui na Greine, Scotstown | 12 | *N/A | [5 empty] | Q2-2022
1461 | SHIP CONSTRUCTION | Monaghan | An Clós, Cornamucklaglass, Ballybay | 7 | *N/A | [5 empty] | Q4-2023
1462 | SHIP CONSTRUCTION | Monaghan | Lui na Greine, Scotstown | 1 | *N/A | [5 empty] | Q2-2022
1463 | SHIP CONSTRUCTION | Monaghan | Lui na Greine, Scotstown | 5 | *N/A | [5 empty] | Q3-2022
1464 | SHIP CONSTRUCTION | Monaghan | Lui na Greine, Scotstown | 8 | *N/A | [5 empty] | Q4-2022
1465 | SHIP CONSTRUCTION | Monaghan | 10 & 12 Cara St., Clones | 7 | *N/A | Stage 1 approved Q1-2023, outline design and costs being prepared.
1466 | SHIP CONSTRUCTION | Monaghan | 15 Dublin St., Monaghan | 6 | *N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
1467 | SHIP CONSTRUCTION | Monaghan | Old Cross Sq., Monaghan Town | 7 | *N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
1468 | CAS CONSTRUCTION TURNKEY | Monaghan | Radharc an Bhri, Castleblaney | 9 | Túath Housing Association Ltd |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1469 | CAS CONSTRUCTION | Monaghan | Liseggerton, Clones | 19 | Oaklee Housing Trust | [5 empty] | Q2-2021
1470 | CAS CONSTRUCTION | Monaghan | Birch Court Apts., 34 Main Street, Ballybay | 4 | North ＆ East Housing Association Ltd | [5 empty] | Q4-2023
1471 | CAS CONSTRUCTION | Monaghan | Castleblayney Fire Station Site | 19 | North ＆ East Housing Association Ltd | Stage 1 approved Q4-2023, outline design and costs being prepared.
1472 | SHIP CONSTRUCTION TURNKEY | Offaly | Main Street, Daingean | 8 | *N/A | [5 empty] | Q4-2021
1473 | SHIP CONSTRUCTION TURNKEY | Offaly | Woodfield, Birr | 5 | *N/A | [5 empty] | Q4-2021
1474 | SHIP CONSTRUCTION TURNKEY | Offaly | Cluain na Greine, Clonygowan | 2 | *N/A | [5 empty] | Q2-2021
1475 | SHIP CONSTRUCTION TURNKEY | Offaly | Coolgarry, Walsh Island | 4 | *N/A | [5 empty] | Q4-2022
1476 | SHIP CONSTRUCTION TURNKEY | Offaly | Castle View, Mucklagh, Tullamore | 8 | *N/A | [5 empty] | Q2-2022
1477 | SHIP CONSTRUCTION TURNKEY | Offaly | MacRegol Pairc, Birr | 2 | *N/A | [5 empty] | Q1-2021
1478 | SHIP CONSTRUCTION TURNKEY | Offaly | Bog Road, Portarlington | 28 | *N/A | [5 empty] | Q2-2024
1479 | SHIP CONSTRUCTION TURNKEY | Offaly | MacRegol Pairc, Birr | 4 | *N/A | [5 empty] | Q2-2021
1480 | SHIP CONSTRUCTION TURNKEY | Offaly | Woodfield, Birr | 6 | *N/A | [5 empty] | Q2-2022
1481 | SHIP CONSTRUCTION TURNKEY | Offaly | Woodfield, Birr | 5 | *N/A | [5 empty] | Q1-2022
1482 | SHIP CONSTRUCTION TURNKEY | Offaly | Woodfield, Birr | 8 | *N/A | [5 empty] | Q3-2022
1483 | SHIP CONSTRUCTION TURNKEY | Offaly | Woodfield, Birr | 10 | N/A | [5 empty] | Q4-2022
1484 | SHIP CONSTRUCTION TURNKEY | Offaly | Bell Lane, Daingean | 6 | *N/A | [5 empty] | Q3-2023
1485 | SHIP CONSTRUCTION TURNKEY | Offaly | Macregol Pairc, Birr | 4 | N/A | [5 empty] | Q1-2024
1486 | SHIP CONSTRUCTION TURNKEY | Offaly | Macregol Pairc, Birr | 2 | N/A | [5 empty] | Q2-2024
1487 | SHIP CONSTRUCTION TURNKEY | Offaly | Macregol Pairc, Birr | 12 | N/A |  |  |  |  | Q1-2023
1488 | SHIP CONSTRUCTION TURNKEY | Offaly | Cois na hAbhainn Ferbane | 2 | N/A |  |  |  |  | Q3-2024
1489 | SHIP CONSTRUCTION RENEWAL | Offaly | 1 Newbridge St., Birr | 1 | *N/A | [5 empty] | Q3-2022
1490 | SHIP CONSTRUCTION RENEWAL | Offaly | Church Hill, Tullamore | 2 | *N/A | [5 empty] | Q3-2022
1491 | SHIP CONSTRUCTION RENEWAL | Offaly | 9 Twickenham, Ballycumer | 1 | N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
1492 | SHIP CONSTRUCTION | Offaly | Beechwood Drive, Circular Road, Daingean | 9 | *N/A |  |  |  |  | Q1-2023
1493 | SHIP CONSTRUCTION | Offaly | Kylebeg, Banagher (Phase 2) | 18 | *N/A | [5 empty] | Q3-2023
1494 | SHIP CONSTRUCTION | Offaly | Beechgrove, Belmont | 7 | *N/A | [5 empty] | Q4-2023
1495 | SHIP CONSTRUCTION | Offaly | Raheen ,Clara | 38 | *N/A |  |  |  |  | Q1-2023
1496 | SHIP CONSTRUCTION | Offaly | Elderberry Drive, Moneygall | 4 | *N/A | [5 empty] | Q4-2022
1497 | SHIP CONSTRUCTION | Offaly | Sr. Senan Avenue, Edenderry | 4 | *N/A |  |  |  |  | Q2-2022
1498 | SHIP CONSTRUCTION | Offaly | Dargan Drive, Chancery Lane, Tullamore (Phase 2) | 20 | *N/A |  | Stage 2 approved Q4-2021, full design/tender being prepared.
1499 | SHIP CONSTRUCTION | Offaly | Sycamore Drive, Ballycumber | 10 | *N/A |  | Stage 2 approved Q4-2022, full design/tender being prepared.
1500 | SHIP CONSTRUCTION | Offaly | Beeechwood Court, Circular Road, Daingean Phase 2 | 10 | *N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
1501 | CAS CONSTRUCTION | Offaly | Killane Court, Edenderry | 2 | Túath Housing Association Ltd | [5 empty] | Q2-2021
1502 | CAS CONSTRUCTION | Offaly | Clonminch, Tullamore | 19 | Oaklee Housing Trust | [5 empty] | Q4-2022
1503 | CAS CONSTRUCTION | Offaly | Presentation Lands, Portarlington | 37 | Sophia Housing Association Ltd |  | Stage 2 approved Q1-2024, full design/tender being prepared.
1504 | CAS CONSTRUCTION | Offaly | Clonamore House Hotel, Tullamore | 17 | Sophia Housing Association Ltd | [5 empty] | Q3-2023
1505 | SHIP CONSTRUCTION TURNKEY | Roscommon | Esker Lawns, Old Tuam Rd, Monksland | 11 | *N/A | [5 empty] | Q4-2023
1506 | SHIP CONSTRUCTION TURNKEY | Roscommon | Esker Lawns, Old Tuam Rd, Monksland | 11 | N/A | [5 empty] | Q4-2023
1507 | SHIP CONSTRUCTION TURNKEY | Roscommon | Esker Lawns, Old Tuam Rd, Monksland | 2 | N/A | [5 empty] | Q1-2024
1508 | SHIP CONSTRUCTION TURNKEY | Roscommon | Ardnanagh, Lisnamult | 3 | *N/A | [5 empty] | Q3-2024
1509 | SHIP CONSTRUCTION TURNKEY | Roscommon | Lisroyne, Strokestown | 6 | N/A |  |  |  |  | Q1-2024
1510 | SHIP CONSTRUCTION TURNKEY | Roscommon | Old Tuam Rd., Monksland | 8 | N/A |  |  |  |  | Q4-2023
1511 | SHIP CONSTRUCTION TURNKEY | Roscommon | The Paddock, Athleague, Co. Roscommon | 10 | *N/A |  |  |  |  | Q1-2024
1512 | SHIP CONSTRUCTION SINGLE STAGE | Roscommon | The Meadows, Castlerea | 2 | *N/A | [5 empty] | Q4-2022
1513 | SHIP CONSTRUCTION SINGLE STAGE | Roscommon | Dysart | 1 | *N/A |  |  |  |  | Q1-2024
1514 | SHIP CONSTRUCTION SINGLE STAGE | Roscommon | Greenfield Road, Roscommon Road | 2 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1515 | SHIP CONSTRUCTION SINGLE STAGE | Roscommon | 2 no. Units Milner/Tarraville St. Patrick's St, Castlerea | 2 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1516 | SHIP CONSTRUCTION RENEWAL | Roscommon | Elphin Courthouse, Elphin | 4 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1517 | SHIP CONSTRUCTION RENEWAL | Roscommon | An Tarras, Pound St., Ballaghaderreen | 1 | *N/A |  |  |  |  | Q1-2024
1518 | SHIP CONSTRUCTION RENEWAL | Roscommon | 6 Arm, Castlerea | 1 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1519 | SHIP CONSTRUCTION | Roscommon | Cloonfad | 3 | *N/A | [5 empty] | Q2-2021
1520 | SHIP CONSTRUCTION | Roscommon | Cluain Fraoigh, Cloonbeirne | 7 | *N/A | [5 empty] | Q1-2021
1521 | SHIP CONSTRUCTION | Roscommon | Sli an Choiste, Monksland | 51 | *N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
1522 | SHIP CONSTRUCTION | Roscommon | Meadowbrook, Ballyclare Td., Ballyleague | 16 | *N/A | [5 empty] | Q4-2021
1523 | SHIP CONSTRUCTION | Roscommon | Parkgate, Elphin St., Strokestown | 10 | *N/A | [5 empty] | Q4-2021
1524 | SHIP CONSTRUCTION | Roscommon | Windmill Road, Elphin Road | 10 | *N/A | [5 empty] | Q3-2024
1525 | SHIP CONSTRUCTION | Roscommon | Lakeview Heights, Bellspark Td., Boyle | 6 | *N/A | [5 empty] | Q3-2023
1526 | SHIP CONSTRUCTION | Roscommon | Lisnamult, Ardnanagh, Roscommon Town | 12 | *N/A | [5 empty] | Q2-2024
1527 | SHIP CONSTRUCTION | Roscommon | Station Rd., Cortober, Carrick on Shannon | 4 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1528 | SHIP CONSTRUCTION | Roscommon | Cnoc na hAbhann (formerly Curlew View), Boyle | 16 | *N/A |  |  |  |  | Q3-2024
1529 | SHIP CONSTRUCTION | Roscommon | Elphin St, Strokestown | 3 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1530 | CAS CONSTRUCTION RENEWAL | Roscommon | 2 Tithe na gCarad, Willliamstown Road, Castlerea | 4 | Sophia Housing Association Ltd | Stage 1 approved Q3-2022, outline design and costs being prepared.
1531 | CAS CONSTRUCTION | Roscommon | Cherrylea, Knockroe, Castlerea | 4 | Roscara Housing Association Ltd | Stage 1 approved Q4-2023, outline design and costs being prepared.
1532 | CAS CONSTRUCTION | Roscommon | The Meadows, Longford Lower, Castlerea | 6 | Túath Housing Association Ltd |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
1533 | SHIP CONSTRUCTION TURNKEY | Sligo | Seaville, Ursuline Convent | 12 | *N/A | [5 empty] | Q2-2023
1534 | SHIP CONSTRUCTION TURNKEY | Sligo | Seaville, Ursuline Convent | 11 | *N/A | [5 empty] | Q2-2023
1535 | SHIP CONSTRUCTION TURNKEY | Sligo | Seaville, Ursuline Convent | 16 | *N/A | [5 empty] | Q3-2023
1536 | SHIP CONSTRUCTION TURNKEY | Sligo | Seaville, Ursuline Convent | 13 | *N/A | [5 empty] | Q4-2023
1537 | SHIP CONSTRUCTION TURNKEY | Sligo | Mass Hill, Tubbercurry | 5 | *N/A | [5 empty] | Q4-2023
1538 | SHIP CONSTRUCTION TURNKEY | Sligo | Seaville, Ursuline Convent | 14 | *N/A | [5 empty] | Q4-2023
1539 | SHIP CONSTRUCTION TURNKEY | Sligo | Radharc Na Habhann, Coolaney | 2 | *N/A | [5 empty] | Q1-2023
1540 | SHIP CONSTRUCTION | Sligo | Carrowbunnaun, Strandhill | 51 | *N/A |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
1541 | SHIP CONSTRUCTION | Sligo | Connolly Park, Tubbercurry (Phase 1) | 10 | *N/A | [5 empty] | Q4-2021
1542 | SHIP CONSTRUCTION | Sligo | Dromore West | 10 | *N/A | [5 empty] | Q4-2021
1543 | SHIP CONSTRUCTION | Sligo | Robbers' Lane, Maugheraboy, Sligo | 24 | *N/A |  |  |  |  | Q3-2024
1544 | SHIP CONSTRUCTION | Sligo | SRD at Crowagh, Dromore West | 1 | *N/A | [5 empty] | Q4-2021
1545 | SHIP CONSTRUCTION | Sligo | Gormley Park, Bunnanadden | 6 | *N/A | [5 empty] | Q4-2022
1546 | SHIP CONSTRUCTION | Sligo | Connolly Park, Tubbercurry (Phase 2) & The Green Rd, Collaney | 4 | *N/A | [5 empty] | Q4-2023
1547 | SHIP CONSTRUCTION | Sligo | Geldof Drive & Centre Park, Cranmore, Sligo | 30 | *N/A |  |  | Stage 3 approved Q4-2023, the scheme is now approved to proceed to tender.
1548 | SHIP CONSTRUCTION | Sligo | Robber's Lane, Maugheraboy, Sligo | 38 | *N/A |  |  |  |  | Q2-2024
1549 | SHIP CONSTRUCTION | Sligo | Pirn Mill Road, Town Centre , Sligo | 20 | *N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
1550 | SHIP CONSTRUCTION | Sligo | 39 High Street, Sligo | 5 | *N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
1551 | SHIP CONSTRUCTION | Sligo | Connolly Park, Tubbercurry (Phase 2) & The Green Rd., Collaney | 15 | *N/A | [5 empty] | Q3-2024
1552 | SHIP CONSTRUCTION | Sligo | Southern Place, Knappagh Road, Sligo | 4 | N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
1553 | SHIP Accel MMC | Sligo | Dromore West | 18 | N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
1554 | SHIP Accel MMC | Sligo | Easkey | 8 | N/A | Stage 1 approved Q2-2023, outline design and costs being prepared.
1555 | SHIP Accel MMC | Sligo | Owenmore Crescent, Collooney | 30 | N/A | Stage 1 approved Q2-2023, outline design and costs being prepared.
1556 | SHIP Accel MMC | Sligo | Grange | 16 | N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
1557 | SHIP Accel MMC | Sligo | Carney | 25 | N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
1558 | SHIP Accel MMC | Sligo | Finisklin, Phase 1 | 47 | N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
1559 | SHIP Accel MMC | Sligo | Cairnsfoot Field (Brown's Field) | 60 | N/A | Stage 1 approved Q2-2023, outline design and costs being prepared.
1560 | SHIP Accel MMC | Sligo | Camross, Ballymote, Sligo | 39 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1561 | SHIP Accel MMC | Sligo | Finisklin, Phase 2 | 40 | N/A | Stage 1 approved Q2-2023, outline design and costs being prepared.
1562 | CAS CONSTRUCTION TURNKEY | Sligo | Avena, Ballisodare, Co Sligo | 6 | Túath Housing Association Ltd | [5 empty] | Q1-2022
1563 | CAS CONSTRUCTION TURNKEY | Sligo | Seaville (Ursuline), Finisklin Road (Group Home) | 10 | Sophia Housing Association Ltd |  |  |  |  | Q4-2022
1564 | CAS CONSTRUCTION | Sligo | Killeshin, First Sea Road, Sligo | 5 | Newgrove Housing Association Ltd | [5 empty] | Q3-2023
1565 | CAS CONSTRUCTION | Sligo | Summerhill, Tubbercurry, Co Sligo | 10 | Sophia Housing Association Ltd | Stage 1 approved Q2-2022, outline design and costs being prepared.
1566 | CAS CONSTRUCTION | Sligo | Kazelain House, 3 Lyons Terrace, Finisklin Road, Sligo | 12 | HAIL | Stage 1 approved Q3-2023, outline design and costs being prepared.
1567 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 16 | *N/A | [5 empty] | Q3-2022
1568 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 20 | *N/A | [5 empty] | Q3-2022
1569 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 11 | *N/A | [5 empty] | Q4-2022
1570 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 10 | *N/A | [5 empty] | Q4-2022
1571 | SHIP DIALOG | South Dublin | Clonburris 1 | 60 | *N/A |  | Stage 2 approved Q1-2023, full design/tender being prepared.
1572 | SHIP DIALOG | South Dublin | Clonburris 2 (Canal Bank) | 56 | *N/A |  |  |  |  | Q4-2023
1573 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 6 | *N/A | [5 empty] | Q4-2022
1574 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 15 | *N/A | [5 empty] | Q4-2022
1575 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 2 | *N/A | [5 empty] | Q1-2023
1576 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 18 | *N/A | [5 empty] | Q2-2023
1577 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 16 | *N/A | [5 empty] | Q2-2023
1578 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 16 | *N/A | [5 empty] | Q2-2023
1579 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 22 | *N/A | [5 empty] | Q4-2023
1580 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 6 | *N/A | [5 empty] | Q4-2023
1581 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 6 | *N/A | [5 empty] | Q4-2023
1582 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 17 | *N/A | [5 empty] | Q4-2023
1583 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 23 | *N/A | [5 empty] | Q3-2024
1584 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 10 | *N/A |  |  |  |  | Q2-2021
1585 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 6 | *N/A | [5 empty] | Q2-2024
1586 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 10 | *N/A | [5 empty] | Q2-2024
1587 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 11 | *N/A | [5 empty] | Q2-2024
1588 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 13 | *N/A |  |  |  |  | Q2-2021
1589 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 18 | *N/A |  |  |  |  | Q2-2021
1590 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 11 | *N/A |  |  |  |  | Q2-2021
1591 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 10 | *N/A |  |  |  |  | Q2-2021
1592 | SHIP DIALOG | South Dublin | Kilcarbery JV Social | 16 | *N/A |  |  |  |  | Q2-2021
1593 | SHIP DIALOG | South Dublin | Clonburris 1 | 33 | *N/A |  | Stage 2 approved Q1-2023, full design/tender being prepared.
1594 | SHIP CONSTRUCTION TURNKEY | South Dublin | Cloragh Mills, Edmonstown Road, Rathfarnham, Dublin 16 | 8 | *N/A | [5 empty] | Q4-2022
1595 | SHIP CONSTRUCTION TURNKEY | South Dublin | Shackleton Street, Adamstow | 4 | *N/A | [5 empty] | Q2-2023
1596 | SHIP CONSTRUCTION TURNKEY | South Dublin | Tandy's Lane | 3 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1597 | SHIP CONSTRUCTION SINGLE STAGE | South Dublin | 37 Greenfort Gardens, Clondalkin | 2 | *N/A | [5 empty] | Q4-2021
1598 | SHIP CONSTRUCTION SINGLE STAGE | South Dublin | Brady's Court, Old Bawn, Tallaght | 12 | *N/A | [5 empty] | Q4-2023
1599 | SHIP CONSTRUCTION SINGLE STAGE | South Dublin | Pearse Brothers Park, Rathfarnham | 10 | *N/A |  |  |  | Stage 4 approved Q4-2022, the scheme is fully approved.
1600 | SHIP CONSTRUCTION SINGLE STAGE | South Dublin | St Aongus Green, Tallaght, Dublin 24 | 12 | *N/A |  |  |  | Stage 4 approved Q4-2022, the scheme is fully approved.
1601 | SHIP CONSTRUCTION SINGLE STAGE | South Dublin | St Ronan's Crescent, Clondalkin | 9 | *N/A |  |  |  | Stage 4 approved Q4-2022, the scheme is fully approved.
1602 | SHIP CONSTRUCTION SINGLE STAGE | South Dublin | Sarsfield Park, Lucan, Co. Dublin | 5 | N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
1603 | SHIP CONSTRUCTION DESIGN BUILD | South Dublin | St. Marks Avenue, Clondalkin | 38 | *N/A | [5 empty] | Q4-2022
1604 | SHIP CONSTRUCTION DESIGN BUILD | South Dublin | Balgaddy F, Griffeen Avenue, Lucan | 49 | *N/A |  |  |  |  | Q1-2023
1605 | SHIP CONSTRUCTION DESIGN BUILD | South Dublin | Riversdale, Clondalkin, Dublin 22 | 25 | *N/A | [5 empty] | Q4-2022
1606 | SHIP CONSTRUCTION DESIGN BUILD | South Dublin | Riverside Cottages, Templeogue | 10 | *N/A | [5 empty] | Q4-2022
1607 | SHIP CONSTRUCTION DESIGN BUILD | South Dublin | Riversdale, Clondalkin, Dublin 22 | 18 | *N/A | [5 empty] | Q4-2023
1608 | SHIP CONSTRUCTION DESIGN BUILD | South Dublin | Grand Canal, Lindisfarne, Clondalkin, | 19 | *N/A |  |  |  |  | Q4-2022
1609 | SHIP CONSTRUCTION DESIGN BUILD | South Dublin | Deansrath/Melrose, Deansrath Green, Clondalkin, Dublin 22 | 27 | N/A |  |  |  |  | Q3-2023
1610 | SHIP CONSTRUCTION DESIGN BUILD | South Dublin | Balgaddy | 20 | *N/A | [5 empty] | Q4-2023
1611 | SHIP CONSTRUCTION | South Dublin | St. Catherine’s, Knockmore Avenue, Killinarden, Tallaght | 12 | *N/A | [5 empty] | Q4-2022
1612 | SHIP CONSTRUCTION | South Dublin | Homeville, Knocklyon, Dublin 16 | 16 | *N/A |  |  |  |  | Q4-2020
1613 | SHIP CONSTRUCTION | South Dublin | Nangor Road, Clondalkin, Dublin 22 | 33 | *N/A | [5 empty] | Q4-2023
1614 | SHIP CONSTRUCTION | South Dublin | Rossfield | 15 | *N/A | Stage 1 approved Q3-2023, outline design and costs being prepared.
1615 | SHIP CONSTRUCTION | South Dublin | Nangor Road, Clondalkin | 30 | *N/A |  |  |  |  | Q2-2022
1616 | SHIP CONSTRUCTION | South Dublin | Nangor Road, Clondalkin | 30 | *N/A |  |  |  |  | Q2-2022
1617 | CAS CONSTRUCTION TURNKEY | South Dublin | Oakridge, Ballynakelly,Edge, Newcastle, Co. Dublin | 3 | Túath Housing Association Ltd | [5 empty] | Q2-2022
1618 | CAS CONSTRUCTION TURNKEY | South Dublin | 3 Cornerpark Rise | 1 | Arlington Novas Ireland Ltd | [5 empty] | Q4-2021
1619 | SHIP CONSTRUCTION TURNKEY | Tipperary | Prior Park, Clonmel | 6 | *N/A | [5 empty] | Q4-2022
1620 | SHIP CONSTRUCTION TURNKEY | Tipperary | Ma Chaoin, Manna South, Templemore | 3 | *N/A | [5 empty] | Q4-2022
1621 | SHIP CONSTRUCTION TURNKEY | Tipperary | Prior Park, Clonmel | 6 | *N/A |  |  |  |  | Q1-2020
1622 | SHIP CONSTRUCTION TURNKEY | Tipperary | Glenconnor Road, Clonmel | 10 | *N/A | [5 empty] | Q4-2022
1623 | SHIP CONSTRUCTION TURNKEY | Tipperary | Hazel Close, Carrick on Suir | 14 | *N/A | [5 empty] | Q4-2021
1624 | SHIP CONSTRUCTION TURNKEY | Tipperary | Lar Whelan, Glenconnor Road, Clonmel (Oakwood Close) | 1 | *N/A |  |  |  |  | Q3-2023
1625 | SHIP CONSTRUCTION TURNKEY | Tipperary | Cois Abhainn, Mullinahone | 3 | *N/A | [5 empty] | Q4-2021
1626 | SHIP CONSTRUCTION TURNKEY | Tipperary | Glentara, Roscrea | 2 | *N/A | [5 empty] | Q4-2021
1627 | SHIP CONSTRUCTION TURNKEY | Tipperary | Glenconnor Road, Clonmel | 11 | *N/A | [5 empty] | Q4-2022
1628 | SHIP CONSTRUCTION TURNKEY | Tipperary | Carrick Beg, Carrick on Suir | 9 | *N/A | [5 empty] | Q4-2023
1629 | SHIP CONSTRUCTION TURNKEY | Tipperary | Glenconnor Road, Clonmel | 2 | *N/A | [5 empty] | Q4-2022
1630 | SHIP CONSTRUCTION TURNKEY | Tipperary | The Creamery, Clogheen Road, Ardfinnan | 13 | *N/A | [5 empty] | Q4-2023
1631 | SHIP CONSTRUCTION TURNKEY | Tipperary | Ard na Sidhe, Clonmel | 4 | *N/A | [5 empty] | Q4-2022
1632 | SHIP CONSTRUCTION TURNKEY | Tipperary | Springfort Meadows, Nenagh | 5 | *N/A |  |  |  |  | Q3-2023
1633 | SHIP CONSTRUCTION TURNKEY | Tipperary | Kilsheelan, Clonmel | 2 | *N/A | [5 empty] | Q3-2022
1634 | SHIP CONSTRUCTION TURNKEY | Tipperary | Stradavoher Road, Thurles | 29 | *N/A |  |  |  | Stage 4 approved Q3-2022, the scheme is fully approved.
1635 | SHIP CONSTRUCTION TURNKEY | Tipperary | Kilsheelan, Clonmel | 1 | *N/A | [5 empty] | Q4-2022
1636 | SHIP CONSTRUCTION TURNKEY | Tipperary | An Grianan, Killenaule | 4 | N/A | [5 empty] | Q4-2022
1637 | SHIP CONSTRUCTION TURNKEY | Tipperary | Glencree, Newport | 8 | N/A | [5 empty] | Q4-2023
1638 | SHIP CONSTRUCTION TURNKEY | Tipperary | Wheatfields, Glenconnor, Clonmel (Garden Close) | 24 | N/A | [5 empty] | Q3-2024
1639 | SHIP CONSTRUCTION TURNKEY | Tipperary | Thomas Street, Clonmel | 21 | N/A |  |  |  |  | Q3-2024
1640 | SHIP CONSTRUCTION TURNKEY | Tipperary | Prior Park, Clonmel | 29 | *N/A |  |  |  |  | Q1-2020
1641 | SHIP CONSTRUCTION TURNKEY | Tipperary | Ma Chaoin, Manna South, Templemore | 3 | *N/A |  |  |  |  | Q1-2023
1642 | SHIP CONSTRUCTION TURNKEY | Tipperary | Ard na Sidhe, Clonmel | 5 | *N/A | [5 empty] | Q2-2023
1643 | SHIP CONSTRUCTION TURNKEY | Tipperary | Dun Uisce, Cahir | 8 | N/A | [5 empty] | Q4-2022
1644 | SHIP CONSTRUCTION TURNKEY | Tipperary | Seanline, Fethard | 14 | N/A | [5 empty] | Q4-2023
1645 | SHIP CONSTRUCTION TURNKEY | Tipperary | Carrick Beg, (Boherbue Close) Waterford Road,Carrick on Suir, | 11 | N/A | [5 empty] | Q3-2024
1646 | SHIP CONSTRUCTION TURNKEY | Tipperary | 5 UNITS AT AN GRIANAN, KILLENAULE, THURLES, TIPPERARY | 5 | *N/A | [5 empty] | Q4-2023
1647 | SHIP CONSTRUCTION TURNKEY | Tipperary | Ma Chaoin, Manna South, Templemore | 1 | *N/A | [5 empty] | Q4-2023
1648 | SHIP CONSTRUCTION TURNKEY | Tipperary | Wheatfields, Glenconnor, Clonmel (Garden Close) | 10 | *N/A | [5 empty] | Q3-2024
1649 | SHIP CONSTRUCTION TURNKEY | Tipperary | CHURCH STREET, (D.BRITT),TEMPLEMORE, TIPPERARY | 4 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1650 | SHIP CONSTRUCTION TURNKEY | Tipperary | Ivowen, Kilsheelan, Tipperary | 8 | N/A |  |  |  |  | Q2-2023
1651 | SHIP CONSTRUCTION TURNKEY | Tipperary | Ivowen, Kilsheelan, Tipperary | 12 | *N/A |  |  |  |  | Q2-2023
1652 | SHIP CONSTRUCTION TURNKEY | Tipperary | Drangan, Tipperary | 7 | N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1653 | SHIP CONSTRUCTION TURNKEY | Tipperary | Ma Chaoin, Manna South, Templemore | 1 | N/A | [5 empty] | Q3-2024
1654 | SHIP CONSTRUCTION TURNKEY | Tipperary | Ma Chaoin, Manna South, Templemore | 5 | N/A |  |  |  |  | Q1-2023
1655 | SHIP CONSTRUCTION TURNKEY | Tipperary | Lar Whelan, Glenconnor Rd, Clonmel (Oakwood Close) | 1 | N/A |  |  |  |  | Q3-2023
1656 | SHIP CONSTRUCTION TURNKEY | Tipperary | Springfort Meadows, Nenagh | 9 | N/A |  |  |  | Stage 4 approved Q2-2022, the scheme is fully approved.
1657 | SHIP CONSTRUCTION TURNKEY | Tipperary | Thomas Street, Clonmel | 34 | N/A |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
1658 | SHIP CONSTRUCTION TURNKEY | Tipperary | Springfort Meadows, Nenagh, Tipperary | 3 | *N/A |  |  |  |  | Q3-2023
1659 | SHIP CONSTRUCTION TURNKEY | Tipperary | Dun Uisce, Cahir, Tipperary | 1 | *N/A |  |  |  |  | Q2-2024
1660 | SHIP CONSTRUCTION RENEWAL | Tipperary | Ard na Greine, Clonmel | 2 | *N/A | [5 empty] | Q4-2022
1661 | SHIP CONSTRUCTION RENEWAL | Tipperary | 15 St Cronins, Roscrea | 1 | N/A | [5 empty] | Q3-2023
1662 | SHIP CONSTRUCTION RENEWAL | Tipperary | 57 Kennedy Park, Roscrea | 1 | *N/A | [5 empty] | Q3-2023
1663 | SHIP CONSTRUCTION RENEWAL | Tipperary | 3 St Mary's Avenue, Thurles | 1 | N/A | [5 empty] | Q3-2023
1664 | SHIP CONSTRUCTION RENEWAL | Tipperary | 9 McDonagh Terrace, Littleton, Tipperary | 1 | N/A | [5 empty] | Q4-2023
1665 | SHIP CONSTRUCTION RENEWAL | Tipperary | 37 Pearse Park, Tipperary Town, Tipperary | 1 | N/A | [5 empty] | Q4-2023
1666 | SHIP CONSTRUCTION RENEWAL | Tipperary | 52 Irishtown, Clonmel | 1 | N/A | [5 empty] | Q1-2024
1667 | SHIP CONSTRUCTION RENEWAL | Tipperary | 11 & 12 Church Avenue, Templemore, Tipperary | 2 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1668 | SHIP CONSTRUCTION | Tipperary | Knockanrawley | 14 | *N/A | [5 empty] | Q1-2021
1669 | SHIP CONSTRUCTION | Tipperary | Mill Road, Thurles | 14 | *N/A | [5 empty] | Q4-2021
1670 | SHIP CONSTRUCTION | Tipperary | Mulkear View, Newport | 10 | *N/A | [5 empty] | Q4-2021
1671 | SHIP CONSTRUCTION | Tipperary | Templetouhy | 10 | *N/A | [5 empty] | Q4-2021
1672 | SHIP CONSTRUCTION | Tipperary | Abbey Street, Cahir | 10 | *N/A | [5 empty] | Q4-2022
1673 | SHIP CONSTRUCTION | Tipperary | Borrisokane | 14 | *N/A | [5 empty] | Q4-2021
1674 | SHIP CONSTRUCTION | Tipperary | Portroe, Nenagh | 14 | *N/A | [5 empty] | Q4-2023
1675 | SHIP CONSTRUCTION | Tipperary | Cloughjordan | 2 | *N/A | [5 empty] | Q2-2021
1676 | SHIP CONSTRUCTION | Tipperary | Mitchel St., Thurles | 1 | *N/A | [5 empty] | Q4-2021
1677 | SHIP CONSTRUCTION | Tipperary | Cormack Drive, Nenagh | 12 | *N/A | [5 empty] | Q3-2022
1678 | SHIP CONSTRUCTION | Tipperary | Bansha | 14 | *N/A | [5 empty] | Q2-2023
1679 | SHIP CONSTRUCTION | Tipperary | Ned Hayes Drive, Twomileborris, Thurles | 22 | *N/A | [5 empty] | Q4-2022
1680 | SHIP CONSTRUCTION | Tipperary | Donohill | 8 | *N/A | [5 empty] | Q4-2023
1681 | SHIP CONSTRUCTION | Tipperary | Killaghy Crescent, Mullinahone, Tipperary | 10 | *N/A | [5 empty] | Q4-2022
1682 | SHIP CONSTRUCTION | Tipperary | Ballyclerihan | 14 | *N/A | [5 empty] | Q4-2023
1683 | SHIP CONSTRUCTION | Tipperary | Ard Alainn, Moyne | 9 | *N/A | [5 empty] | Q3-2023
1684 | SHIP CONSTRUCTION | Tipperary | Ardcroney | 4 | *N/A | [5 empty] | Q4-2022
1685 | SHIP CONSTRUCTION | Tipperary | Church Street, Templemore | 2 | *N/A |  |  |  |  | Q3-2023
1686 | SHIP CONSTRUCTION | Tipperary | Woodview Close, Castle Crescent, Nenagh | 10 | *N/A | [5 empty] | Q4-2023
1687 | SHIP CONSTRUCTION | Tipperary | Boherclough Street, Cashel | 9 | *N/A | [5 empty] | Q4-2023
1688 | SHIP CONSTRUCTION | Tipperary | Grove Street. Roscrea | 9 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1689 | SHIP CONSTRUCTION | Tipperary | Glencarrick, Roscrea | 27 | *N/A |  |  | Stage 3 approved Q4-2023, the scheme is now approved to proceed to tender.
1690 | SHIP CONSTRUCTION | Tipperary | Knockanrawley | 14 | *N/A | [5 empty] | Q2-2021
1691 | SHIP CONSTRUCTION | Tipperary | Mill Road, Thurles | 14 | *N/A | [5 empty] | Q2-2022
1692 | SHIP CONSTRUCTION | Tipperary | Mulkear View, Newport | 1 | *N/A | [5 empty] | Q1-2022
1693 | SHIP CONSTRUCTION | Tipperary | Mountain View, Cahir | 20 | *N/A |  |  | Stage 3 approved Q4-2023, the scheme is now approved to proceed to tender.
1694 | SHIP CONSTRUCTION | Tipperary | Glencarrick, Roscrea | 20 | *N/A |  |  | Stage 3 approved Q4-2023, the scheme is now approved to proceed to tender.
1695 | SHIP CONSTRUCTION | Tipperary | William Street, Nenagh | 7 | *N/A |  | Stage 2 approved Q2-2022, full design/tender being prepared.
1696 | SHIP CONSTRUCTION | Tipperary | Borrisokane | 1 | *N/A | [5 empty] | Q1-2022
1697 | SHIP CONSTRUCTION | Tipperary | Ashbury, Roscrea | 10 | *N/A |  | Stage 2 approved Q4-2022, full design/tender being prepared.
1698 | SHIP CONSTRUCTION | Tipperary | Fr. Matthew Street, Tipperary Town | 4 | *N/A |  | Stage 2 approved Q2-2023, full design/tender being prepared.
1699 | SHIP CONSTRUCTION | Tipperary | Puckane, Nenagh | 21 | *N/A | Stage 1 approved Q4-2022, outline design and costs being prepared.
1700 | SHIP CONSTRUCTION | Tipperary | Mountain View, Cahir | 25 | N/A |  |  | Stage 3 approved Q4-2023, the scheme is now approved to proceed to tender.
1701 | SHIP CONSTRUCTION | Tipperary | Killenaule Road, Ballingarry | 10 | N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
1702 | SHIP CONSTRUCTION | Tipperary | Old Rialto Cinema Emmet Place | 12 | N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
1703 | SHIP CONSTRUCTION | Tipperary | Gortlandroe Road, Nenagh | 27 | N/A | Stage 1 approved Q2-2023, outline design and costs being prepared.
1704 | SHIP CONSTRUCTION | Tipperary | Gantly Road, Roscrea | 17 | N/A |  | Stage 2 approved Q3-2024, full design/tender being prepared.
1705 | SHIP CONSTRUCTION | Tipperary | Clashapoocha, Clogheen | 14 | N/A |  | Stage 2 approved Q2-2023, full design/tender being prepared.
1706 | SHIP CONSTRUCTION | Tipperary | 6 UNITS AT RATHCABBIN, CO. TIPPERARY | 6 | N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
1707 | SHIP CONSTRUCTION | Tipperary | NEW LINE ROAD, NENAGH, TIPPERARY | 14 | *N/A | Stage 1 approved Q3-2023, outline design and costs being prepared.
1708 | SHIP CONSTRUCTION | Tipperary | MILLARSBROOK, NENAGH, CO. TIPPERARY | 13 | *N/A | Stage 1 approved Q3-2023, outline design and costs being prepared.
1709 | SHIP CONSTRUCTION | Tipperary | MULCAIR MANOR, NEWPORT, CO. TIPPERARY | 13 | *N/A | Stage 1 approved Q4-2023, outline design and costs being prepared.
1710 | CAS CONSTRUCTION TURNKEY | Tipperary | Kickham Street, Carrick en Suir | 12 | Túath Housing Association Ltd | [5 empty] | Q4-2022
1711 | CAS CONSTRUCTION TURNKEY | Tipperary | The Glove Factory | 6 | Focus Ireland |  |  |  |  | Q2-2024
1712 | CAS CONSTRUCTION SINGLE STAGE | Tipperary | Deerpark Road, Ashwell's Lot | 2 | SPADE – St. Patrick’s Dwellings for the Elderly | [5 empty] | Q2-2022
1713 | CAS CONSTRUCTION RENEWAL | Tipperary | 1 and 1A Limerick Road | 2 | Thurles Lions Trust Housing Assoc. |  | Stage 2 approved Q1-2024, full design/tender being prepared.
1714 | CAS CONSTRUCTION RENEWAL | Tipperary | Irish House, 63/64 Main Street Tipperary Town | 6 | Focus Ireland | [5 empty] | Q4-2023
1715 | CAS CONSTRUCTION RENEWAL | Tipperary | Templemore Road, Roscrea, Tipperary | 2 | Marillac Housing Association |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1716 | CAS CONSTRUCTION | Tipperary | Glenconnor Road, Clonmel | 9 | Cluid Housing Association | [5 empty] | Q4-2022
1717 | CAS CONSTRUCTION | Tipperary | Stanwix House, Kickham Street, Thurles | 19 | Thurles Lions Trust Housing Assoc. | [5 empty] | Q4-2022
1718 | CAS CONSTRUCTION | Tipperary | Main Street, Templemore | 22 | Templemore Voluntary Housing Association |  | Stage 2 approved Q2-2022, full design/tender being prepared.
1719 | CAS CONSTRUCTION | Tipperary | Presentation Convent, Fethard | 14 | Fethard | Stage 1 approved Q4-2023, outline design and costs being prepared.
1720 | CAS CONSTRUCTION | Tipperary | Gort an Oir, Fethard | 7 | Belmont Park Housing Association Ltd |  | Stage 2 approved Q1-2024, full design/tender being prepared.
1721 | CAS CONSTRUCTION | Tipperary | An Clos, Croke Street, Thurles, Co. Tipperary | 6 | Thurles Lions Trust Housing Assoc. |  | Stage 2 approved Q3-2024, full design/tender being prepared.
1722 | CAS CONSTRUCTION | Tipperary | Morton Street, Clonmel, Tipperary | 6 | N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
1723 | SHIP CONSTRUCTION TURNKEY | Waterford | Mount William, Williamstown, Waterford City | 13 | *N/A | [5 empty] | Q1-2021
1724 | SHIP CONSTRUCTION TURNKEY | Waterford | Mount William, Williamstown, Waterford City | 10 | *N/A | [5 empty] | Q2-2021
1725 | SHIP CONSTRUCTION TURNKEY | Waterford | Mount William, Williamstown, Waterford City | 23 | *N/A | [5 empty] | Q2-2021
1726 | SHIP CONSTRUCTION TURNKEY | Waterford | The Courtyard, Morrissons Road, Waterford City | 8 | *N/A | [5 empty] | Q2-2021
1727 | SHIP CONSTRUCTION TURNKEY | Waterford | Bounds Court, Airport Road, Waterford | 15 | N/A | [5 empty] | Q1-2022
1728 | SHIP CONSTRUCTION TURNKEY | Waterford | Brideview Close, Tallow; Main St., Aglish; Bye Lane, Kilmacthomas | 6 | N/A | [5 empty] | Q4-2021
1729 | SHIP CONSTRUCTION TURNKEY | Waterford | Ormonde House, Dungarvan, Co Waterford | 19 | *N/A | [5 empty] | Q4-2023
1730 | SHIP CONSTRUCTION TURNKEY | Waterford | Brideview Close, Tallow; Main St., Aglish; Bye Lane, Kilmacthomas | 3 | *N/A | [5 empty] | Q3-2022
1731 | SHIP CONSTRUCTION TURNKEY | Waterford | Radharc na Siuire, Knockboy | 3 | *N/A | [5 empty] | Q1-2022
1732 | SHIP CONSTRUCTION TURNKEY | Waterford | Radharc na Siuire, Knockboy | 4 | *N/A | [5 empty] | Q4-2022
1733 | SHIP CONSTRUCTION TURNKEY | Waterford | Bounds Court, Airport Road, Waterford | 2 | *N/A | [5 empty] | Q4-2022
1734 | SHIP CONSTRUCTION TURNKEY | Waterford | 22-23 Mary Street, Dungarvan | 7 | *N/A | [5 empty] | Q4-2023
1735 | SHIP CONSTRUCTION TURNKEY | Waterford | Cuil na Circle, Cappoquin, Waterford | 7 | N/A | [5 empty] | Q4-2023
1736 | SHIP CONSTRUCTION TURNKEY | Waterford | Ormond Rise and Ormond Drive, Waterford City | 8 | *N/A | [5 empty] | Q2-2024
1737 | SHIP CONSTRUCTION TURNKEY | Waterford | 24 The Mills, | 1 | N/A | [5 empty] | Q4-2023
1738 | SHIP CONSTRUCTION SINGLE STAGE | Waterford | 22 and 23 Thomas Hill, Waterford | 3 | *N/A |  |  |  |  | Q4-2023
1739 | SHIP CONSTRUCTION RENEWAL | Waterford | Apt 1 and Apt 2 Rivercourt, Grattan Quay, Waterford City | 2 | *N/A |  |  |  |  | Q1-2024
1740 | SHIP CONSTRUCTION RENEWAL | Waterford | Meeting House Lane, Waterford City | 6 | N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
1741 | SHIP CONSTRUCTION RENEWAL | Waterford | 29 The Glen, Waterford City | 4 | *N/A |  |  |  |  | Q1-2024
1742 | SHIP CONSTRUCTION RENEWAL | Waterford | Apts 1-6, The Old Convent and Rossmore, Kilmacthomas | 12 | *N/A |  |  | Stage 3 approved Q2-2024, the scheme is now approved to proceed to tender.
1743 | SHIP CONSTRUCTION RENEWAL | Waterford | 70 & 71 O'Connell Street, Waterford | 5 | *N/A |  | Stage 2 approved Q3-2023, full design/tender being prepared.
1744 | SHIP CONSTRUCTION RENEWAL | Waterford | 29-30 Manor Street, Waterford | 4 | *N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
1745 | SHIP CONSTRUCTION RENEWAL | Waterford | Tower Lodge, Ballytruckle, Waterford | 2 | *N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
1746 | SHIP CONSTRUCTION RENEWAL | Waterford | 60 Poleberry, Waterford City | 1 | *N/A | [5 empty] | Q4-2023
1747 | SHIP CONSTRUCTION RENEWAL | Waterford | 17 Shortcourse Court, Waterford | 1 | *N/A | [5 empty] | Q4-2023
1748 | SHIP CONSTRUCTION RENEWAL | Waterford | 21 Hillview, Kilmacthomas | 1 | *N/A | [5 empty] | Q4-2023
1749 | SHIP CONSTRUCTION RENEWAL | Waterford | 6-9 Anne Street, Waterford | 8 | N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
1750 | SHIP CONSTRUCTION RENEWAL | Waterford | 1 Newgate Street, Waterford | 1 | N/A | [5 empty] | Q4-2023
1751 | SHIP CONSTRUCTION RENEWAL | Waterford | 36 Mayors Walk | 2 | N/A | [5 empty] | Q4-2023
1752 | SHIP CONSTRUCTION RENEWAL | Waterford | 5/6 Great Georges Street, Waterford | 7 | N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
1753 | SHIP CONSTRUCTION RENEWAL | Waterford | 3 Railway Square, Waterford | 1 | N/A | [5 empty] | Q3-2024
1754 | SHIP CONSTRUCTION RENEWAL | Waterford | 5 Henry St., Waterford | 1 | *N/A | [5 empty] | Q3-2024
1755 | SHIP CONSTRUCTION RENEWAL | Waterford | Ballygambon Lower, Ballinameela, Dungarvan, Co. Waterford | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1756 | SHIP CONSTRUCTION RENEWAL | Waterford | Morrisons Avenue, Waterford | 1 | N/A | [5 empty] | Q3-2024
1757 | SHIP CONSTRUCTION RENEWAL | Waterford | 4 Slievekeale Road, Waterford | 1 | N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1758 | SHIP CONSTRUCTION RENEWAL | Waterford | 294 St. John’s Park, Waterford | 1 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1759 | SHIP CONSTRUCTION DESIGN BUILD | Waterford | Ballygunner, Waterford City | 37 | *N/A | [5 empty] | Q4-2023
1760 | SHIP CONSTRUCTION DESIGN BUILD | Waterford | Ballygunner, Waterford City | 12 | *N/A |  |  |  |  | Q3-2022
1761 | SHIP CONSTRUCTION | Waterford | An Garrán, Crobally Upper, Tramore | 35 | *N/A |  |  |  |  | Q2-2023
1762 | SHIP CONSTRUCTION | Waterford | Larchville, Waterford City | 5 | *N/A | [5 empty] | Q2-2021
1763 | SHIP CONSTRUCTION | Waterford | Doyles Street, Waterford City | 4 | *N/A | [5 empty] | Q4-2021
1764 | SHIP CONSTRUCTION | Waterford | The Glen, Bridge St, Waterford | 17 | *N/A |  | Stage 2 approved Q3-2018, full design/tender being prepared.
1765 | SHIP CONSTRUCTION | Waterford | Summerland Square, Waterford | 12 | *N/A |  |  | Stage 3 approved Q1-2019, the scheme is now approved to proceed to tender.
1766 | SHIP CONSTRUCTION | Waterford | Graigueshoneen, Kilmacthomas | 16 | *N/A | [5 empty] | Q1-2022
1767 | SHIP CONSTRUCTION | Waterford | Mount Esker, Ballytruckle Road, Waterford City | 14 | *N/A | [5 empty] | Q4-2022
1768 | SHIP CONSTRUCTION | Waterford | Newgate Street, Waterford City | 27 | *N/A |  | Stage 2 approved Q1-2023, full design/tender being prepared.
1769 | SHIP CONSTRUCTION | Waterford | Fountain Street, Ferrybank, Waterford | 14 | *N/A | [5 empty] | Q3-2024
1770 | SHIP CONSTRUCTION | Waterford | 50-53 Ballytruckle Road, Waterford | 10 | *N/A |  |  |  |  | Q1-2024
1771 | SHIP CONSTRUCTION | Waterford | St. Mary's Terrace, Hennessy's Road, Waterford | 6 | *N/A |  | Stage 2 approved Q4-2023, full design/tender being prepared.
1772 | SHIP CONSTRUCTION | Waterford | The Old Coalyard, St Patricks Terrace, Waterford City | 9 | *N/A |  | Stage 2 approved Q3-2023, full design/tender being prepared.
1773 | SHIP CONSTRUCTION | Waterford | Old Parish, Knockanroe, Co. Waterford | 6 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
1774 | SHIP CONSTRUCTION | Waterford | Tobar Ciuin, Ardmore, Co. Waterford | 20 | *N/A |  | Stage 2 approved Q1-2024, full design/tender being prepared.
1775 | SHIP CONSTRUCTION | Waterford | Fairlane, Dungarvan | 50 | *N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
1776 | SHIP CONSTRUCTION | Waterford | Bilberry, Waterford | 80 | N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
1777 | SHIP CONSTRUCTION | Waterford | Vine Square, Lower Yellow Road, Waterford | 18 | N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
1778 | SHIP CONSTRUCTION | Waterford | De La Salle, 25 Patrick Street | 10 | N/A | Stage 1 approved Q3-2024, outline design and costs being prepared.
1779 | SHIP CONSTRUCTION | Waterford | An Garrán, Corbally Upper, Tramore | 15 | N/A |  |  |  |  | Q2-2023
1780 | SHIP Accel MMC | Waterford | Shandon, Dungarvan | 38 | N/A |  |  | Stage 3 approved Q1-2024, the scheme is now approved to proceed to tender.
1781 | CAS CONSTRUCTION TURNKEY | Waterford | Doyle Street, Waterford | 1 | Tintean Housing Association Ltd | [5 empty] | Q3-2023
1782 | CAS CONSTRUCTION TURNKEY | Waterford | 15 Grange Terrace, Ballytruckle, Waterford | 1 | Tintean Housing Association Ltd | [5 empty] | Q2-2024
1783 | CAS CONSTRUCTION RENEWAL | Waterford | Wadding Manor, Ferrybank | 10 | Respond | [5 empty] | Q2-2021
1784 | CAS CONSTRUCTION RENEWAL | Waterford | 21 Bridge Street, Waterford City | 4 | Society of Saint Vincent de Paul |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
1785 | CAS CONSTRUCTION RENEWAL | Waterford | 33 Green Street, Waterford | 1 | Tintean Housing Association Ltd | [5 empty] | Q3-2024
1786 | CAS CONSTRUCTION | Waterford | Cluain Cairbre, Ballymacarbry | 3 | BEHAL | Stage 1 approved Q1-2024, outline design and costs being prepared.
1787 | SHIP DIALOG | Westmeath | Lissywollen, Athlone | 55 | *N/A |  |  |  | Stage 4 approved Q3-2020, the scheme is fully approved.
1788 | SHIP DIALOG | Westmeath | Lissywollen, Athlone | 55 | *N/A |  |  |  | Stage 4 approved Q3-2020, the scheme is fully approved.
1789 | SHIP DIALOG | Westmeath | Lissywollen, Athlone | 38 | *N/A |  |  |  | Stage 4 approved Q3-2020, the scheme is fully approved.
1790 | SHIP DIALOG | Westmeath | Lissywollen, Athlone | 22 | *N/A |  |  |  | Stage 4 approved Q3-2020, the scheme is fully approved.
1791 | SHIP CONSTRUCTION TURNKEY | Westmeath | Barrack Court, Bellview Road, Austin Friar Street, Mullingar | 4 | *N/A | [5 empty] | Q4-2022
1792 | SHIP CONSTRUCTION TURNKEY | Westmeath | Oakcrest, Ballinderry, Mullingar | 5 | *N/A | [5 empty] | Q4-2022
1793 | SHIP CONSTRUCTION TURNKEY | Westmeath | St. Marys Place, Athlone | 9 | *N/A |  |  |  |  | Q2-2021
1794 | SHIP CONSTRUCTION TURNKEY | Westmeath | Rathgarve Green, Castlepollard | 1 | *N/A | [5 empty] | Q2-2021
1795 | SHIP CONSTRUCTION TURNKEY | Westmeath | Bellaugh, Athlone | 17 | *N/A | [5 empty] | Q4-2022
1796 | SHIP CONSTRUCTION TURNKEY | Westmeath | The Cedars, Lakepoint, Mullingar | 7 | *N/A | [5 empty] | Q2-2022
1797 | SHIP CONSTRUCTION TURNKEY | Westmeath | The Cedars, Lakepoint, Mullingar | 17 | *N/A | [5 empty] | Q4-2022
1798 | SHIP CONSTRUCTION TURNKEY | Westmeath | The Cedars, Lakepoint, Mullingar | 4 | *N/A | [5 empty] | Q4-2022
1799 | SHIP CONSTRUCTION TURNKEY | Westmeath | Austin Friar Street, Mullingar | 2 | *N/A | [5 empty] | Q4-2022
1800 | SHIP CONSTRUCTION TURNKEY | Westmeath | Athboy Rd, Delvin | 6 | *N/A | [5 empty] | Q4-2023
1801 | SHIP CONSTRUCTION TURNKEY | Westmeath | Kileenboylegan, Moate | 6 | *N/A |  |  |  |  | Q2-2023
1802 | SHIP CONSTRUCTION TURNKEY | Westmeath | Mount Carmel Drive, Moate | 9 | N/A | [5 empty] | Q2-2023
1803 | SHIP CONSTRUCTION TURNKEY | Westmeath | Austin Friar Street, Mullingar | 4 | *N/A |  |  |  | Stage 4 approved Q1-2022, the scheme is fully approved.
1804 | SHIP CONSTRUCTION TURNKEY | Westmeath | Arcadia, Clonbrusk | 2 | *N/A | [5 empty] | Q4-2023
1805 | SHIP CONSTRUCTION TURNKEY | Westmeath | Gort na Locha, Lake Road, Moate | 2 | *N/A | [5 empty] | Q3-2024
1806 | SHIP CONSTRUCTION TURNKEY | Westmeath | Farranshock Park, Mullingar - Phase1 | 19 | *N/A | [5 empty] | Q4-2023
1807 | SHIP CONSTRUCTION TURNKEY | Westmeath | Farranshock Park, Mullingar - Phase 2 | 21 | *N/A | [5 empty] | Q2-2024
1808 | SHIP CONSTRUCTION TURNKEY | Westmeath | Gracefield, Drumaconn, Athlone | 9 | N/A | [5 empty] | Q4-2023
1809 | SHIP CONSTRUCTION TURNKEY | Westmeath | Mardyke Street, Athlone | 3 | N/A | [5 empty] | Q3-2024
1810 | SHIP CONSTRUCTION TURNKEY | Westmeath | Newbrook Road, Mullingar | 17 | N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1811 | SHIP CONSTRUCTION TURNKEY | Westmeath | Gort na Locha, Lake Road, Moate | 11 | *N/A |  |  |  |  | Q3-2023
1812 | SHIP CONSTRUCTION RENEWAL | Westmeath | Belvedere Orphanage, Tyrellspass | 5 | *N/A | Stage 1 approved Q1-2022, outline design and costs being prepared.
1813 | SHIP CONSTRUCTION RENEWAL | Westmeath | 36 Connaught Street, Athlone | 3 | *N/A |  | Stage 2 approved Q3-2023, full design/tender being prepared.
1814 | SHIP CONSTRUCTION RENEWAL | Westmeath | 53 Connaught Street, Athlone | 1 | *N/A |  | Stage 2 approved Q3-2023, full design/tender being prepared.
1815 | SHIP CONSTRUCTION RENEWAL | Westmeath | 59 Connaught Street, Athlone | 2 | N/A |  | Stage 2 approved Q3-2023, full design/tender being prepared.
1816 | SHIP CONSTRUCTION RENEWAL | Westmeath | Thornbury Drive, Athlone | 4 | N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
1817 | SHIP CONSTRUCTION DESIGN BUILD | Westmeath | St. Brigids Green, Mullingar | 10 | *N/A |  |  |  |  | Q4-2023
1818 | SHIP CONSTRUCTION DESIGN BUILD | Westmeath | Dalton Park, Mullingar | 17 | *N/A |  |  |  |  | Q2-2024
1819 | SHIP CONSTRUCTION DESIGN BUILD | Westmeath | Water Street, Castlepollard | 8 | *N/A |  |  |  |  | Q4-2023
1820 | SHIP CONSTRUCTION DESIGN BUILD | Westmeath | Ennell Court, Mullingar | 8 | *N/A |  |  |  |  | Q1-2024
1821 | SHIP CONSTRUCTION DESIGN BUILD | Westmeath | Ennell Court, Mullingar | 7 | *N/A |  |  |  |  | Q1-2024
1822 | SHIP CONSTRUCTION DESIGN BUILD | Westmeath | Castle Park, Rochfortbridge | 12 | N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
1823 | SHIP CONSTRUCTION DESIGN BUILD | Westmeath | St. Brigids Green, Mullingar | 12 | *N/A |  |  |  |  | Q4-2023
1824 | SHIP CONSTRUCTION | Westmeath | Bun Daire, Kinnegad (Phase 3) | 8 | *N/A | [5 empty] | Q2-2021
1825 | SHIP CONSTRUCTION | Westmeath | Ennell Court, Mullingar | 19 | *N/A | [5 empty] | Q4-2022
1826 | SHIP CONSTRUCTION | Westmeath | Quinlan Park, Athlone | 10 | *N/A | [5 empty] | Q4-2022
1827 | SHIP CONSTRUCTION | Westmeath | Bishopsgate, Mullingar | 2 | *N/A | [5 empty] | Q2-2021
1828 | SHIP CONSTRUCTION | Westmeath | Greally Park, Arcadia, Athlone | 24 | *N/A |  |  |  |  | Q3-2023
1829 | SHIP CONSTRUCTION | Westmeath | Canal Avenue, Mullingar | 32 | *N/A |  | Stage 2 approved Q4-2022, full design/tender being prepared.
1830 | SHIP CONSTRUCTION | Westmeath | Bun Daire, Kinnegad (Phase 3) | 4 | *N/A | [5 empty] | Q3-2021
1831 | SHIP CONSTRUCTION | Westmeath | Bishopsgate, Mullingar | 2 | *N/A | [5 empty] | Q4-2021
1832 | SHIP CONSTRUCTION | Westmeath | Abbey Rd, Athlone | 1 | N/A |  |  |  |  | Q1-2024
1833 | SHIP CONSTRUCTION | Westmeath | Cornamaddy, Athlone | 43 | *N/A |  | Stage 2 approved Q3-2023, full design/tender being prepared.
1834 | SHIP CONSTRUCTION | Westmeath | Water Street, Castlepollard | 1 | *N/A |  |  |  |  | Q3-2024
1835 | SHIP CONSTRUCTION | Westmeath | Cornamaddy, Athlone | 44 | *N/A |  | Stage 2 approved Q3-2023, full design/tender being prepared.
1836 | SHIP CONSTRUCTION | Westmeath | Ennell Court, Mullingar | 12 | *N/A | [5 empty] | Q4-2022
1837 | SHIP CONSTRUCTION | Westmeath | Abbeylands, Mullingar | 1 | *N/A |  | Stage 2 approved Q4-2022, full design/tender being prepared.
1838 | SHIP Accel MMC | Westmeath | Bun Daire, Kinnegad (Phase 4) | 12 | *N/A |  |  |  |  | Q3-2024
1839 | CAS CONSTRUCTION TURNKEY | Westmeath | Elm Row, Royal Canal, Mullingar | 10 | Túath Housing Association Ltd | [5 empty] | Q1-2021
1840 | CAS CONSTRUCTION TURNKEY | Westmeath | Elm Row, Royal Canal, Mullingar | 17 | Túath Housing Association Ltd | [5 empty] | Q3-2022
1841 | CAS CONSTRUCTION TURNKEY | Westmeath | Elm Row, Royal Canal, Mullingar | 9 | Túath Housing Association Ltd | [5 empty] | Q3-2022
1842 | CAS CONSTRUCTION TURNKEY | Westmeath | 14 The Drive, Drumaconn, Athlone | 1 | Túath Housing Association Ltd | [5 empty] | Q4-2023
1843 | CAS CONSTRUCTION RENEWAL | Westmeath | The Hermitage Building, Retreat Road, Athlone | 28 | Túath Housing Association Ltd |  | Stage 2 approved Q2-2023, full design/tender being prepared.
1844 | CAS CONSTRUCTION RENEWAL | Westmeath | The Hermitage Building, Retreat Road, Athlone | 27 | Túath Housing Association Ltd |  | Stage 2 approved Q2-2023, full design/tender being prepared.
1845 | CAS CONSTRUCTION | Westmeath | Farran, Mullingar | 4 | Túath Housing Association Ltd | [5 empty] | Q3-2021
1846 | SHIP CONSTRUCTION TURNKEY | Wexford | Airhill, Belvedere Rd, Wexford | 7 | *N/A | [5 empty] | Q3-2021
1847 | SHIP CONSTRUCTION TURNKEY | Wexford | Michael Street, New Ross | 3 | *N/A | [5 empty] | Q2-2021
1848 | SHIP CONSTRUCTION TURNKEY | Wexford | Ballynaglough, Blackwater | 4 | *N/A | [5 empty] | Q2-2022
1849 | SHIP CONSTRUCTION TURNKEY | Wexford | Tobar Muire, Creagh Gorey | 10 | *N/A | [5 empty] | Q3-2022
1850 | SHIP CONSTRUCTION TURNKEY | Wexford | Gleann an Ghairdin, Gorey - Phase 2 | 4 | *N/A | [5 empty] | Q4-2021
1851 | SHIP CONSTRUCTION TURNKEY | Wexford | Ard Uisce, Whiterock Hill, Wexford | 5 | *N/A | [5 empty] | Q2-2021
1852 | SHIP CONSTRUCTION TURNKEY | Wexford | Cluain Beag, Clonard, Wexford | 5 | *N/A | [5 empty] | Q4-2021
1853 | SHIP CONSTRUCTION TURNKEY | Wexford | Cluain Beag, Clonard, Wexford | 6 | *N/A | [5 empty] | Q4-2021
1854 | SHIP CONSTRUCTION TURNKEY | Wexford | Ard Uisce, Whiterock, Wexford | 2 | *N/A | [5 empty] | Q2-2021
1855 | SHIP CONSTRUCTION TURNKEY | Wexford | Ard an Bhile, Healysland, New Ross | 16 | *N/A | [5 empty] | Q4-2022
1856 | SHIP CONSTRUCTION TURNKEY | Wexford | Tobar Muire, Creagh Gorey | 29 | *N/A |  |  |  |  | Q4-2020
1857 | SHIP CONSTRUCTION TURNKEY | Wexford | Ballynaglough, Blackwater | 12 | *N/A | [5 empty] | Q4-2022
1858 | SHIP CONSTRUCTION TURNKEY | Wexford | Roxborough Manor, Mulgannon | 3 | *N/A | [5 empty] | Q2-2022
1859 | SHIP CONSTRUCTION TURNKEY | Wexford | Roxborough Manor, Mulgannon | 4 | *N/A | [5 empty] | Q2-2022
1860 | SHIP CONSTRUCTION TURNKEY | Wexford | Roxborough Manor, Mulgannon | 3 | *N/A | [5 empty] | Q2-2022
1861 | SHIP CONSTRUCTION TURNKEY | Wexford | Roxborough Manor, Mulgannon | 3 | *N/A | [5 empty] | Q4-2022
1862 | SHIP CONSTRUCTION TURNKEY | Wexford | Ard Uisce, Whiterock, Wexford | 2 | *N/A | [5 empty] | Q2-2021
1863 | SHIP CONSTRUCTION TURNKEY | Wexford | Clonard Little, Wexford | 9 | *N/A | [5 empty] | Q4-2023
1864 | SHIP CONSTRUCTION TURNKEY | Wexford | Ard an Bhile, Healysland, New Ross | 14 | *N/A | [5 empty] | Q4-2022
1865 | SHIP CONSTRUCTION TURNKEY | Wexford | Cluain Beag, Clonard, Wexford | 7 | *N/A | [5 empty] | Q1-2022
1866 | SHIP CONSTRUCTION TURNKEY | Wexford | Ard Uisce, Whiterock Hill, Wexford | 4 | *N/A | [5 empty] | Q2-2022
1867 | SHIP CONSTRUCTION TURNKEY | Wexford | Castlelands, Ferns | 20 | *N/A | [5 empty] | Q4-2023
1868 | SHIP CONSTRUCTION TURNKEY | Wexford | Cluain Beag, Clonard, Wexford | 2 | *N/A | [5 empty] | Q2-2022
1869 | SHIP CONSTRUCTION TURNKEY | Wexford | Ard Uisce, Whiterock Hill, Wexford | 4 | *N/A | [5 empty] | Q4-2022
1870 | SHIP CONSTRUCTION TURNKEY | Wexford | An Glasan, Greenville Lane, Enniscorthy | 8 | *N/A | [5 empty] | Q3-2024
1871 | SHIP CONSTRUCTION TURNKEY | Wexford | Gleann an Ghairdin, Ballytegan, Gorey | 24 | *N/A |  |  |  |  | Q1-2023
1872 | SHIP CONSTRUCTION TURNKEY | Wexford | Cross Street, New Ross | 2 | *N/A | [5 empty] | Q4-2023
1873 | SHIP CONSTRUCTION TURNKEY | Wexford | Green Hill, Clonhaston, Enniscorthy | 8 | *N/A | [5 empty] | Q4-2022
1874 | SHIP CONSTRUCTION TURNKEY | Wexford | Ard an Bhile, Healysland, New Ross | 13 | *N/A | [5 empty] | Q4-2022
1875 | SHIP CONSTRUCTION TURNKEY | Wexford | Forgelands, Enniscorthy | 2 | *N/A | [5 empty] | Q4-2023
1876 | SHIP CONSTRUCTION TURNKEY | Wexford | Gleann an Ghairdin, Ballytegan, Gorey | 16 | *N/A | [5 empty] | Q3-2024
1877 | SHIP CONSTRUCTION TURNKEY | Wexford | Ard Uisce, Whiterock Hill, Wexford | 2 | *N/A | [5 empty] | Q4-2023
1878 | SHIP CONSTRUCTION TURNKEY | Wexford | Churchview, Ballynaghlogh, Blackwater, Co. Wexford Phase 2 | 14 | *N/A |  |  |  |  | Q3-2023
1879 | SHIP CONSTRUCTION TURNKEY | Wexford | Mangan, Hollyfort, Gorey, Co. Wexford | 2 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
1880 | SHIP CONSTRUCTION TURNKEY | Wexford | Forgelands, Old Forge Road, Enniscorthy | 4 | *N/A | [5 empty] | Q4-2023
1881 | SHIP CONSTRUCTION TURNKEY | Wexford | Holly Way, Green Hill, Clonhaston, Enniscorthy, Co. Wexford | 5 | *N/A |  |  |  |  | Q3-2023
1882 | SHIP CONSTRUCTION TURNKEY | Wexford | Ard an Bhile, New Ross, Healysland, Co. Wexford | 24 | *N/A |  |  |  |  | Q1-2024
1883 | SHIP CONSTRUCTION TURNKEY | Wexford | Cnoc na Greine, Greenville Lane, Enniscorthy, Co. Wexford | 10 | *N/A |  |  |  | Stage 4 approved Q1-2024, the scheme is fully approved.
1884 | SHIP CONSTRUCTION TURNKEY | Wexford | Carrig on Bannow, Co. Wexford | 5 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1885 | SHIP CONSTRUCTION TURNKEY | Wexford | Forgelands, Old Forge Road, Enniscorthy, Co. Wexford | 3 | *N/A |  |  |  |  | Q1-2024
1886 | SHIP CONSTRUCTION TURNKEY | Wexford | Coolballow Road, Wexford | 20 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1887 | SHIP CONSTRUCTION TURNKEY | Wexford | Carrig on Bannow, Co. Wexford | 5 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1888 | SHIP CONSTRUCTION TURNKEY | Wexford | Ard an Bhile, New Ross, Healysland, Co. Wexford | 8 | *N/A |  |  |  |  | Q2-2024
1889 | SHIP CONSTRUCTION TURNKEY | Wexford | Grattan Court, Gorey, Co. Wexford | 14 | *N/A |  |  |  |  | Q4-2022
1890 | SHIP CONSTRUCTION TURNKEY | Wexford | Forgelands, Old Forge Road, Enniscorthy, Co. Wexford | 2 | *N/A |  |  |  |  | Q1-2024
1891 | SHIP CONSTRUCTION TURNKEY | Wexford | Forgelands, Old Forge Road, Enniscorthy, Co. Wexford | 4 | *N/A |  |  |  |  | Q1-2024
1892 | SHIP CONSTRUCTION TURNKEY | Wexford | Forgelands, Old Forge Road, Enniscorthy, Co. Wexford | 3 | *N/A |  |  |  |  | Q1-2024
1893 | SHIP CONSTRUCTION TURNKEY | Wexford | Cnoc na Greine, Enniscorthy, Wexford | 2 | *N/A |  |  |  |  | Q3-2024
1894 | SHIP CONSTRUCTION TURNKEY | Wexford | Cnoc na Greine, Enniscorthy, Wexford | 2 | *N/A |  |  |  |  | Q3-2024
1895 | SHIP CONSTRUCTION SINGLE STAGE | Wexford | Doire Molin, Monamolin, Gorey, Co. Wexford | 5 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1896 | SHIP CONSTRUCTION SINGLE STAGE | Wexford | Ballygillane Big, Rosslare Harbour | 5 | *N/A | Stage 1 approved Q4-2021, outline design and costs being prepared.
1897 | SHIP CONSTRUCTION SINGLE STAGE | Wexford | 20 Francis Street, Co. Wexford | 2 | *N/A |  |  |  | Stage 4 approved Q1-2023, the scheme is fully approved.
1898 | SHIP CONSTRUCTION SINGLE STAGE | Wexford | 30,31 Bride Street, Wexford | 3 | *N/A |  |  |  | Stage 4 approved Q2-2024, the scheme is fully approved.
1899 | SHIP CONSTRUCTION RENEWAL | Wexford | Newtown, Ferns | 1 | *N/A | [5 empty] | Q3-2024
1900 | SHIP CONSTRUCTION DESIGN BUILD | Wexford | Creagh, Gorey, Co. Wexford | 22 | *N/A |  |  |  |  | Q4-2023
1901 | SHIP CONSTRUCTION DESIGN BUILD | Wexford | Grogan’s Road, Wexford Town | 4 | *N/A | Stage 1 approved Q4-2021, outline design and costs being prepared.
1902 | SHIP CONSTRUCTION DESIGN BUILD | Wexford | Grahormack, Tagoat, Co. Wexford | 18 | *N/A |  |  |  |  | Q1-2024
1903 | SHIP CONSTRUCTION DESIGN BUILD | Wexford | Clonard Little, Wexford | 56 | *N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
1904 | SHIP CONSTRUCTION | Wexford | Whiterock Hill, Wexford - Phase 1 | 22 | *N/A | [5 empty] | Q4-2023
1905 | SHIP CONSTRUCTION | Wexford | Killeens, Wexford | 60 | *N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
1906 | SHIP CONSTRUCTION | Wexford | Ross Road, Enniscorthy | 1 | *N/A | [5 empty] | Q4-2021
1907 | SHIP CONSTRUCTION | Wexford | Glentire, The Ballagh, Enniscorthy | 7 | *N/A | [5 empty] | Q3-2022
1908 | SHIP CONSTRUCTION | Wexford | Rosetown, Rosslare - Phase 1 | 23 | *N/A | [5 empty] | Q4-2022
1909 | SHIP CONSTRUCTION | Wexford | Carley's Bridge, Enniscorthy | 17 | *N/A | [5 empty] | Q1-2022
1910 | SHIP CONSTRUCTION | Wexford | Rosbercon, New Ross | 38 | *N/A | Stage 1 approved Q2-2023, outline design and costs being prepared.
1911 | SHIP CONSTRUCTION | Wexford | Wexford Street, Gorey | 30 | *N/A |  |  |  |  | Q3-2023
1912 | SHIP CONSTRUCTION | Wexford | Bullawn, Irishtown, New Ross | 3 | *N/A |  |  |  |  | Q3-2021
1913 | SHIP CONSTRUCTION | Wexford | Ballyhine, Barntown | 8 | *N/A | [5 empty] | Q3-2024
1914 | SHIP CONSTRUCTION | Wexford | Whiterock Hill, Wexford - Phase 2 | 22 | *N/A |  |  |  |  | Q2-2023
1915 | SHIP CONSTRUCTION | Wexford | Rosetown, Rosslare - Phase 2 | 12 | *N/A | [5 empty] | Q2-2024
1916 | SHIP Accel MMC | Wexford | Cluain Fada, New Ross, Co. Wexford | 12 | *N/A |  | Stage 2 approved Q2-2024, full design/tender being prepared.
1917 | CAS CONSTRUCTION TURNKEY | Wexford | Clonattin, Gorey | 6 | Túath Housing Association Ltd | [5 empty] | Q2-2021
1918 | CAS CONSTRUCTION TURNKEY | Wexford | 2&3 The Quay, New Ross | 6 | Peter McVerry Trust Ltd | [5 empty] | Q4-2022
1919 | CAS CONSTRUCTION TURNKEY | Wexford | Riverchapel Road, Riverchapel Wood, Gorey, Wexford | 6 | Focus Ireland |  |  |  |  | Q1-2023
1920 | CAS CONSTRUCTION RENEWAL | Wexford | Ard na Naoimh, Gorey Hill | 4 | St. Aidan's Day Care Centre CLG |  |  | Stage 3 approved Q1-2024, the scheme is now approved to proceed to tender.
1921 | CAS CONSTRUCTION | Wexford | DVR @ Maudlintown | 12 | Wexford Womens’ Refuge CLG | [5 empty] | Q3-2024
1922 | CAS CONSTRUCTION | Wexford | 18 & 19 Grattan Street Gorey, Co. Wexford | 2 | Society of Saint Vincent de Paul | Stage 1 approved Q3-2023, outline design and costs being prepared.
1923 | CAS CONSTRUCTION | Wexford | 4 St. Michaels Place, Gorey, Wexford | 3 | Society of Saint Vincent de Paul | Stage 1 approved Q4-2023, outline design and costs being prepared.
1924 | CAS CONSTRUCTION | Wexford | Monastery Building/St. Josephs House, Gorey, Co. Wexford | 7 | Society of Saint Vincent de Paul | Stage 1 approved Q4-2023, outline design and costs being prepared.
1925 | CAS CONSTRUCTION | Wexford | 18 & 19 Grattan Street Gorey, Co. Wexford | 2 | Society of Saint Vincent de Paul | Stage 1 approved Q3-2023, outline design and costs being prepared.
1926 | SHIP CONSTRUCTION TURNKEY | Wicklow | Weaver Square, Baltinglass | 2 | *N/A |  |  |  |  | Q4-2023
1927 | SHIP CONSTRUCTION TURNKEY | Wicklow | The Birches, Ballinaclash | 2 | *N/A | [5 empty] | Q2-2021
1928 | SHIP CONSTRUCTION TURNKEY | Wicklow | Bramble Hill, Lugduff, Tinahely | 2 | *N/A | [5 empty] | Q1-2021
1929 | SHIP CONSTRUCTION TURNKEY | Wicklow | Vartry Heights, Roundwood | 4 | *N/A |  |  |  | Stage 4 approved Q3-2023, the scheme is fully approved.
1930 | SHIP CONSTRUCTION TURNKEY | Wicklow | Avonmore View, Rathdrum | 13 | *N/A | [5 empty] | Q1-2023
1931 | SHIP CONSTRUCTION TURNKEY | Wicklow | Bramble Hill, Lugduff, Tinahely | 1 | *N/A | [5 empty] | Q2-2021
1932 | SHIP CONSTRUCTION TURNKEY | Wicklow | 95 Waverley Drive, Broomhall, Rathnew | 1 | *N/A | [5 empty] | Q1-2022
1933 | SHIP CONSTRUCTION TURNKEY | Wicklow | Waverley Drive, Broomhall, Rathnew | 3 | *N/A | [5 empty] | Q2-2022
1934 | SHIP CONSTRUCTION TURNKEY | Wicklow | Waverley Drive, Broomhall, Rathnew | 3 | N/A | [5 empty] | Q1-2022
1935 | SHIP CONSTRUCTION TURNKEY | Wicklow | Waverley Drive, Broomhall, Rathnew | 1 | *N/A | [5 empty] | Q2-2022
1936 | SHIP CONSTRUCTION TURNKEY | Wicklow | Waverley Drive, Broomhall, Rathnew | 2 | *N/A | [5 empty] | Q2-2022
1937 | SHIP CONSTRUCTION TURNKEY | Wicklow | Heatherside, Vale Road, Arklow | 3 | N/A |  |  |  |  | Q4-2023
1938 | SHIP CONSTRUCTION TURNKEY | Wicklow | Brookfield Park, Broomhall, Rathnew | 1 | *N/A | [5 empty] | Q2-2024
1939 | SHIP CONSTRUCTION TURNKEY | Wicklow | Fairfield Court, Greystones | 5 | *N/A | [5 empty] | Q3-2024
1940 | SHIP CONSTRUCTION TURNKEY | Wicklow | Burkeen Dales, Rathnew, Co. Wicklow | 5 | *N/A |  |  |  |  | Q2-2024
1941 | SHIP CONSTRUCTION TURNKEY | Wicklow | Burkeen Dales, Rathnew, Co. Wicklow | 8 | *N/A |  |  |  |  | Q2-2024
1942 | SHIP CONSTRUCTION SINGLE STAGE | Wicklow | Ballynerrin Upper, Wicklow Town | 10 | *N/A | [5 empty] | Q2-2024
1943 | SHIP CONSTRUCTION SINGLE STAGE | Wicklow | Merrymeeting View, Rathnew - Phase 3 | 7 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
1944 | SHIP CONSTRUCTION RENEWAL | Wicklow | 30 South Green, Arklow | 1 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1945 | SHIP CONSTRUCTION RENEWAL | Wicklow | 5 Priory Way, Delgany, Co. Wicklow | 1 | *N/A |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
1946 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Merrymeeting View, Rathnew | 46 | *N/A | [5 empty] | Q2-2021
1947 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Shillelagh (Phase 4) | 20 | *N/A |  |  |  |  | Q4-2022
1948 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Ashtown Lane, Wicklow Town | 40 | *N/A | [5 empty] | Q2-2022
1949 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Ard na Greine, West Ward, Bray | 31 | *N/A | [5 empty] | Q1-2022
1950 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Avondale Heights, Rathdrum | 20 | *N/A | [5 empty] | Q2-2023
1951 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Sheehan Court, Back Street, Arklow | 7 | *N/A | [5 empty] | Q3-2022
1952 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Mountainview, Moneycarroll, Newtownmountkennedy | 22 | *N/A | [5 empty] | Q2-2022
1953 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Three Trouts, Greystones | 41 | *N/A |  |  |  |  | Q3-2022
1954 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Cedar Court, Schools Road, Bray | 14 | *N/A | [5 empty] | Q3-2023
1955 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Coolattin Oaks, Carnew (Phase 4) | 8 | *N/A | [5 empty] | Q1-2021
1956 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Merrymeeting, Rathnew (Phase 2) | 21 | *N/A | [5 empty] | Q3-2024
1957 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Tinahely, Lugduff | 20 | *N/A |  |  |  |  | Q3-2023
1958 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Carrigoona, Bray | 13 | *N/A |  |  | Stage 3 approved Q3-2024, the scheme is now approved to proceed to tender.
1959 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Lott Lane, Kilcoole | 80 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1960 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Ballinahinch, Ashford | 23 | *N/A |  | Stage 2 approved Q3-2023, full design/tender being prepared.
1961 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Tinahask Upper, Arklow | 74 | *N/A | Stage 1 approved Q1-2024, outline design and costs being prepared.
1962 | SHIP CONSTRUCTION DESIGN BUILD | Wicklow | Hawkstown Phase 2, Ballynerrin, Wicklow, Town | 56 | *N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
1963 | SHIP CONSTRUCTION | Wicklow | Delaney Park, Emoclew Road, Arklow Phase 2 and 3 | 10 | *N/A | [5 empty] | Q1-2022
1964 | SHIP CONSTRUCTION | Wicklow | 10A & 10 B Castle Villas, Greystones | 2 | *N/A | [5 empty] | Q4-2023
1965 | SHIP CONSTRUCTION | Wicklow | Delaney Park, Emoclew Road, Arklow Phase 2 and 3 | 37 | *N/A | [5 empty] | Q4-2021
1966 | SHIP CONSTRUCTION | Wicklow | Blackhills, Glenealy | 2 | *N/A | [5 empty] | Q1-2023
1967 | SHIP CONSTRUCTION | Wicklow | Main St, Kilcoole, Greystones | 4 | *N/A | [5 empty] | Q3-2024
1968 | SHIP CONSTRUCTION | Wicklow | Mill Road, Killincarrig, Greystones | 2 | *N/A | [5 empty] | Q3-2023
1969 | SHIP CONSTRUCTION | Wicklow | Carraig Eden, Greysones (Phase 3) | 14 | *N/A |  | Stage 2 approved Q4-2021, full design/tender being prepared.
1970 | SHIP CONSTRUCTION | Wicklow | Kilbride Lane, Bray (Murphy's Lands) | 19 | *N/A | [5 empty] | Q2-2021
1971 | SHIP CONSTRUCTION | Wicklow | Knockroe, Delgany | 2 | *N/A | [5 empty] | Q4-2023
1972 | SHIP CONSTRUCTION | Wicklow | Mountain View, Blessington | 10 | *N/A | Stage 1 approved Q3-2022, outline design and costs being prepared.
1973 | SHIP CONSTRUCTION | Wicklow | 5A Rednagh Road, Aughrim | 1 | *N/A |  |  |  | Stage 4 approved Q3-2024, the scheme is fully approved.
1974 | SHIP CONSTRUCTION | Wicklow | 1 Mill Road, Greystones | 4 | *N/A | Stage 1 approved Q2-2024, outline design and costs being prepared.
1975 | CAS CONSTRUCTION TURNKEY | Wicklow | Rathcoran Square, Baltinglass | 8 | Peter McVerry Trust Ltd | [5 empty] | Q2-2021
1976 | CAS CONSTRUCTION TURNKEY | Wicklow | Aldborough Manor, Hawkins Wood, Greystones | 90 | Túath Housing Association Ltd | [5 empty] | Q4-2022
1977 | CAS CONSTRUCTION SINGLE STAGE | Wicklow | Hollybrook Park, Bray | 4 | St. John of God Housing Association Ltd |  |  |  |  | Q4-2023
1978 | CAS CONSTRUCTION RENEWAL | Wicklow | 4 Wyndham Park, Bray | 2 | DePaul Housing |  |  |  | Stage 4 approved Q4-2023, the scheme is fully approved.
1979 | CAS CONSTRUCTION | Wicklow | Parnell Road, Bray | 17 | Túath Housing Association Ltd |  |  | Stage 3 approved Q2-2023, the scheme is now approved to proceed to tender.
1980 | CALF Turnkey | Carlow | Ballickmoyler, Graigcullen, Carlow (Phase 1) | 22 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2021
1981 | CALF Turnkey | Carlow | Ballickmoyler, Graigcullen, Carlow (Phase 2) | 35 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2021
1982 | CALF Turnkey | Carlow | Cois Dara, Tullow Road, Chapelstown, Carlow (Phase 1)* | 17 | Tuath Housing Association | [5 empty] | Q3-2021
1983 | CALF Turnkey | Carlow | Cois Dara, Tullow Road, Chapelstown, Carlow (Phase 2)* | 15 | Tuath Housing Association | [5 empty] | Q4-2021
1984 | CALF Turnkey | Carlow | Cois Dara, Tullow Road, Chapelstown, Carlow (Phase 3)* | 21 | Tuath Housing Association | [5 empty] | Q1-2022
1985 | CALF Turnkey | Carlow | Cois Dara, Tullow Road, Chapelstown, Carlow (Phase 4) | 10 | Tuath Housing Association | [5 empty] | Q2-2022
1986 | CALF Turnkey | Carlow | Granite Court, Ballyknockan, Fenagh, Co Carlow (Phase 1) | 8 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
1987 | CALF Turnkey | Carlow | Mill Race, Paupish Lane, Carlow, Co. Carlow (Phase 2) | 6 | Tuath Housing Association | [5 empty] | Q2-2021
1988 | CALF Turnkey | Carlow | Montgomery Street , Carlow (Phase 1)* | 32 | Clúid Housing |  |  |  |  | Q2-2024
1989 | CALF Turnkey | Carlow | Rivercourt, Carlow (Phase 2)* | 19 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q1-2022
1990 | CALF Turnkey | Carlow | Sli na Ri , Bagnelstown, Co. Carlow (Phase 5) (Phase 1)* | 4 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
1991 | CALF Turnkey | Carlow | Sli Na Ri, Moneybeg, Bagenalstown, Co. Carlow (Phase 1) | 7 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2023
1992 | CALF Turnkey | Carlow | Sli Na Ri, Moneybeg, Bagenalstown, Co. Carlow (Phase 2)* | 3 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
1993 | CALF Turnkey | Carlow | Sli Na Ri, Moneybeg, Bagenalstown, Co. Carlow (Phase 3) | 4 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
1994 | CALF Turnkey | Carlow | Sli Na Ri, Moneybeg, Bagenalstown, Co. Carlow (Phase 4) | 5 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2021
1995 | CALF Turnkey | Carlow | Tanner Hall, Athy Road, Carlow (Phase 1) | 11 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2022
1996 | CALF Turnkey | Carlow | Tanner Hall, Athy Road, Carlow (Phase 2)* | 38 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2022
1997 | CALF Turnkey | Carlow | The Millrace, Burrin, Co. Carlow (Phase 1)* | 22 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2021
1998 | CALF Turnkey | Carlow | Tullowbeg, Tullow, Co. Carlow (Phase 1)* | 26 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
1999 | CALF Turnkey | Carlow | Tullowbeg, Tullow, Co. Carlow (Phase 2)* | 22 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
2000 | CALF Turnkey | Cavan | 16 Units, Fairgreen Park, Mullagh, Co. Cavan (Phase 1) | 16 | Clanmil Housing Association Ireland | [5 empty] | Q4-2021
2001 | CALF Turnkey | Cavan | Drumalee Manor, Drumalee, Co. Cavan (Phase 1) | 12 | Tuath Housing Association | [5 empty] | Q2-2022
2002 | CALF Turnkey | Cavan | Drumalee Manor, Drumalee, Co. Cavan (Phase 2) | 5 | Tuath Housing Association | [5 empty] | Q4-2022
2003 | CALF Turnkey | Cavan | Drumalee Manor, Drumalee, Co. Cavan (Phase 3) | 8 | Tuath Housing Association | [5 empty] | Q3-2023
2004 | CALF Turnkey | Cavan | Market Square View, Main Street, Arvagh, Co. Cavan, (Phase 1) | 4 | North and East Housing Association CLG |  |  |  |  | Q2-2024
2005 | CALF Turnkey | Cavan | Market Street, Cootehill, Co. Cavan (Phase 1) | 9 | North and East Housing Association CLG |  |  |  |  | Q4-2023
2006 | CALF Turnkey | Cavan | Rampart View, Virginia, Co. Cavan (Phase 1) | 5 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2007 | CALF Turnkey | Cavan | Rampart View, Virginia, Co. Cavan (Phase 3) | 6 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2021
2008 | CALF Turnkey | Cavan | Sli Na Coille, Belturbet, Co. Cavan (Phase 1) | 4 | North and East Housing Association CLG | [5 empty] | Q3-2024
2009 | CALF Turnkey | Cavan | Sli Na Coille, Belturbet, Co. Cavan (Phase 2) | 6 | North and East Housing Association CLG |  |  |  |  | Q1-2023
2010 | CALF Turnkey | Cavan | The Gallops, Cavan Town, Co. Cavan (Phase 2) | 22 | Clúid Housing | [5 empty] | Q2-2022
2011 | CALF Turnkey | Clare | 4 units, Ballyminogue, Scarrif, Co. Clare (Phase 1) | 4 | Focus Housing Association CLG | [5 empty] | Q4-2023
2012 | CALF Turnkey | Clare | Acha Bhile, Lahinch Road, Ennis, Co Clare (Loughville) (Phase 1) | 12 | Clúid Housing | [5 empty] | Q4-2023
2013 | CALF Turnkey | Clare | Acha Bhile, Lahinch Road, Ennis, Co Clare (Loughville) (Phase 2) | 11 | Clúid Housing |  |  |  |  | Q2-2023
2014 | CALF Turnkey | Clare | Acha Bhile, Lahinch Road, Ennis, Co Clare (Loughville) (Phase 3) | 10 | Clúid Housing |  |  |  |  | Q2-2023
2015 | CALF Turnkey | Clare | An Cosan Gheall, Limerick Rd, Ennis, Co Clare (Phase 1)* | 18 | Inis Housing Association | [5 empty] | Q3-2023
2016 | CALF Turnkey | Clare | Ard Ratha, Sixemilebridge, Co. Clare (Phase 1)* | 3 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2023
2017 | CALF Turnkey | Clare | Cahercalla, Drumbiggle, Ennis, Clare (Phase 2)* | 2 | Clúid Housing | [5 empty] | Q1-2022
2018 | CALF Turnkey | Clare | Cappahard, Tulla Road, Ennis Co. Clare (Phase 1)* | 26 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2019 | CALF Turnkey | Clare | Carraig Nua, Carraig Nua, Tulla, Co Clare (Phase 1)* | 4 | Clúid Housing |  |  |  |  | Q3-2023
2020 | CALF Turnkey | Clare | Cill Stuifin, School Road, Lahinch Co Clare (Phase 1)* | 3 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2023
2021 | CALF Turnkey | Clare | Cluain Na Laoi, Kilkishen, Co. Clare (Phase 1)* | 8 | Circle Voluntary Housing Association CLG | [5 empty] | Q2-2024
2022 | CALF Turnkey | Clare | Cluain Na Laoi, Kilkishen, Co. Clare (Phase 2) | 8 | Circle Voluntary Housing Association CLG | [5 empty] | Q2-2024
2023 | CALF Turnkey | Clare | Doire Mor, Knockaderry, Ennis, Co Clare (Phase 1)* | 2 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2024 | CALF Turnkey | Clare | Gleann Cora, Newmarket on Fergus, Co. Clare (Phase 2)* | 2 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2021
2025 | CALF Turnkey | Clare | Hogan’s Place, Limerick Road, Ennis, Co. Clare (formerly Abbey View) (Phase 1) | 9 | Clúid Housing | [5 empty] | Q4-2022
2026 | CALF Turnkey | Clare | Hogan’s Place, Limerick Road, Ennis, Co. Clare (formerly Abbey View) (Phase 2)* | 15 | Clúid Housing | [5 empty] | Q2-2023
2027 | CALF Turnkey | Clare | Loughvella, Ennis, Co. Clare (aka Loughville Lahinch Road) (Phase 1)* | 14 | Tuath Housing Association |  |  |  |  | Q1-2024
2028 | CALF Turnkey | Clare | Loughvella, Ennis, Co. Clare (aka Loughville Lahinch Road) (Phase 2)* | 34 | Tuath Housing Association |  |  |  |  | Q1-2024
2029 | CALF Turnkey | Clare | Market Square Apartments, Ennis, Co. Clare (Phase 1)* | 14 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
2030 | CALF Turnkey | Clare | Millbank, Roslevan, Ennis, Co Clare (Phase 1)* | 15 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q1-2024
2031 | CALF Turnkey | Clare | Millbank, Roslevan, Ennis, Co Clare (Phase 2)* | 10 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q1-2024
2032 | CALF Turnkey | Clare | Quingardens, Quin, Ennis, Co. Clare (Phase 1)* | 36 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
2033 | CALF Turnkey | Clare | Radharc an Chnoic, Tulla, Co. Clare (Phase 1)* | 2 | Clúid Housing | [5 empty] | Q2-2023
2034 | CALF Turnkey | Clare | Radharc an Dun, Crusheen, Co Clare (Phase 1)* | 3 | Clúid Housing | [5 empty] | Q3-2024
2035 | CALF Turnkey | Clare | Radharc Doire, Smithstown, Shannon, Co Clare (Phase 1)* | 5 | Clúid Housing |  |  |  |  | Q1-2023
2036 | CALF Construction | Clare | Revised - Bruachlan, Westbury, Co Clare (Phase 1) | 22 | Co - Operative Housing Ireland Society Limited |  |  |  | Q2-2021
2037 | CALF Turnkey | Clare | Roslevan, Ennis, Co Clare (Phase 1)* | 25 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2023
2038 | CALF Turnkey | Clare | Roslevan, Tulla Road, Ennis, County Clare (Phase 1) | 14 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2021
2039 | CALF Turnkey | Clare | Roslevan, Tulla Road, Ennis, County Clare (Phase 2)* | 15 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q1-2022
2040 | CALF Turnkey | Clare | Roslevan, Tulla Road, Ennis, County Clare (Phase 3)* | 24 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2022
2041 | CALF Turnkey | Clare | Roslevan, Tulla Road, Ennis, County Clare (Phase 4)* | 16 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2022
2042 | CALF Turnkey | Cork City | 16 homes at Grand Parade, Cork City (Phase 1) | 16 | Focus Housing Association CLG | [5 empty] | Q4-2022
2043 | CALF Turnkey | Cork City | 3 units, Model Quarters, Tower, Blarney, Co Cork (Phase 1) | 3 | Circle Voluntary Housing Association CLG | [5 empty] | Q2-2023
2044 | CALF Turnkey | Cork City | 6 units at Kyle Street, Cork (Phase 1) | 6 | Focus Housing Association CLG | [5 empty] | Q3-2023
2045 | CALF Turnkey | Cork City | Ashbrook, Ballinglanna, Riverstown, Glanmire, Cork (Phase 1)* | 30 | Focus Housing Association CLG |  |  |  |  | Q2-2023
2046 | CALF Turnkey | Cork City | Aylesbury, Ballintemple, Cork City (Phase 1)* | 8 | Respond | [5 empty] | Q4-2022
2047 | CALF Turnkey | Cork City | Aylesbury, Ballintemple, Cork City (Phase 2) | 8 | Respond | [5 empty] | Q4-2022
2048 | CALF Turnkey | Cork City | Baker Street, Ballincollig, Co Cork (Phase 1)* | 14 | Clúid Housing | [5 empty] | Q4-2023
2049 | CALF Turnkey | Cork City | Barrett's Lane, Bishopstown, Cork (Phase 1) | 8 | Galtan Ltd |  |  |  |  | Q2-2024
2050 | CALF Turnkey | Cork City | Barters Wood, Tower, Cork (Phase 1)* | 3 | Tuath Housing Association | [5 empty] | Q2-2022
2051 | CALF Turnkey | Cork City | Barters Wood, Tower, Cork (Phase 2)* | 3 | Tuath Housing Association | [5 empty] | Q2-2022
2052 | CALF Turnkey | Cork City | Block 10 Jacobs Island, Mahon, Cork (Phase 1) | 69 | Respond |  |  |  |  | Q4-2022
2053 | CALF Construction | Cork City | Crann Darach, Middle Glanmire Road, Montenotte, Cork (formerly St Dominics) (Phase 1) | 27 | Tuath Housing Association | [5 empty] | Q4-2022
2054 | CALF Turnkey | Cork City | Evergreen Road, Turners Cross, Cork (Phase 1)* | 28 | Respond | [5 empty] | Q4-2022
2055 | CALF Turnkey | Cork City | Fairfield Meadows, Upper Fair Hill, Cork (Phase 1)* | 18 | Focus Housing Association CLG |  |  |  | Q4-2022
2056 | CALF Turnkey | Cork City | Fairfield View, Gurranabraher, Cork City (Phase 1)* | 21 | Respond | [5 empty] | Q4-2023
2057 | CALF Turnkey | Cork City | Fairfield View, Gurranabraher, Cork City (Phase 2)* | 25 | Respond | [5 empty] | Q2-2024
2058 | CALF Turnkey | Cork City | Glanmire Lodge, Dunkettle, Cork (Phase 1)* | 26 | Clúid Housing |  |  |  |  | Q2-2024
2059 | CALF Turnkey | Cork City | Glanmire Village, Glanmire, Cork (Phase 1) | 3 | Focus Housing Association CLG | [5 empty] | Q2-2022
2060 | CALF Construction | Cork City | Green Lane, Blackpool, Cork City- (Thomas Davis St) (Phase 1) | 112 | Clúid Housing | [5 empty] | Q4-2023
2061 | CALF Turnkey | Cork City | Haig Gardens, Boreenamanna Road and Wallace Avenue, Ballintemple (Glenanaar) (Phase 1)* | 27 | Respond | [5 empty] | Q4-2022
2062 | CALF Turnkey | Cork City | Hereford Place, Ballymacthomas Street, Cork City (Phase 1)* | 19 | Respond | [5 empty] | Q4-2022
2063 | CALF Turnkey | Cork City | High Street, Cork City, 19-20 High Street, Cork City (Phase 1) | 4 | Focus Housing Association CLG |  |  |  |  | Q4-2023
2064 | CALF Turnkey | Cork City | Lancaster Gate, Western Road, Cork (Phase 1) | 15 | Clúid Housing | [5 empty] | Q4-2022
2065 | CALF Turnkey | Cork City | Link Road, De Barra Court, Ballincollig, Co. Cork (Phase 1)* | 40 | Respond |  |  |  |  | Q3-2021
2066 | CALF Turnkey | Cork City | Manhattan Bar, Lower Friars Walk, Ballyphehane, Cork (Phase 1)* | 24 | Focus Housing Association CLG |  |  |  |  | Q3-2024
2067 | CALF Turnkey | Cork City | Miles Stream, Shanakiel, Cork (Phase 1) | 22 | Tuath Housing Association | [5 empty] | Q4-2022
2068 | CALF Turnkey | Cork City | Miles Stream, Shanakiel, Cork (Phase 2) | 20 | Tuath Housing Association | [5 empty] | Q4-2022
2069 | CALF Turnkey | Cork City | Millfield Cottages, Blackpool, Cork City (Phase 1)* | 18 | Respond | [5 empty] | Q4-2023
2070 | CALF Turnkey | Cork City | Newton Heights, Boherboy Road, Lotamore, Co Cork (second Phase) (Phase 1) | 15 | Clúid Housing | [5 empty] | Q4-2023
2071 | CALF Turnkey | Cork City | Newton Heights, Boherboy Road, Lotamore, Co Cork (second Phase) (Phase 2) | 11 | Clúid Housing | [5 empty] | Q4-2023
2072 | CALF Turnkey | Cork City | Newton Heights, Boherboy Road, Lotamore, Co Cork (second Phase) (Phase 3) | 3 | Clúid Housing |  |  |  |  | Q4-2021
2073 | CALF Turnkey | Cork City | Newton Heights, Boherboy Road, Lotamore, Cork (Phase 1) | 8 | Clúid Housing | [5 empty] | Q4-2022
2074 | CALF Turnkey | Cork City | Palaceanne Villas, South Douglas Road, Cork (Phase 1) | 3 | Galtan Ltd |  |  |  |  | Q1-2024
2075 | CALF Turnkey | Cork City | Redforge Road, Blackpool, Cork City (Phase 2) | 31 | Respond | [5 empty] | Q4-2021
2076 | CALF Turnkey | Cork City | Redforge Road, Blackpool, Cork City (Phase 3) | 20 | Respond | [5 empty] | Q3-2022
2077 | CALF Turnkey | Cork City | Redforge Road, Blackpool, Cork City (Phase 4)* | 11 | Respond | [5 empty] | Q4-2023
2078 | CALF Turnkey | Cork City | Riverside Farm, Model Farm Road, Bishopstown, Cork (Phase 1)* | 48 | Respond |  |  |  |  | Q2-2023
2079 | CALF Turnkey | Cork City | Riverside Grove, Bayly, Douglas, Cork (Castletreasure) (Phase 1) | 23 | Tuath Housing Association | [5 empty] | Q4-2023
2080 | CALF Turnkey | Cork City | Sarsfield Road, Doughcloyne, Wilton, Cork (Phase 1)* | 22 | Respond | [5 empty] | Q2-2022
2081 | CALF Turnkey | Cork City | Sarsfield Road, Doughcloyne, Wilton, Cork (Phase 2)* | 19 | Respond | [5 empty] | Q4-2022
2082 | CALF Turnkey | Cork City | Sarsfield Road, Doughcloyne, Wilton, Cork (Phase 3) | 24 | Respond | [5 empty] | Q4-2022
2083 | CALF Turnkey | Cork City | Sarsfield Road, Doughcloyne, Wilton, Cork City (Phase 1) | 4 | Respond | [5 empty] | Q4-2022
2084 | CALF Turnkey | Cork City | Southern Road, Ballintemple, Cork City. (Phase 1) | 2 | Galtan Ltd |  |  |  |  | Q3-2024
2085 | CALF Turnkey | Cork City | Springville House, Bulls Lane, Blackrock Road, Cork (Phase 1) | 35 | Tuath Housing Association | [5 empty] | Q4-2022
2086 | CALF Turnkey | Cork City | Strawberry Hill, Blarney Street, Cork (Phase 1)* | 16 | Respond |  |  |  |  | Q4-2023
2087 | CALF Turnkey | Cork City | Summerville Place, Sunday’s Well, Cork (Phase 1) | 10 | Respond | [5 empty] | Q4-2022
2088 | CALF Turnkey | Cork City | The Oaks, Frankfield, Douglas, Cork City (Phase 1)* | 2 | Tuath Housing Association | [5 empty] | Q4-2021
2089 | CALF Turnkey | Cork County | Burton, Ballyvaloon, Cobh, Co. Cork (Phase 1)* | 56 | Respond |  |  |  |  | Q1-2022
2090 | CALF Turnkey | Cork County | Cascade Apartments, Castlelake, Carrigtwohill, Cork (Phase 1) | 95 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2091 | CALF Turnkey | Cork County | Castle Heights, Kilmoney, Carrigaline, Co. Cork (Phase 1) | 12 | Clúid Housing | [5 empty] | Q4-2022
2092 | CALF Turnkey | Cork County | Chapel Lane View, Doneraile, Co. Cork (Phase 1) | 4 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2093 | CALF Turnkey | Cork County | Church Place, Oliver Plunkett Street, Fermoy, Co Cork (Phase 1) | 7 | Focus Housing Association CLG |  |  |  |  | Q3-2023
2094 | CALF Turnkey | Cork County | Cois Gallain, Brindle Hill, Charleville, Co Cork (Phase 1)* | 42 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2024
2095 | CALF Turnkey | Cork County | Cois Gallain, Brindle Hill, Charleville, Co Cork (Phase 2)* | 7 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
2096 | CALF Turnkey | Cork County | Cooline Heights, Cooline, Cobh, Co Cork (Phase 1) | 18 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2097 | CALF Turnkey | Cork County | Cooline, Cobh, Co Cork (Phase 1) | 17 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2098 | CALF Turnkey | Cork County | Cooline, Cobh, Co Cork (Phase 2) | 15 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2099 | CALF Turnkey | Cork County | Cooline, Cobh, Co Cork, Phase 5 (Phase 1) | 24 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q1-2023
2100 | CALF Turnkey | Cork County | Cork Road, Coolcarron, Fermoy, Co. Cork (Phase 1)* | 28 | Focus Housing Association CLG |  |  |  | Q3-2024
2101 | CALF Construction | Cork County | Corran Anna Fisher, Barrack Road, Youghal, Co. Cork (Phase 1) | 28 | Respond |  |  |  | Q2-2024
2102 | CALF Turnkey | Cork County | Cul na Cille, Church Hill, Carrigaline, Co Cork (formerly Church Hill, Carrigaline, Co.Cork) (Phase 1)* | 37 | Respond | [5 empty] | Q4-2023
2103 | CALF Turnkey | Cork County | Harbour Heights, Passage West, Co Cork (Phase 1) | 14 | Clúid Housing | [5 empty] | Q3-2022
2104 | CALF Turnkey | Cork County | Harbour Heights, Passage West, Co Cork (Phase 2) | 13 | Clúid Housing | [5 empty] | Q4-2022
2105 | CALF Turnkey | Cork County | Hazel View, Hazel Brooke, Spa Glen, Mallow, Co Cork (Phase 1) | 12 | Clúid Housing | [5 empty] | Q3-2023
2106 | CALF Turnkey | Cork County | Helms Point , Crosshaven , Co Cork (Phase 1)* | 4 | Clúid Housing |  |  |  |  | Q1-2024
2107 | CALF Turnkey | Cork County | Helms Point , Crosshaven , Co Cork (Phase 2)* | 16 | Clúid Housing |  |  |  |  | Q1-2024
2108 | CALF Turnkey | Cork County | Maple Woods, Ballinacurra, Midleton, Cork (Phase 1) | 14 | Tuath Housing Association | [5 empty] | Q3-2024
2109 | CALF Turnkey | Cork County | Meadow Grove, Newtown, Cobh, Co. Cork. (Phase 1)* | 30 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2022
2110 | CALF Turnkey | Cork County | Pairc an Mhuilinn, Distillery Road, Bandon, Co. Cork (Phase 1)* | 43 | Respond |  |  |  | Q2-2024
2111 | CALF Turnkey | Cork County | Phase 1 - West End, Mallow, Co Cork (Phase 1) | 4 | Focus Housing Association CLG | [5 empty] | Q2-2024
2112 | CALF Turnkey | Cork County | Phase 2 - West End, Mallow, 5-7 West End, Mallow, Co Cork (Phase 1) | 9 | Focus Housing Association CLG | [5 empty] | Q2-2024
2113 | CALF Turnkey | Cork County | Rath More Green, Barrack Street, Kinsale, Co. Cork (Phase 1)* | 3 | Tuath Housing Association | [5 empty] | Q3-2023
2114 | CALF Turnkey | Cork County | Rathgoggin Place, Charleville North, Charleville, Cork Formerly Cedar Court, Rathgoggin North, Charleville, Cork (Phase 1) | 11 | Tuath Housing Association | [5 empty] | Q4-2023
2115 | CALF Turnkey | Cork County | Shambles Lane, Thomas Davis Street, Mallow, Co Cork (Phase 1) | 6 | Focus Housing Association CLG | [5 empty] | Q4-2022
2116 | CALF Turnkey | Cork County | Warrens Court, Barnahely, Ringaskiddy, Cork (Formerly Barnahely, Ringaskiddy, Cork) (Phase 1) | 2 | Circle Voluntary Housing Association CLG | [5 empty] | Q3-2023
2117 | CALF Turnkey | Cork County | Westview, Coolroe, Ballincollig, Co. Cork (Phase 2) | 20 | Respond | [5 empty] | Q1-2021
2118 | CALF Turnkey | DLR | Alto Apartments, Frascati Centre, Blackrock, Co. Dublin (Phase 1)* | 3 | Housing Association of Integrated Living | [5 empty] | Q4-2023
2119 | CALF Turnkey | DLR | Ardilea Crescent, Ardilea, Clonskeagh, Dublin 14, Co. Dublin (Phase 1)* | 2 | Tuath Housing Association | [5 empty] | Q4-2021
2120 | CALF Turnkey | DLR | Beech Wood Manor and Beech Wood House, Beech Park, Stillorgan, Co. Dublin (Phase 1)* | 16 | Respond | [5 empty] | Q3-2023
2121 | CALF Turnkey | DLR | Block G, Domville Crescent, Cherrywood, Dublin 18 (Phase 1)* | 30 | Oaklee Housing |  |  |  |  | Q1-2022
2122 | CALF Turnkey | DLR | Castle House, Castle Way, Cherrywood, Dublin 18 (Phase 1) | 47 | Oaklee Housing |  |  |  |  | Q3-2023
2123 | CALF Turnkey | DLR | Chapel Hill, Glebe Road, Kilternan, Co. Dublin (Phase 1) | 4 | Fold Housing Association Ireland Ltd | [5 empty] | Q4-2023
2124 | CALF Turnkey | DLR | Cherrywood Town Centre, Dublin 18 (Phase 1)* | 80 | Clúid Housing | [5 empty] | Q4-2023
2125 | CALF Turnkey | DLR | Cherrywood Town Centre, Dublin 18 (Phase 2)* | 61 | Clúid Housing |  |  |  |  | Q4-2019
2126 | CALF Turnkey | DLR | Cookstown Lane, Ballybetagh Road, Kilternan, Co Dublin (Phase 1)* | 22 | Clanmil Housing Association Ireland | [5 empty] | Q4-2023
2127 | CALF Turnkey | DLR | Crofters Quarter, Deansgrange Road, Deansgrange, Blackrock, Co. Dublin (Phase 1)* | 120 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2128 | CALF Turnkey | DLR | Dun Oir Grove, Glenamuck Road, Kiltiernan, Dublin 18 (Phase 1)* | 49 | Tuath Housing Association | [5 empty] | Q4-2023
2129 | CALF Turnkey | DLR | Egremont, Church Road, Killiney, Co. Dublin (Phase 1)* | 4 | Circle Voluntary Housing Association CLG |  |  |  |  | Q4-2019
2130 | CALF Construction | DLR | Enniskerry Road, Sandyford, Dublin 18 (Phase 1) | 9 | Respond | [5 empty] | Q4-2021
2131 | CALF Construction | DLR | Enniskerry Road, Sandyford, Dublin 18 (Phase 2) | 22 | Respond | [5 empty] | Q1-2022
2132 | CALF Construction | DLR | Enniskerry Road, Sandyford, Dublin 18 (Phase 3) | 22 | Respond | [5 empty] | Q1-2022
2133 | CALF Construction | DLR | Enniskerry Road, Sandyford, Dublin 19 (Phase 1) | 18 | Tuath Housing Association | [5 empty] | Q4-2021
2134 | CALF Construction | DLR | Enniskerry Road, Sandyford, Dublin 19 (Phase 2) | 16 | Tuath Housing Association | [5 empty] | Q1-2022
2135 | CALF Construction | DLR | Enniskerry Road, Sandyford, Dublin 19 (Phase 3) | 18 | Tuath Housing Association | [5 empty] | Q1-2022
2136 | CALF Turnkey | DLR | Johnstown Place,Johnstown Road, Cabinteely, Dublin 18 (Formerly Johnstown Court) (Phase 1)* | 51 | Clúid Housing | [5 empty] | Q2-2021
2137 | CALF Turnkey | DLR | Kiln View, Clay Farm Place (formerly Way), Leopardstown, Co Dublin (Phase 1)* | 55 | The Iveagh Trust | [5 empty] | Q3-2023
2138 | CALF Turnkey | DLR | Lisieux Manor, Murphystown Road, Leopardstown, Dublin 18 (Phase 1)* | 133 | Respond |  |  |  |  | Q4-2022
2139 | CALF Construction | DLR | Loughlinstown View(formerly Cromlech Fields) Loughlinstown, Ballybrack, Dublin (Phase 1) | 34 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2024
2140 | CALF Turnkey | DLR | Mount Eagle, Kilgobbin Road, Sandyford, Dublin 18 (Phase 1)* | 14 | Tuath Housing Association | [5 empty] | Q1-2021
2141 | CALF Turnkey | DLR | Mount Eagle, Kilgobbin Road, Sandyford, Dublin 18 (Phase 2)* | 18 | Tuath Housing Association | [5 empty] | Q2-2021
2142 | CALF Turnkey | DLR | Oakton Court, Ballybrack, Co. Dublin (Phase 1) | 5 | Circle Voluntary Housing Association CLG | [5 empty] | Q4-2022
2143 | CALF Turnkey | DLR | Phase 2, Elmwood, Johnstown Road, Cabinteely, Dun Laoghaire, Co. Dublin (Phase 1)* | 58 | Clúid Housing | [5 empty] | Q1-2022
2144 | CALF Turnkey | DLR | Saint Germaine, Killiney, Co Dublin (Phase 1)* | 31 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2145 | CALF Turnkey | DLR | St Helen's Court, Dun Laoghaire, Co. Dublin (Phase 1) | 18 | Focus Housing Association CLG |  |  |  |  | Q1-2023
2146 | CALF Turnkey | DLR | Sussex Street, Dún Laoghaire, Co. Dublin (Phase 1)* | 10 | Sophia Housing Association Ltd |  |  |  |  | Q2-2023
2147 | CALF Turnkey | DLR | The Glen, Glenamuck Road, Carrickmines, Dublin 18 (Phase 1)* | 48 | Respond |  |  |  |  | Q1-2021
2148 | CALF Turnkey | DLR | Whinsfield, Sandyford Road, Dublin 18 (Phase 1) | 30 | Respond |  |  |  |  | Q3-2020
2149 | CALF Turnkey | DLR | Whinsfield, Sandyford Road, Dublin 18 (Phase 1)* | 3 | Respond |  |  |  |  | Q3-2020
2150 | CALF Turnkey | DLR | Whinsfield, Sandyford Road, Dublin 18 (Phase 2) | 29 | Respond |  |  |  |  | Q3-2020
2151 | CALF Turnkey | DLR | Whinsfield, Sandyford Road, Dublin 18 (Phase 2)* | 3 | Respond |  |  |  |  | Q3-2020
2152 | CALF Turnkey | DLR | Willow House, Kiltiernan Wood, Bishop’s Gate, Enniskerry Road, Kiltiernan, Dublin 18 (formerly Willow House, Bishop’s Gate, Kiltiernan, Enniskerry Road, Dublin 18) (Phase 1)* | 22 | Tuath Housing Association | [5 empty] | Q3-2023
2153 | CALF Turnkey | Donegal | Ard na Gréine, Glencar Scotch, Letterkenny, Co. Donegal (Phase 1) | 12 | Clúid Housing | [5 empty] | Q3-2023
2154 | CALF Turnkey | Donegal | Ard na Gréine, Glencar Scotch, Letterkenny, Co. Donegal (Phase 2)* | 6 | Clúid Housing | [5 empty] | Q4-2023
2155 | CALF Turnkey | Donegal | Ardán Rua, Killylastin, Letterkenny, Co Donegal, (Phase 1) | 25 | Clúid Housing |  |  |  |  | Q4-2023
2156 | CALF Turnkey | Donegal | Ardán Rua, Killylastin, Letterkenny, Co Donegal, (Phase 2) | 22 | Clúid Housing |  |  |  |  | Q4-2023
2157 | CALF Turnkey | Donegal | Ardán Rua, Killylastin, Letterkenny, Co Donegal, (Phase 3) | 28 | Clúid Housing |  |  |  |  | Q4-2023
2158 | CALF Turnkey | Donegal | Ardán Rua, Killylastin, Letterkenny, Co Donegal, (Phase 4) | 25 | Clúid Housing |  |  |  |  | Q4-2023
2159 | CALF Turnkey | Donegal | Ballaghderg, Letterkenny, Co Donegal (Phase 1)* | 33 | Respond | [5 empty] | Q1-2021
2160 | CALF Turnkey | Donegal | Cnoc Móinéir, Ardrawer, Letterkenny, Co. Donegal (Phase 1)* | 14 | Clúid Housing |  |  |  |  | Q2-2018
2161 | CALF Turnkey | Dublin City | 25-27 Bow Lane West, Dublin 8 (Phase 1) | 27 | Focus Housing Association CLG |  |  |  |  | Q4-2023
2162 | CALF Turnkey | Dublin City | 3 Camac Park, Bluebell, Dublin 12 (Phase 1) | 4 | Simon Community: Dublin Simon |  |  |  |  | Q2-2024
2163 | CALF Turnkey | Dublin City | 3 units, McAuley Ave and Lein Road, Artane, Dublin 5 (Phase 1) | 3 | iCare Housing CLG | [5 empty] | Q2-2023
2164 | CALF Turnkey | Dublin City | 344 South Circular Road, Dublin 8 (Phase 1) | 4 | Depaul Housing |  |  |  |  | Q3-2023
2165 | CALF Turnkey | Dublin City | 75 Old Cabra Road, Dublin 7 (Phase 1) | 6 | Circle Voluntary Housing Association CLG | [5 empty] | Q4-2022
2166 | CALF Turnkey | Dublin City | 80 Phillipsburgh Avenue, Fairview, Dublin 3 (Phase 1) | 42 | Cabhru Housing Association Services |  |  |  | Q2-2024
2167 | CALF Turnkey | Dublin City | 92A Prussia Street, Dublin 7 (Phase 1) | 5 | Focus Housing Association CLG | [5 empty] | Q2-2024
2168 | CALF Turnkey | Dublin City | Aughrim Street, Stoneybatter, Dublin 7 (Phase 1) | 4 | Clanmil Housing Association Ireland | [5 empty] | Q2-2021
2169 | CALF Turnkey | Dublin City | Belvedere Court, Dublin 1 (Phase 1) | 13 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2170 | CALF Construction | Dublin City | Bethany House, Gilford Road, Sandymount, Dublin 4 (Phase 1) | 62 | Clúid Housing |  |  |  |  | Q4-2021
2171 | CALF Turnkey | Dublin City | Blackbanks View, 754 Howth Road, Raheny, Dublin (Phase 1)* | 40 | Clúid Housing | [5 empty] | Q1-2021
2172 | CALF Construction | Dublin City | Blackbird Park, Rathoath Road, Cabra, Dublin 7 (Phase 1) | 95 | Focus Housing Association CLG |  |  |  | Q2-2024
2173 | CALF Turnkey | Dublin City | Block 1, Parkside, Dublin 13 (Phase 1) | 122 | Clúid Housing |  |  |  |  | Q1-2023
2174 | CALF Turnkey | Dublin City | Block 2, Parkside, Dublin 13 (Phase 1) | 173 | Clúid Housing |  |  |  |  | Q3-2023
2175 | CALF Turnkey | Dublin City | Block 4, Parkside, Dublin 13 (Phase 1)* | 67 | Clúid Housing | [5 empty] | Q4-2023
2176 | CALF Turnkey | Dublin City | Block 5 Castleview, Naas Rd, Dublin 12 (formerly Carriglea, Naas Rd, Drimnagh, Dublin 12) (Phase 1)* | 38 | The Iveagh Trust | [5 empty] | Q3-2024
2177 | CALF Turnkey | Dublin City | Bluebell Avenue, Bluebell, Dublin 12 (Phase 1)* | 52 | Respond | [5 empty] | Q2-2022
2178 | CALF Turnkey | Dublin City | Camac Park, Bluebell, Dublin 12 (Phase 1) | 3 | Tuath Housing Association | [5 empty] | Q4-2021
2179 | CALF Turnkey | Dublin City | Chanel Manor Apartments, Chanel College, Coolock, Dublin 5 (Phase 1)* | 65 | Respond |  |  |  |  | Q2-2019
2180 | CALF Turnkey | Dublin City | Chanel Manor Apartments, Chanel College, Coolock, Dublin 5 (Phase 1)* | 22 | Respond |  |  |  |  | Q4-2020
2181 | CALF Turnkey | Dublin City | Charlemont Gate, Griffith Avenue, Dublin 9 (Phase 1)* | 35 | Clúid Housing | [5 empty] | Q2-2022
2182 | CALF Construction | Dublin City | Charles Street House, 51 Charles Street Great, Dublin 1 (Phase 1) | 52 | Clúid Housing |  |  |  |  | Q2-2024
2183 | CALF Turnkey | Dublin City | Clonard Road, Kimmage, Dublin 12 (Phase 1) | 2 | Depaul Housing | [5 empty] | Q4-2023
2184 | CALF Turnkey | Dublin City | Clonshaugh Road, Clonshaugh, Dublin 17 (Phase 1) | 9 | North and East Housing Association CLG | [5 empty] | Q4-2022
2185 | CALF Turnkey | Dublin City | Connaught Street, Phibsborough, Dublin 7 (Phase 1) | 20 | Focus Housing Association CLG | [5 empty] | Q4-2022
2186 | CALF Turnkey | Dublin City | Donnybrook Gardens, Lands of Greenfield Park, Donnybrook, Dublin 4 (Phase 1)* | 4 | RHD Housing | [5 empty] | Q2-2021
2187 | CALF Turnkey | Dublin City | Edenmore Avenue, Edenmore Park, D5 (Phase 1) | 4 | iCare Housing CLG |  |  |  |  | Q1-2023
2188 | CALF Turnkey | Dublin City | Elanora Court, Long Mile Road, Walkinstown, Dublin 12 (Phase 1)* | 153 | Respond | [5 empty] | Q4-2023
2189 | CALF Turnkey | Dublin City | Elmville, Harolds Cross, Dublin 6 (Phase 1)* | 9 | Focus Housing Association CLG | [5 empty] | Q4-2023
2190 | CALF Turnkey | Dublin City | Griffin Court, Griffin Point, Clare Hall Avenue, D13 (Formerly Hole in the Wall Road, Clongriffin, Dublin 13) (Phase 1)* | 146 | Respond |  |  |  |  | Q4-2022
2191 | CALF Turnkey | Dublin City | Griffin Hall, Griffin Point, Clarehall Avenue, Dublin 13 (Formerly Hole in the Wall Road, Clongriffin, Dublin 13) (Phase 1)* | 98 | Respond |  |  |  |  | Q1-2024
2192 | CALF Turnkey | Dublin City | Hillside Manor, Lucan Road, Chapelizod, Dublin 20 (Phase 1)* | 30 | Clúid Housing | [5 empty] | Q2-2023
2193 | CALF Turnkey | Dublin City | Hollybrook House, 55 Naas Road, Dublin 12 (Phase 1)* | 15 | Focus Housing Association CLG |  |  |  |  | Q1-2023
2194 | CALF Turnkey | Dublin City | Lawlors Corner, Marrowbone Lane, Dublin 8 (Phase 1) | 35 | Circle Voluntary Housing Association CLG |  |  |  | Q2-2024
2195 | CALF Turnkey | Dublin City | Longboat Quay, Sir John Rogerson Quay, Dublin 2 (Phase 1)* | 15 | Tuath Housing Association | [5 empty] | Q4-2022
2196 | CALF Turnkey | Dublin City | Merville Place, Finglas, Dublin 11 (Phase 1)* | 200 | Respond |  |  |  |  | Q1-2024
2197 | CALF Construction | Dublin City | Millwood, New Millwood Court, Woodbine Road, Raheny, Dublin 5. (Phase 1) | 52 | Fold Housing Association Ireland Ltd |  |  |  |  | Q1-2024
2198 | CALF Turnkey | Dublin City | Moeran Road, Walkinstown, Dublin D12 (Phase 1) | 43 | Oaklee Housing |  |  |  | Q3-2023
2199 | CALF Turnkey | Dublin City | Newtown Cottages Malahide Road Coolock Dublin 17 (Phase 1) | 3 | Clanmil Housing Association Ireland | [5 empty] | Q4-2022
2200 | CALF Turnkey | Dublin City | North Bank, Castleforbes Road, Dublin 1 (Phase 1)* | 19 | Tuath Housing Association | [5 empty] | Q2-2023
2201 | CALF Turnkey | Dublin City | North Bank, Castleforbes Road, Dublin 1 (Phase 2)* | 6 | Tuath Housing Association | [5 empty] | Q3-2023
2202 | CALF Turnkey | Dublin City | North Bank, Castleforbes Road, Dublin 1 (Phase 3)* | 7 | Tuath Housing Association | [5 empty] | Q2-2024
2203 | CALF Turnkey | Dublin City | North Bank, Castleforbes Road, Dublin 1 (Phase 4)* | 8 | Tuath Housing Association |  |  |  |  | Q2-2020
2204 | CALF Turnkey | Dublin City | North Strand, 87 North Strand, Dublin 3 (Phase 1) | 17 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2205 | CALF Turnkey | Dublin City | O’Neill Court, Main Street, Belmayne, Dublin 13 (Phase 1)* | 50 | Tuath Housing Association |  |  |  |  | Q4-2022
2206 | CALF Turnkey | Dublin City | Oscar Traynor Road, Dublin 17 (1) (Phase 1) | 39 | Clúid Housing |  |  |  |  | Q2-2024
2207 | CALF Turnkey | Dublin City | Oscar Traynor Road, Dublin 17 (1) (Phase 2) | 80 | Clúid Housing |  |  |  |  | Q2-2024
2208 | CALF Turnkey | Dublin City | Oscar Traynor Road, Dublin 17 (1) (Phase 3) | 14 | Clúid Housing |  |  |  |  | Q2-2024
2209 | CALF Turnkey | Dublin City | Oscar Traynor Road, Dublin 17 (1) (Phase 4) | 48 | Clúid Housing |  |  |  |  | Q2-2024
2210 | CALF Turnkey | Dublin City | Oscar Traynor Road, Dublin 17 (2) (Phase 1) | 162 | Clúid Housing |  |  |  |  | Q2-2024
2211 | CALF Turnkey | Dublin City | Park West Campus, Kileen Road, Dublin 12 (Phase 1) | 43 | Tuath Housing Association | [5 empty] | Q2-2022
2212 | CALF Turnkey | Dublin City | Plunkett Hall, Hole in the Wall Road, Dublin 13 (Phase 1)* | 6 | Oaklee Housing | [5 empty] | Q3-2023
2213 | CALF Construction | Dublin City | Railway Street, Dublin 1 (Phase 1) | 47 | Circle Voluntary Housing Association CLG | [5 empty] | Q3-2024
2214 | CALF Turnkey | Dublin City | Rathborne, Ashtown, Dublin 15 (Phase 1)* | 192 | Respond |  |  |  |  | Q2-2024
2215 | CALF Turnkey | Dublin City | Rathborne, Ashtown, Dublin 15 (Phase 2)* | 134 | Respond |  |  |  |  | Q2-2024
2216 | CALF Turnkey | Dublin City | Ravensdale Court, Kimmage, Dublin 12. (Phase 1) | 12 | Tuath Housing Association | [5 empty] | Q2-2022
2217 | CALF Turnkey | Dublin City | Richmond Avenue, Dublin 3 (Phase 1) | 28 | Oaklee Housing |  |  |  |  | Q1-2024
2218 | CALF Turnkey | Dublin City | Richmond Avenue, Dublin 3 (Phase 1) | 35 | Focus Housing Association CLG |  |  |  |  | Q4-2023
2219 | CALF Turnkey | Dublin City | Rosemount Gate, 153-155 Harolds Cross Road, Dublin 6W (Phase 1) | 35 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
2220 | CALF Turnkey | Dublin City | St Canice’s Hall, Ballygall Road West, Finglas, Dublin 11 (Phase 1)* | 32 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2021
2221 | CALF Turnkey | Dublin City | St Pappin Road, Glasnevin, D11 (Phase 1) | 2 | iCare Housing CLG | [5 empty] | Q4-2023
2222 | CALF Turnkey | Dublin City | St. Margaret’s Road, Hampton Wood, Dublin 11 (Phase 1)* | 12 | Tuath Housing Association | [5 empty] | Q2-2023
2223 | CALF Turnkey | Dublin City | The Gardens, Elm Park, Dublin 4 (Phase 1)* | 22 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2024
2224 | CALF Turnkey | Dublin City | Wellington Street, Dublin 7 (Phase 1) | 24 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2024
2225 | CALF Turnkey | Fingal | 2 properties, Ballygossan Walk, Ballygossan Hill, Golf Links Road, Skerries, Co. Dublin (Phase 1) | 2 | Tuath Housing Association |  |  |  |  | Q3-2024
2226 | CALF Turnkey | Fingal | Barnewall Lane, Rathmore, Lusk, Co. Dublin (Phase 1)* | 5 | Clúid Housing |  |  |  |  | Q2-2023
2227 | CALF Turnkey | Fingal | Bellingsmore, Hollywoodrath, Dublin 15 (Phase 1)* | 17 | Tuath Housing Association | [5 empty] | Q2-2021
2228 | CALF Turnkey | Fingal | Bellingsmore, Hollywoodrath, Dublin 15 (Phase 2) | 21 | Tuath Housing Association | [5 empty] | Q4-2021
2229 | CALF Turnkey | Fingal | Beresford, Oakstown, Donabate, Co. Dublin (Phase 1)* | 36 | Tuath Housing Association | [5 empty] | Q4-2022
2230 | CALF Turnkey | Fingal | Beresford, Oakstown, Donabate, Co. Dublin (Phase 2)* | 4 | Tuath Housing Association | [5 empty] | Q2-2024
2231 | CALF Turnkey | Fingal | Blackwood Square, Northwood Avenue, Santry Dublin 9 (Phase 1)* | 33 | Tuath Housing Association | [5 empty] | Q4-2022
2232 | CALF Turnkey | Fingal | Carrs Lane, Malahide Road, Dublin 17 (Phase 1)* | 29 | Respond | [5 empty] | Q2-2021
2233 | CALF Turnkey | Fingal | Carrs Lane, Malahide Road, Dublin 17 (Phase 2)* | 30 | Respond | [5 empty] | Q4-2021
2234 | CALF Turnkey | Fingal | Castleland Park, Castleland, Balbriggan, Co. Dublin. (Phase 1) | 23 | Tuath Housing Association | [5 empty] | Q4-2022
2235 | CALF Turnkey | Fingal | Chapel Hill, Chapel Lane, Garristown, Co. Dublin (Phase 1)* | 2 | Clanmil Housing Association Ireland | [5 empty] | Q4-2022
2236 | CALF Turnkey | Fingal | Charlestown Centre, Charlestown Place & St., Margarets Road, Dublin 11 (Phase 1)* | 90 | Respond | [5 empty] | Q4-2021
2237 | CALF Turnkey | Fingal | Charlestown Centre, Charlestown Place & St., Margarets Road, Dublin 11 (Phase 2)* | 48 | Respond | [5 empty] | Q4-2021
2238 | CALF Turnkey | Fingal | Clonross, Navan Road, Blanchardstown, Dublin 15 (Phase 1)* | 26 | Clúid Housing | [5 empty] | Q4-2023
2239 | CALF Turnkey | Fingal | Clonsilla Grove Apartments, Clonsilla Road, Clonsilla, Dublin 15 (Phase 1) | 12 | Respond |  |  |  |  | Q4-2021
2240 | CALF Turnkey | Fingal | Cobbe Court, Portrane Road, Donabate, Co. Dublin (Phase 1)* | 12 | Tuath Housing Association | [5 empty] | Q4-2022
2241 | CALF Turnkey | Fingal | Drynam Heath, Feltrim Road, Swords, Co. Dublin (Phase 2)* | 6 | Tuath Housing Association | [5 empty] | Q2-2021
2242 | CALF Turnkey | Fingal | Dun Si, St Marnocks Bay, Portmarnock, Co Dublin (Phase 1)* | 18 | Clúid Housing | [5 empty] | Q2-2023
2243 | CALF Turnkey | Fingal | Folkstown Park, Balbriggan, Co. Dublin (Phase 1) | 5 | Tuath Housing Association |  |  |  |  | Q1-2024
2244 | CALF Turnkey | Fingal | Folkstown Park, Balbriggan, Co. Dublin (Phase 2) | 23 | Tuath Housing Association |  |  |  |  | Q1-2024
2245 | CALF Turnkey | Fingal | Folkstown Park, Balbriggan, Co. Dublin (Phase 3) | 22 | Tuath Housing Association |  |  |  |  | Q1-2024
2246 | CALF Turnkey | Fingal | Hansfield Station Quarter, Hansfield, Dublin 15 (Phase 1) | 23 | Fold Housing Association Ireland Ltd | [5 empty] | Q4-2023
2247 | CALF Turnkey | Fingal | Hansfield Station Quarter, Hansfield, Dublin 15 (Phase 2) | 38 | Fold Housing Association Ireland Ltd | [5 empty] | Q4-2023
2248 | CALF Turnkey | Fingal | Hansfield Station Quarter, Hansfield, Dublin 15 (Phase 3) | 38 | Fold Housing Association Ireland Ltd | [5 empty] | Q4-2023
2249 | CALF Turnkey | Fingal | Hansfield Station Quarter, Hansfield, Dublin 15 (Phase 4) | 34 | Fold Housing Association Ireland Ltd | [5 empty] | Q4-2023
2250 | CALF Turnkey | Fingal | Hansfield View, 7 Hansfield Square, Hansfield, Dublin 15. (formerly Station View, Station Road, Dublin 15) (Phase 1)* | 22 | Tuath Housing Association | [5 empty] | Q4-2022
2251 | CALF Turnkey | Fingal | Harmans Rest, Turvey Avenue, Donabate, Co. Dublin (Phase 1)* | 44 | Oaklee Housing |  |  |  |  | Q2-2024
2252 | CALF Turnkey | Fingal | Hollyfield, Mulhuddart, Dublin 15 (Phase 1) | 18 | Clúid Housing |  |  |  |  | Q3-2023
2253 | CALF Turnkey | Fingal | Hollyfield, Mulhuddart, Dublin 15 (Phase 2)* | 22 | Clúid Housing |  |  |  |  | Q3-2023
2254 | CALF Turnkey | Fingal | Kilmartin Grove, Hollystown, Dublin 15 (Phase 1) | 9 | Tuath Housing Association | [5 empty] | Q3-2024
2255 | CALF Turnkey | Fingal | Kilmartin Grove, Hollystown, Dublin 15 (Phase 2) | 3 | Tuath Housing Association |  |  |  |  | Q3-2023
2256 | CALF Turnkey | Fingal | Kilmartin Grove, Hollystown, Dublin 15 (Phase 3) | 9 | Tuath Housing Association |  |  |  |  | Q3-2023
2257 | CALF Construction | Fingal | Ladyswell Road & Church Road, Mulhuddart, Dublin 15 (Phase 1) | 65 | Clúid Housing | [5 empty] | Q4-2021
2258 | CALF Turnkey | Fingal | Lanestown View (formerly Ballymastone), Donabate, County Dublin (Phase 1)* | 43 | Circle Voluntary Housing Association CLG | [5 empty] | Q3-2023
2259 | CALF Turnkey | Fingal | Lusk Village Quarter, Lusk, Co. Dublin (Phase 1)* | 14 | Clúid Housing | [5 empty] | Q4-2023
2260 | CALF Turnkey | Fingal | Lusk Village, Lusk, Co. Dublin, Phase 2 (Phase 1)* | 14 | Clúid Housing | [5 empty] | Q4-2021
2261 | CALF Turnkey | Fingal | Lusk Village, Lusk, Co. Dublin, Phase 2 (Phase 2)* | 4 | Clúid Housing | [5 empty] | Q3-2022
2262 | CALF Turnkey | Fingal | Mariners Way, Rush, Co. Dublin (Phase 1)* | 6 | Respond | [5 empty] | Q4-2023
2263 | CALF Turnkey | Fingal | Mariners Way, Rush, Co. Dublin (Phase 2)* | 9 | Respond |  |  |  |  | Q1-2020
2264 | CALF Construction | Fingal | Old Coolock Lane, Santry, Dublin 9 (Phase 1) | 28 | Circle Voluntary Housing Association CLG |  |  |  | Q1-2019
2265 | CALF Turnkey | Fingal | Old Corduff Road, Blanchardstown, Dublin (Phase 2)* | 10 | Respond | [5 empty] | Q2-2021
2266 | CALF Turnkey | Fingal | Oldtown, Swords, Co Dublin (Phase 1) | 30 | Respond |  |  |  |  | Q3-2022
2267 | CALF Turnkey | Fingal | Oldtown, Swords, Co Dublin (Phase 2) | 30 | Respond |  |  |  |  | Q3-2022
2268 | CALF Turnkey | Fingal | Oldtown, Swords, Co Dublin (Phase 3) | 39 | Respond |  |  |  |  | Q3-2022
2269 | CALF Turnkey | Fingal | Part 3, Kilmartin Grove, Hollystown, Dublin 15 (Phase 1) | 25 | Tuath Housing Association |  |  |  |  | Q1-2024
2270 | CALF Turnkey | Fingal | Part 3, Kilmartin Grove, Hollystown, Dublin 15 (Phase 2) | 32 | Tuath Housing Association |  |  |  |  | Q1-2024
2271 | CALF Turnkey | Fingal | Part 3, Kilmartin Grove, Hollystown, Dublin 15 (Phase 3) | 32 | Tuath Housing Association |  |  |  |  | Q1-2024
2272 | CALF Turnkey | Fingal | Pipers Square, Charlestown Place, Dublin 11 (Phase 1)* | 211 | Respond |  |  |  |  | Q4-2023
2273 | CALF Turnkey | Fingal | Pipers Square, Charlestown Place, Dublin 11 (Phase 2) | 95 | Respond |  |  |  |  | Q4-2023
2274 | CALF Turnkey | Fingal | Ravens Mill, Church Road, Rowlestown, Co. Dublin (Phase 1)* | 38 | Tuath Housing Association | [5 empty] | Q4-2022
2275 | CALF Turnkey | Fingal | Riverwood Square, Porterstown, Dublin 15 (Phase 1)* | 24 | Clúid Housing | [5 empty] | Q3-2021
2276 | CALF Turnkey | Fingal | Semple Woods, Donabate, Co. Dublin (Phase 1)* | 8 | Tuath Housing Association | [5 empty] | Q4-2023
2277 | CALF Turnkey | Fingal | Semple Woods, Donabate, Co. Dublin (Phase 2)* | 3 | Tuath Housing Association |  |  |  |  | Q4-2019
2278 | CALF Turnkey | Fingal | St Josephs, Clonsilla, Dublin 15 (Phase 1)* | 28 | Clúid Housing | [5 empty] | Q4-2021
2279 | CALF Turnkey | Fingal | Station Manor, Station Road, Portmarnock, Co. Dublin (Phase 2)* | 8 | Circle Voluntary Housing Association CLG | [5 empty] | Q4-2021
2280 | CALF Turnkey | Fingal | Taylor Hill, Balbriggan, Co. Dublin (Phase 1)* | 7 | Clúid Housing | [5 empty] | Q4-2021
2281 | CALF Turnkey | Fingal | The Coast, Stapolin, Baldoyle, Dublin 13 (Phase 1)* | 29 | Respond | [5 empty] | Q4-2023
2282 | CALF Turnkey | Fingal | The Paddocks, Ballygossan Hill (Phase 1)* | 95 | Tuath Housing Association |  |  |  |  | Q3-2023
2283 | CALF Turnkey | Fingal | Whitehaven, Northwood Avenue, Santry, Dublin 9 (Phase 1) | 47 | Tuath Housing Association |  |  |  |  | Q1-2024
2284 | CALF Turnkey | Fingal | Whitehaven, Northwood Avenue, Santry, Dublin 9 (Phase 2) | 47 | Tuath Housing Association |  |  |  |  | Q1-2024
2285 | CALF Turnkey | Galway City | Ballybanemor Road, Ballybrit, Galway (Phase 1)* | 28 | Respond | [5 empty] | Q4-2023
2286 | CALF Turnkey | Galway City | Ballybanemor Road, Ballybrit, Galway (Phase 2)* | 61 | Respond | [5 empty] | Q4-2023
2287 | CALF Turnkey | Galway City | Ballybanemor Road, Ballybrit, Galway (Phase 3) | 12 | Respond | [5 empty] | Q4-2023
2288 | CALF Turnkey | Galway City | Briar Hill, Old Monivea Road, Ballybrit, Galway (Phase 1) | 7 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2022
2289 | CALF Turnkey | Galway City | Claí Mór, Old Monivea Road, Ballybrit, Galway City (Phase 1)* | 41 | Tuath Housing Association |  |  |  |  | Q4-2023
2290 | CALF Turnkey | Galway City | Cnoc Rathuin Apartments, Nijella, Mincloon, Rahoon, Galway City (Phase 1)* | 13 | Tuath Housing Association |  |  |  |  | Q3-2023
2291 | CALF Turnkey | Galway City | Creig Ard, Roscam, Galway City (Phase 2) | 10 | Clúid Housing | [5 empty] | Q2-2021
2292 | CALF Turnkey | Galway City | Creig Ard, Roscam, Galway City, Co. Galway (Phase 1)* | 17 | Clúid Housing | [5 empty] | Q4-2021
2293 | CALF Turnkey | Galway City | Cuirt Bhoirne, Roscam, Co Galway (Phase 1)* | 12 | Clúid Housing | [5 empty] | Q4-2022
2294 | CALF Turnkey | Galway City | Fanan, Letteragh Road, Galway (Phase 1)* | 4 | Tuath Housing Association | [5 empty] | Q4-2021
2295 | CALF Turnkey | Galway City | Fanan, Letteragh Road, Galway (Phase 2)* | 3 | Tuath Housing Association | [5 empty] | Q3-2022
2296 | CALF Turnkey | Galway City | Fanan, Letteragh Road, Galway (Phase 3)* | 3 | Tuath Housing Association | [5 empty] | Q4-2022
2297 | CALF Turnkey | Galway City | Gaelcarrig, Letteragh, Galway City (Phase 1)* | 83 | Respond | [5 empty] | Q4-2022
2298 | CALF Turnkey | Galway City | Garrai Sheain, Roscam, Galway (Phase 1) | 9 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2299 | CALF Turnkey | Galway City | Gleann Na Mona, Knocknacarra, Galway (Phase 1)* | 16 | Clúid Housing | [5 empty] | Q4-2022
2300 | CALF Turnkey | Galway City | Letteragh Road, Rahoon, Galway City (Phase 1)* | 10 | Clúid Housing | [5 empty] | Q3-2021
2301 | CALF Turnkey | Galway City | Letteragh Road, Rahoon, Galway City (Phase 2) | 13 | Clúid Housing | [5 empty] | Q4-2021
2302 | CALF Turnkey | Galway City | Phase 3 and 4 Cnocan Glas, Letteragh Road, Rahoon, Galway City (Phase 1)* | 16 | Clúid Housing | [5 empty] | Q2-2023
2303 | CALF Turnkey | Galway City | Phase 3 and 4 Cnocan Glas, Letteragh Road, Rahoon, Galway City (Phase 2)* | 23 | Clúid Housing | [5 empty] | Q3-2024
2304 | CALF Turnkey | Galway County | Cuil na Canalach, Ballinasloe, Co Galway (Phase 1) | 7 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2305 | CALF Turnkey | Galway County | Cúlán Eiscir Riada (formely Cuirt Dun Leo), Dunlo, Ballinasloe, Co Galway (Phase 1) | 24 | Clúid Housing | [5 empty] | Q4-2023
2306 | CALF Turnkey | Galway County | Cúlán Eiscir Riada (formely Cuirt Dun Leo), Dunlo, Ballinasloe, Co Galway (Phase 2) | 14 | Clúid Housing | [5 empty] | Q4-2023
2307 | CALF Turnkey | Galway County | Gort na Fuinse, Headford, Co. Galway (Phase 1)* | 11 | Clúid Housing | [5 empty] | Q4-2022
2308 | CALF Turnkey | Galway County | Gort na Fuinse, Headford, Co. Galway (Phase 2) | 14 | Clúid Housing | [5 empty] | Q1-2023
2309 | CALF Turnkey | Galway County | Plás an Chruichéid, Cricket Place, Dunmore Road, Tuam, Co Galway (Phase 1)* | 8 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2023
2310 | CALF Turnkey | Galway County | Rivercrest, Tuam, Co Galway (Phase 1)* | 17 | Tuath Housing Association | [5 empty] | Q4-2023
2311 | CALF Turnkey | Galway County | Riveroaks, Claregalway, Co Galway (Phase 2) | 12 | Clúid Housing | [5 empty] | Q1-2021
2312 | CALF Turnkey | Galway County | Riveroaks, Claregalway, Co Galway (Phase 3)* | 16 | Clúid Housing | [5 empty] | Q2-2021
2313 | CALF Turnkey | Galway County | Sliabh Carran, Ennis Road, Gort, Co. Galway (Phase 1) | 9 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2024
2314 | CALF Turnkey | Galway County | St. Laurencefields, (13 Properties) Cottage Hill, Loughrea, Co. Galway (Phase 1)* | 13 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
2315 | CALF Turnkey | Galway County | The Old Mill House, Milltown, Co Galway (Phase 1) | 7 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2021
2316 | CALF Turnkey | Galway County | Vicars Choral, Tuam, Co Galway (Phase 1) | 9 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2317 | CALF Turnkey | Galway County | Vicars Choral, Tuam, Co Galway (Phase 1) | 7 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2023
2318 | CALF Turnkey | Galway County | Vicars Choral, Tuam, Co Galway (Phase 2)* | 4 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2023
2319 | CALF Turnkey | Galway County | Vicars Choral, Tuam, Co Galway (Phase 3)* | 11 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2320 | CALF Turnkey | Galway County | Woodfield, Tuam, Co. Galway (Phase 1) | 6 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q4-2023
2321 | CALF Turnkey | Kerry | 31 Focus Units, Riverside, Killarney Road, Castleisland, Co Kerry (Phase 1) | 15 | Focus Housing Association CLG | [5 empty] | Q3-2023
2322 | CALF Turnkey | Kerry | 31 Focus Units, Riverside, Killarney Road, Castleisland, Co Kerry (Phase 2)* | 12 | Focus Housing Association CLG | [5 empty] | Q4-2023
2323 | CALF Turnkey | Kerry | 31 Focus Units, Riverside, Killarney Road, Castleisland, Co Kerry (Phase 3) | 4 | Focus Housing Association CLG | [5 empty] | Q1-2024
2324 | CALF Turnkey | Kerry | 36 Co-Operative Housing Units, Riverside, Killarney Road, Castleisland, Co Kerry (Phase 1)* | 16 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2023
2325 | CALF Turnkey | Kerry | 36 Co-Operative Housing Units, Riverside, Killarney Road, Castleisland, Co Kerry (Phase 2) | 16 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2326 | CALF Turnkey | Kerry | 36 Co-Operative Housing Units, Riverside, Killarney Road, Castleisland, Co Kerry (Phase 3) | 4 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q1-2024
2327 | CALF Turnkey | Kerry | Ard Na Greine, Knockavota, Milltown, Co. Kerry (Phase 1) | 28 | Clúid Housing | [5 empty] | Q3-2022
2328 | CALF Turnkey | Kerry | Ard Na Greine, Knockavota, Milltown, Co. Kerry (Phase 2)* | 26 | Clúid Housing | [5 empty] | Q4-2022
2329 | CALF Turnkey | Kerry | Barraduff Phase 6, Killarney, Co Kerry (Phase 1) | 9 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2023
2330 | CALF Turnkey | Kerry | Barraduff Phase 6, Killarney, Co Kerry (Phase 2)* | 16 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2023
2331 | CALF Turnkey | Kerry | Barraduff Phase 6E, Killarney, Co Kerry (Phase 1) | 13 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2332 | CALF Turnkey | Kerry | Barraduff, Killarney, Co Kerry (Phase 1)* | 3 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2022
2333 | CALF Turnkey | Kerry | Barraduff, Killarney, Co. Kerry (Phase 4)* | 13 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q1-2021
2334 | CALF Construction | Kerry | Bypass Road, Killarney, Co Kerry (Phase 1) | 67 | Focus Housing Association CLG |  |  |  | Q3-2024
2335 | CALF Turnkey | Kerry | Cahirdown Wood, Listowel, Co. Kerry - Phase 4 (Phase 1) | 13 | Clúid Housing |  |  |  | Q2-2024
2336 | CALF Turnkey | Kerry | Cahirdown Wood, Listowel, Co. Kerry (Phase 1)* | 12 | Clúid Housing | [5 empty] | Q3-2022
2337 | CALF Turnkey | Kerry | Cahirdown Wood, Listowel, Co. Kerry (Phase 2) | 10 | Clúid Housing | [5 empty] | Q3-2023
2338 | CALF Turnkey | Kerry | Cahirdown Wood, Listowel, Co. Kerry (Phase 3) | 16 | Clúid Housing | [5 empty] | Q4-2023
2339 | CALF Turnkey | Kerry | Cashen Court, Dun Alainn, Listowel, Co Kerry (Phase 1) | 39 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2021
2340 | CALF Turnkey | Kerry | Cherry Drive, Ard Na Greine, Knockavota, Milltown, Co Kerry (Phase 1)* | 44 | Clúid Housing |  |  |  |  | Q1-2023
2341 | CALF Turnkey | Kerry | Cronin's Wood, Upper Park Road, Killarney, Kerry (Phase 1)* | 54 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2024
2342 | CALF Turnkey | Kerry | Cronin's Wood, Upper Park Road, Killarney, Kerry (Phase 2)* | 49 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2024
2343 | CALF Turnkey | Kerry | Cronin's Wood, Upper Park Road, Killarney, Kerry (Phase 3)* | 46 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2024
2344 | CALF Turnkey | Kerry | Cronin's Wood, Upper Park Road, Killarney, Kerry (Phase 4) | 40 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2024
2345 | CALF Turnkey | Kerry | Cronin's Wood, Upper Park Road, Killarney, Kerry (Phase 5) | 36 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2024
2346 | CALF Turnkey | Kerry | Cronin's Wood, Upper Park Road, Killarney, Kerry (Phase 6) | 24 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2024
2347 | CALF Turnkey | Kerry | Dun Alainn, Listowel, Co. Kerry (Phase 1)* | 10 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2022
2348 | CALF Turnkey | Kerry | Dun Ard, Doon Road, Ballybunnion, Co Kerry (Phase 4) | 1 | Respond | [5 empty] | Q2-2021
2349 | CALF Turnkey | Kerry | Lawlors Hill, (formerly Commons East) Ardfert, Co. Kerry (Phase 1)* | 12 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2021
2350 | CALF Turnkey | Kerry | Lawlors Hill, (formerly Commons East) Ardfert, Co. Kerry (Phase 2) | 8 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2021
2351 | CALF Turnkey | Kerry | Lawlors Hill, (formerly Commons East) Ardfert, Co. Kerry (Phase 3) | 10 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2022
2352 | CALF Turnkey | Kerry | Lawlors Hill, Station Road Ardfert, Co Kerry (Phase 1)* | 20 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
2353 | CALF Turnkey | Kerry | Lawlors Hill, Station Road, Ardfert, Co Kerry (Phase 1)* | 20 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2023
2354 | CALF Turnkey | Kerry | Lios Ard, Lisloose, Tralee, Co. Kerry (Phase 1) | 28 | Clúid Housing | [5 empty] | Q3-2021
2355 | CALF Turnkey | Kerry | Moanmore, Pound Road, Castleisland, Co. Kerry (Phase 1)* | 14 | Clúid Housing | [5 empty] | Q4-2021
2356 | CALF Turnkey | Kerry | Orglan Heights, Ardmoneel, Killorglin, Co. Kerry (Phase 1)* | 30 | Clúid Housing |  |  |  |  | Q2-2023
2357 | CALF Turnkey | Kildare | 1 unit, Loughlion Green, Kildare Town (Phase 1) | 1 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2021
2358 | CALF Turnkey | Kildare | 15 units, Ledwill Park, Kilcock, Co. Kildare (Phase 1) | 15 | Clúid Housing | [5 empty] | Q4-2021
2359 | CALF Turnkey | Kildare | 2 units, Ledwill Park, Kilcock, Co. Kildare (Phase 1) | 2 | Clúid Housing | [5 empty] | Q4-2021
2360 | CALF Turnkey | Kildare | 3 Properties at Kilheale Park and 9 Properties at Kilheale Heath, Kilheale Manor, Hartwell Road Kill Co Kildare (Phase 1)* | 12 | Oaklee Housing | [5 empty] | Q2-2024
2361 | CALF Turnkey | Kildare | Ardrath, Celbridge, Co Kildare (Phase 1) | 44 | Clúid Housing | [5 empty] | Q4-2023
2362 | CALF Turnkey | Kildare | Baille Park, Old Dublin Road, Celbridge, Co. Kildare (Phase 1) | 6 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2023
2363 | CALF Turnkey | Kildare | Belin Woods, Newbridge, Co. Kildare (Phase 1)* | 13 | Tuath Housing Association | [5 empty] | Q4-2022
2364 | CALF Turnkey | Kildare | Belin Woods, Newbridge, Co. Kildare (Phase 2)* | 21 | Tuath Housing Association | [5 empty] | Q4-2022
2365 | CALF Turnkey | Kildare | Block 3, Rathvoy Park, Devoy, Naas, Co. Kildare (Phase 1) | 30 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2366 | CALF Turnkey | Kildare | Block 4, Rathvoy Park, Devoy, Naas, Co.Kildare (Phase 1)* | 24 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2023
2367 | CALF Turnkey | Kildare | Broadhook Street, Magee Quarter, Co. Kildare (Phase 1)* | 8 | Clúid Housing |  |  |  |  | Q1-2023
2368 | CALF Construction | Kildare | Castlefen, Castlesize, Sallins, Co. Kildare (Phase 1) | 29 | Tuath Housing Association | [5 empty] | Q3-2022
2369 | CALF Turnkey | Kildare | Cluain Bhearu, Athy, Co. Kildare (Phase 1) | 19 | Clúid Housing | [5 empty] | Q4-2023
2370 | CALF Turnkey | Kildare | Cluain Bhearu, Athy, Co. Kildare (Phase 2) | 20 | Clúid Housing | [5 empty] | Q1-2024
2371 | CALF Turnkey | Kildare | Elsmore Place, Whitethorn Village, Naas, Co. Kildare (Phase 1)* | 12 | Tuath Housing Association | [5 empty] | Q4-2022
2372 | CALF Turnkey | Kildare | Elsmore, Jigginstown and Oakpark, Craddockstown, Naas, Kildare (Phase 2)* | 17 | Tuath Housing Association | [5 empty] | Q4-2021
2373 | CALF Turnkey | Kildare | Ferns Woods, Monasterevin, Co Kildare (Phase 1)* | 9 | Tuath Housing Association | [5 empty] | Q2-2023
2374 | CALF Turnkey | Kildare | Ferns Woods, Monasterevin, Co Kildare (Phase 2)* | 2 | Tuath Housing Association | [5 empty] | Q1-2024
2375 | CALF Construction | Kildare | Flinters Field, Athy, Co. Kildare (Phase 1) | 27 | Respond | [5 empty] | Q2-2023
2376 | CALF Construction | Kildare | Flinters Field, Athy, Co. Kildare (Phase 2) | 8 | Respond | [5 empty] | Q2-2023
2377 | CALF Turnkey | Kildare | Friary House, Friary Rd, Naas, Co. Kildare (Phase 1) | 8 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2023
2378 | CALF Turnkey | Kildare | Grand Canal Wood, Allenwood, Co. Kildare (Phase 1)* | 21 | Clúid Housing | [5 empty] | Q1-2021
2379 | CALF Turnkey | Kildare | Grand Canal Wood, Allenwood, Co. Kildare (Phase 2) | 19 | Clúid Housing | [5 empty] | Q2-2021
2380 | CALF Turnkey | Kildare | Grey Abbey, Kildare Town, Co. Kildare (Phase 1)* | 49 | Tuath Housing Association | [5 empty] | Q4-2023
2381 | CALF Turnkey | Kildare | Grey Abbey, Kildare Town, Co. Kildare (Phase 2)* | 15 | Tuath Housing Association | [5 empty] | Q4-2023
2382 | CALF Turnkey | Kildare | Grey Abbey, Kildare Town, Co. Kildare (Phase 3)* | 6 | Tuath Housing Association | [5 empty] | Q4-2023
2383 | CALF Turnkey | Kildare | Hamilton Park, Clane Co Kildare (Phase 1)* | 3 | Respond |  |  |  |  | Q3-2022
2384 | CALF Turnkey | Kildare | Harpur Lane, Leixlip, Co. Kildare (Phase 1)* | 4 | Tuath Housing Association | [5 empty] | Q4-2023
2385 | CALF Turnkey | Kildare | Harpur Lane, Leixlip, Co. Kildare (Phase 2)* | 20 | Tuath Housing Association |  |  |  |  | Q1-2022
2386 | CALF Turnkey | Kildare | Kilbelin Abbey, Kildare, Phase 1 (Phase 1)* | 4 | Clúid Housing | [5 empty] | Q1-2021
2387 | CALF Turnkey | Kildare | Kilbelin Abbey, Kildare, Phase 2 (Phase 1)* | 4 | Clúid Housing | [5 empty] | Q2-2023
2388 | CALF Turnkey | Kildare | Ledwill Park, Kilcock, Co. Kildare (Phase 1)* | 27 | Clúid Housing | [5 empty] | Q3-2021
2389 | CALF Turnkey | Kildare | Ledwill Park, Kilcock, Co. Kildare (Phase 1)* | 3 | Clúid Housing | [5 empty] | Q4-2021
2390 | CALF Turnkey | Kildare | Ledwill Park, Kilcock, Co. Kildare (Phase 1)* | 20 | Clúid Housing | [5 empty] | Q4-2022
2391 | CALF Turnkey | Kildare | Leinster Square, Dublin Street, Kildare Town, Co Kildare (Phase 1)* | 4 | Clanmil Housing Association Ireland | [5 empty] | Q3-2021
2392 | CALF Turnkey | Kildare | Linden Demense, Maynooth, Co. Kildare (Phase 1) | 47 | Tuath Housing Association | [5 empty] | Q3-2023
2393 | CALF Turnkey | Kildare | Linden Demense, Maynooth, Co. Kildare (Phase 2)* | 8 | Tuath Housing Association | [5 empty] | Q3-2023
2394 | CALF Turnkey | Kildare | Linden Demense, Maynooth, Co. Kildare (Phase 3)* | 31 | Tuath Housing Association | [5 empty] | Q4-2023
2395 | CALF Turnkey | Kildare | Loughlion, Kildare Town, Kildare (Phase 3)* | 16 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q1-2021
2396 | CALF Turnkey | Kildare | Loughlion, Kildare Town, Kildare (Phase 4) | 16 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2021
2397 | CALF Turnkey | Kildare | Loughlion, Kildare Town, Kildare (Phase 5)* | 16 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2021
2398 | CALF Turnkey | Kildare | Main Street, Prosperous, Clane, Co. Kildare (Phase 1)* | 16 | Clanmil Housing Association Ireland |  |  |  |  | Q4-2020
2399 | CALF Turnkey | Kildare | Mariavilla, Maynooth, Co. Kildare (Phase 1)* | 11 | Tuath Housing Association | [5 empty] | Q4-2021
2400 | CALF Turnkey | Kildare | Mullen Park and Carton Grove, Maynooth, Co. Kildare (Phase )* | 2 | Tuath Housing Association |  |  |  |  | Q4-2019
2401 | CALF Turnkey | Kildare | Mullen Park and Carton Grove, Maynooth, Co. Kildare (Phase 1)* | 15 | Tuath Housing Association | [5 empty] | Q4-2022
2402 | CALF Turnkey | Kildare | Mullen Park and Carton Grove, Maynooth, Co. Kildare (Phase 2)* | 10 | Tuath Housing Association |  |  |  |  | Q4-2019
2403 | CALF Turnkey | Kildare | Newbridge Road, Naas, Co. Kildare (Phase 1) | 4 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2023
2404 | CALF Turnkey | Kildare | Newtown, Kill, Co. Kildare (Phase 1)* | 3 | Tuath Housing Association | [5 empty] | Q3-2023
2405 | CALF Turnkey | Kildare | Newtown, Kill, Co. Kildare (Phase 2)* | 10 | Tuath Housing Association | [5 empty] | Q4-2023
2406 | CALF Turnkey | Kildare | Newtown, Kill, Co. Kildare (Phase 3)* | 2 | Tuath Housing Association | [5 empty] | Q2-2024
2407 | CALF Turnkey | Kildare | Oak Park, Naas, Co. Kildare (Phase 1) | 26 | Tuath Housing Association | [5 empty] | Q4-2022
2408 | CALF Turnkey | Kildare | Páirc na Manach (Phase 4), Newbridge, Co. Kildare (Phase 1)* | 27 | Clúid Housing |  |  |  |  | Q3-2023
2409 | CALF Turnkey | Kildare | Pairc na Manach, Ballymany, Newbridge, Co. Kildare (Phase 1) | 20 | Clúid Housing |  |  |  |  | Q3-2023
2410 | CALF Turnkey | Kildare | Pairc na Manach, Ballymany, Newbridge, Co. Kildare (Phase 2) | 27 | Clúid Housing |  |  |  |  | Q3-2023
2411 | CALF Turnkey | Kildare | Riverside Green, Riverside Manor, Kilcullen, Co. Kildare (Phase 1) | 30 | Clúid Housing | [5 empty] | Q4-2022
2412 | CALF Turnkey | Kildare | Riverside Green, Riverside Manor, Kilcullen, Co. Kildare (Phase 2)* | 34 | Clúid Housing | [5 empty] | Q4-2023
2413 | CALF Turnkey | Kildare | Steepleview, Naas Road,Newbridge,Co. Kildare. (Phase 1)* | 11 | Respond | [5 empty] | Q3-2023
2414 | CALF Turnkey | Kildare | The Court (Block A) Westfield, Green Lane, Leixlip, Co. Kildare (Phase 1)* | 20 | Respond | [5 empty] | Q4-2022
2415 | CALF Turnkey | Kildare | The Meadows, Kill, Co. Kildare (Phase 1) | 9 | Tuath Housing Association | [5 empty] | Q2-2024
2416 | CALF Turnkey | Kildare | The Paddocks, Morristown, Newbridge, Kildare (Phase 3)* | 16 | Clúid Housing | [5 empty] | Q2-2021
2417 | CALF Turnkey | Kildare | The Paddocks, Newbridge, Kildare (Phase 1) | 26 | Clúid Housing | [5 empty] | Q3-2021
2418 | CALF Turnkey | Kildare | The Paddocks, Newbridge, Kildare (Phase 2) | 33 | Clúid Housing | [5 empty] | Q4-2021
2419 | CALF Turnkey | Kildare | The Vestry, Glebelands, Athy, Co. Kildare (Phase 1)* | 18 | Respond | [5 empty] | Q2-2021
2420 | CALF Turnkey | Kildare | The Vestry, Glebelands, Athy, Co. Kildare (Phase 3) (Phase 1) | 20 | Respond | [5 empty] | Q4-2023
2421 | CALF Turnkey | Kildare | Tinnycross Park, Ballymore Eustace, Co. Kildare (Phase 1)* | 4 | Tuath Housing Association | [5 empty] | Q4-2022
2422 | CALF Turnkey | Kildare | Tinnycross Park, Ballymore Eustace, Co. Kildare (Phase 2)* | 5 | Tuath Housing Association | [5 empty] | Q4-2023
2423 | CALF Turnkey | Kildare | Walkers Gate, Kildare Town, Co. Kildare (Phase 1)* | 10 | Tuath Housing Association | [5 empty] | Q4-2022
2424 | CALF Turnkey | Kildare | Walkers Gate, Kildare Town, Co. Kildare (Phase 2)* | 7 | Tuath Housing Association | [5 empty] | Q2-2023
2425 | CALF Turnkey | Kildare | Walkers Gate, Kildare Town, Co. Kildare (Phase 3)* | 23 | Tuath Housing Association | [5 empty] | Q2-2023
2426 | CALF Turnkey | Kildare | Westfield, Leixlip, Co. Kildare (Phase 1)* | 20 | Respond | [5 empty] | Q4-2021
2427 | CALF Turnkey | Kildare | Whitethorn, Naas, Co. Kildare (Phase 1)* | 12 | Tuath Housing Association | [5 empty] | Q4-2021
2428 | CALF Turnkey | Kildare | Whitethorn, Naas, Co. Kildare (Phase 2)* | 4 | Tuath Housing Association | [5 empty] | Q4-2021
2429 | CALF Turnkey | Kildare | Whitethorn, Naas, Co. Kildare (Phase 3)* | 4 | Tuath Housing Association | [5 empty] | Q3-2022
2430 | CALF Turnkey | Kilkenny | 22 Units (Phase 3) Nuncio Road, Kilkenny (Phase 1) | 22 | Respond | [5 empty] | Q4-2023
2431 | CALF Turnkey | Kilkenny | 4 Units in Barrack Street, Goresbridge, (formerly Gorsebridge) Kilkenny (Phase 1) | 4 | Circle Voluntary Housing Association CLG |  |  |  |  | Q1-2023
2432 | CALF Turnkey | Kilkenny | Block 2, Nyne Park Close, Callan Road, Co. Kilkenny (Phase 1) | 12 | Clúid Housing | [5 empty] | Q3-2024
2433 | CALF Turnkey | Kilkenny | Chapel Lane, Kilkenny (Phase 1) | 5 | Focus Housing Association CLG |  |  |  |  | Q1-2022
2434 | CALF Turnkey | Kilkenny | Cluain Glasan, Ayrfield , Co. Kilkenny - Phase 2 (Phase 1)* | 8 | Clúid Housing |  |  |  |  | Q1-2023
2435 | CALF Turnkey | Kilkenny | Cluain Glasan, Ayrfield, Co. Kilkenny (Phase 1)* | 43 | Clúid Housing | [5 empty] | Q4-2023
2436 | CALF Turnkey | Kilkenny | Cluain Glasan, Ayrfield, Co. Kilkenny (Phase 2)* | 2 | Clúid Housing | [5 empty] | Q2-2024
2437 | CALF Turnkey | Kilkenny | Cois Na Bearu, Graiguenemanagh, Kilkenny (Phase 1) | 14 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q1-2021
2438 | CALF Turnkey | Kilkenny | Margaret’s Field, Callan Road, Kilkenny City (Phase 1) | 40 | Respond | [5 empty] | Q2-2021
2439 | CALF Turnkey | Kilkenny | Nyne Park Close, Callan Road, Co. Kilkenny (Phase 1)* | 40 | Clúid Housing | [5 empty] | Q4-2023
2440 | CALF Turnkey | Kilkenny | Orchard Close, Kilkenny (Phase 1)* | 23 | Clúid Housing | [5 empty] | Q3-2022
2441 | CALF Turnkey | Laois | An Lochan, Summerhill, Portlaoise, Co. Laois (Phase 1)* | 12 | Respond |  |  |  |  | Q4-2022
2442 | CALF Turnkey | Laois | An Lochan, Summerhill, Portlaoise, Co. Laois (Phase 2)* | 8 | Respond |  |  |  |  | Q4-2022
2443 | CALF Turnkey | Laois | Ballymorris Green, Portarlington, Co Laois (Phase 1) | 34 | Clúid Housing | [5 empty] | Q2-2023
2444 | CALF Turnkey | Laois | Ballymorris Green, Portarlington, Co Laois (Phase 2) | 12 | Clúid Housing |  |  |  |  | Q2-2021
2445 | CALF Turnkey | Laois | Bellingham, Portlaoise (Phase 4)* | 9 | Clúid Housing | [5 empty] | Q1-2021
2446 | CALF Turnkey | Laois | Bellingham, Portlaoise (Phase 5)* | 6 | Clúid Housing | [5 empty] | Q3-2021
2447 | CALF Turnkey | Laois | Borris Road, Portlaoise, Co. Laois (Phase 4) | 9 | Tuath Housing Association | [5 empty] | Q1-2021
2448 | CALF Turnkey | Laois | Clonrooske Abbey, Portlaoise, Co. Laois (Phase 1) | 14 | Clúid Housing | [5 empty] | Q4-2022
2449 | CALF Turnkey | Laois | Clonrooske Abbey, Portlaoise, Co. Laois (Phase 2) | 6 | Clúid Housing | [5 empty] | Q1-2024
2450 | CALF Turnkey | Laois | Clonrooske Abbey, Portlaoise, Co. Laois (Phase 3)* | 12 | Clúid Housing | [5 empty] | Q2-2024
2451 | CALF Construction | Laois | Curragh na Mona, Abbeyleix Rd, Portlaoise, Co. Laois (Phase 1) | 39 | Respond |  |  |  | Q2-2024
2452 | CALF Turnkey | Laois | Doirin Alainn, Ballylinan, Co. Laois (Phase 1) | 9 | North and East Housing Association CLG | [5 empty] | Q4-2022
2453 | CALF Turnkey | Laois | Doirinn Alainn, Ballylynan, Co. Laois (Phase 3)* | 6 | North and East Housing Association CLG | [5 empty] | Q2-2021
2454 | CALF Turnkey | Laois | Droughill Lawn, Portarlington, Co. Laois (Phase 1)* | 26 | Oaklee Housing | [5 empty] | Q2-2022
2455 | CALF Turnkey | Laois | Dunamaise View, Kilminchy, Dublin Road, Portlaoise, Laois (Phase 1)* | 36 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2023
2456 | CALF Turnkey | Laois | Goldencroft, Portlaoise, Co. Laois (Phase 1) | 13 | Clúid Housing | [5 empty] | Q4-2022
2457 | CALF Turnkey | Laois | Goldencroft, Portlaoise, Co. Laois (Phase 2) | 24 | Clúid Housing | [5 empty] | Q3-2023
2458 | CALF Turnkey | Laois | Goldencroft, Portlaoise, Co. Laois (Phase 3) | 30 | Clúid Housing | [5 empty] | Q4-2023
2459 | CALF Turnkey | Laois | Harpurs Lane, Portlaoise, Co. Laois (Phase 1)* | 44 | Respond | [5 empty] | Q4-2023
2460 | CALF Turnkey | Laois | Holdbrook, Portlaoise, Co. Laois (Phase 1) | 10 | Clúid Housing | [5 empty] | Q3-2021
2461 | CALF Turnkey | Laois | Holdbrook, Portlaoise, Co. Laois (Phase 2) | 10 | Clúid Housing | [5 empty] | Q4-2022
2462 | CALF Turnkey | Laois | Lake Drive, Kilminchy, Portlaoise, Co. Laois (Phase 1) | 10 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2021
2463 | CALF Turnkey | Laois | Oakvale Way, Main Street, Stradbally, Co. Laois (Phase 1)* | 19 | North and East Housing Association CLG |  |  |  |  | Q4-2023
2464 | CALF Turnkey | Laois | Phase 2 The Glen, Kilnacourt, Portarlington, Co Laois (Phase 1) | 18 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2021
2465 | CALF Turnkey | Laois | Phase 3 The Glen, Kilnacourt, Portarlington, Co Laois. (Phase 1) | 8 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2021
2466 | CALF Construction | Laois | Radharc Darach, Ballyfin Road, Portlaoise, Co. Laois. Formerly Hepburn Court (Phase 1) | 54 | Clúid Housing |  |  |  | Q2-2024
2467 | CALF Turnkey | Laois | Rathillion, Killeshin, Co. Laois (Phase 1)* | 4 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2021
2468 | CALF Turnkey | Laois | Rockview, Mountrath Road, Portlaoise (Phase 1)* | 12 | Oaklee Housing | [5 empty] | Q2-2024
2469 | CALF Turnkey | Laois | Rockview, Mountrath Road, Portlaoise (Phase 2)* | 12 | Oaklee Housing | [5 empty] | Q3-2024
2470 | CALF Turnkey | Laois | Rockview, Mountrath Road, Portlaoise (Phase 3)* | 23 | Oaklee Housing |  |  |  |  | Q2-2023
2471 | CALF Turnkey | Laois | The Maltings and Roselawn, Portlaoise, Co. Laois (Phase 1)* | 15 | Clúid Housing | [5 empty] | Q3-2022
2472 | CALF Turnkey | Laois | The Maltings and Roselawn, Portlaoise, Co. Laois (Phase 2)* | 40 | Clúid Housing | [5 empty] | Q4-2022
2473 | CALF Turnkey | Laois | The Meadows, Mountrath Road, Portlaoise, Co. Laois (Phase 1)* | 48 | Clúid Housing | [5 empty] | Q4-2023
2474 | CALF Turnkey | Laois | The Springs, Kilminchy, Portlaoise, Co Laois (Phase 1)* | 43 | Clúid Housing | [5 empty] | Q4-2022
2475 | CALF Turnkey | Laois | Wallis Street, Mountrath, Co. Laois (Phase 1) | 7 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
2476 | CALF Turnkey | Laois | Wallis Street, Mountrath, Co. Laois (Phase 2)* | 4 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
2477 | CALF Turnkey | Limerick | 2 units, Castleview Shopping Centre Castleconnell Limerick (Phase 1) | 2 | Focus Housing Association CLG | [5 empty] | Q4-2021
2478 | CALF Construction | Limerick | 3 Focus Units in County Limerick (Phase 1) | 3 | Focus Housing Association CLG | [5 empty] | Q4-2023
2479 | CALF Turnkey | Limerick | 8 units Woodfield Manor, Newcastle West, Limerick (Phase 1)* | 8 | Clúid Housing | [5 empty] | Q4-2023
2480 | CALF Turnkey | Limerick | Baunacloka Heights, Mungret Gate, Mungret, Co. Limerick (Phase 2)* | 25 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2021
2481 | CALF Turnkey | Limerick | Bloodmill Road, Singland, Limerick (Phase 1)* | 52 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2021
2482 | CALF Turnkey | Limerick | Bloodmill Road, Singland, Limerick (Phase 2) | 32 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2483 | CALF Turnkey | Limerick | Bloodmill Road, Singland, Limerick (Phase 3) | 10 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2484 | CALF Turnkey | Limerick | Bloodmill Road, Singland, Limerick (Phase 4)* | 19 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2485 | CALF Turnkey | Limerick | Bloodmill Road, Singland, Limerick (Phase 5) | 24 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2486 | CALF Turnkey | Limerick | Broad Street, Curry Lane, Limerick City (Phase 1) | 30 | Focus Housing Association CLG |  |  |  |  | Q3-2024
2487 | CALF Turnkey | Limerick | Castlerock Avenue, Coolbane, Castleconnell, Limerick (Phase 1)* | 15 | Respond | [5 empty] | Q4-2023
2488 | CALF Turnkey | Limerick | Castletroy Part V, Mill Ave, Grove, Court, Castletroy, Limerick (Phase 1)* | 30 | Circle Voluntary Housing Association CLG |  |  |  |  | Q1-2024
2489 | CALF Turnkey | Limerick | Clonmacken, Condell Road, Limerick (Phase 1)* | 35 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2021
2490 | CALF Turnkey | Limerick | Clonmacken, Condell Road, Limerick (Phase 2) | 12 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2022
2491 | CALF Turnkey | Limerick | Clonmacken, Condell Road, Limerick (Phase 3)* | 29 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2492 | CALF Turnkey | Limerick | Clonmacken, Condell Road, Limerick (Phase 4)* | 12 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2493 | CALF Turnkey | Limerick | Clonmacken, Condell Road, Limerick (Phase 5)* | 22 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2494 | CALF Turnkey | Limerick | Davin Gardens, Redgate Road, Caherdavin, Limerick (Phase 1) | 6 | Focus Housing Association CLG |  |  |  |  | Q1-2023
2495 | CALF Turnkey | Limerick | Dromsally Woods, Cappamore, Co. Limerick (Phase 1) | 5 | Focus Housing Association CLG | [5 empty] | Q4-2022
2496 | CALF Construction | Limerick | Limerick Derelict Properties (Phase 2), Ballynanty, Ballinacurra Weston and Prospect (Phase 1) | 6 | Focus Housing Association CLG |  |  |  | Q1-2024
2497 | CALF Construction | Limerick | Limerick Derelict Properties (Phase 3), Ballinacurra Weston and Weston, Limerick City (Phase 1) | 6 | Focus Housing Association CLG |  |  |  | Q1-2024
2498 | CALF Turnkey | Limerick | Mungret Gate, Baunacloka, Mungret, Limerick (Phase 1) | 8 | Clúid Housing | [5 empty] | Q2-2021
2499 | CALF Turnkey | Limerick | Mungret Gate, Baunacloka, Mungret, Limerick (Phase 2)* | 23 | Clúid Housing | [5 empty] | Q2-2022
2500 | CALF Turnkey | Limerick | New Link Road, Shanabooly, Cahedavin, Limerick (Phase 1)* | 13 | Focus Housing Association CLG |  |  |  | Q3-2024
2501 | CALF Turnkey | Limerick | New Street, Abbeyfeale, Co. Limerick (Phase 1) | 3 | Focus Housing Association CLG | [5 empty] | Q3-2024
2502 | CALF Turnkey | Limerick | Newtown, Castletroy, Limerick (Phase 1)* | 31 | Clúid Housing | [5 empty] | Q4-2023
2503 | CALF Turnkey | Limerick | Old Dublin Road, Rhebogue, Limerick (Phase 1)* | 16 | Focus Housing Association CLG | [5 empty] | Q2-2022
2504 | CALF Turnkey | Limerick | Phase 2 Newtown Meadows, Castletroy, Limerick (Phase 1)* | 32 | Clúid Housing | [5 empty] | Q4-2023
2505 | CALF Turnkey | Limerick | The Hill, Bru Na Gruadan, Castletroy, Limerick (Phase 1) | 5 | Focus Housing Association CLG | [5 empty] | Q4-2023
2506 | CALF Turnkey | Limerick | The Hill, Bru Na Gruadan, Castletroy, Limerick (Phase 2)* | 10 | Focus Housing Association CLG |  |  |  |  | Q2-2023
2507 | CALF Turnkey | Limerick | The Hill, Bru Na Gruadan, Castletroy, Limerick (Phase 3)* | 9 | Focus Housing Association CLG |  |  |  |  | Q2-2023
2508 | CALF Turnkey | Limerick | The Hill, Bru Na Gruadan, Castletroy, Limerick (Phase 4) | 4 | Focus Housing Association CLG |  |  |  |  | Q2-2023
2509 | CALF Turnkey | Limerick | The Hill, Bru Na Gruadan, Castletroy, Limerick (Phase 5)* | 9 | Focus Housing Association CLG |  |  |  |  | Q2-2023
2510 | CALF Turnkey | Limerick | The Mills, Castletroy, Co Limerick (Phase 1) | 13 | Circle Voluntary Housing Association CLG | [5 empty] | Q4-2023
2511 | CALF Turnkey | Limerick | The Mills, Castletroy, Co Limerick (Phase 2) | 17 | Circle Voluntary Housing Association CLG | [5 empty] | Q4-2023
2512 | CALF Turnkey | Limerick | The Mills, Castletroy, Co Limerick (Phase 3) | 19 | Circle Voluntary Housing Association CLG | [5 empty] | Q4-2023
2513 | CALF Turnkey | Limerick | The Mills, Castletroy, Co Limerick (Phase 4) | 3 | Circle Voluntary Housing Association CLG | [5 empty] | Q2-2024
2514 | CALF Turnkey | Limerick | The Mills, Castletroy, Co Limerick (Phase 5) | 4 | Circle Voluntary Housing Association CLG |  |  |  |  | Q3-2022
2515 | CALF Turnkey | Limerick | The Orchard, Main Street, Pallaskenry, Co Limerick (Phase 1) | 16 | Focus Housing Association CLG | [5 empty] | Q4-2023
2516 | CALF Turnkey | Limerick | Toormore, Main Street, Bruree, Co. Limerick (Phase 1) | 16 | Clúid Housing | [5 empty] | Q2-2021
2517 | CALF Construction | Limerick | Turagh Close, Cappamore, Limerick (Phase 1) | 17 | Clúid Housing |  |  |  | Q3-2024
2518 | CALF Turnkey | Limerick | Windmill House, Dock Road, Limerick (Phase 1) | 12 | Focus Housing Association CLG |  |  |  |  | Q3-2023
2519 | CALF Turnkey | Limerick | Windmill House, Dock Road, Limerick (Phase 2) | 12 | Focus Housing Association CLG |  |  |  |  | Q3-2023
2520 | CALF Turnkey | Limerick | Woodfield Manor, Cloonyscrehane, Newcastle West, Co Limerick (Phase 1)* | 11 | Clúid Housing | [5 empty] | Q4-2022
2521 | CALF Turnkey | Louth | An Caislean Solasach, Flaxmill Lane ,Yellowbatter, Drogheda, Co. Louth (Phase 1)* | 17 | North and East Housing Association CLG |  |  |  |  | Q4-2022
2522 | CALF Turnkey | Louth | Bellewsbridge Road, Dundalk, Co. Louth (Phase 1) | 5 | Circle Voluntary Housing Association CLG | [5 empty] | Q4-2022
2523 | CALF Turnkey | Louth | Cathedral View, Ramparts, Dundalk, Co. Louth (Phase 1)* | 16 | Tuath Housing Association | [5 empty] | Q1-2021
2524 | CALF Turnkey | Louth | Cathedral View, Ramparts, Dundalk, Co. Louth (Phase 2) | 10 | Tuath Housing Association | [5 empty] | Q2-2021
2525 | CALF Turnkey | Louth | Cathedral View, Ramparts, Dundalk, Co. Louth (Phase 3) | 16 | Tuath Housing Association | [5 empty] | Q4-2021
2526 | CALF Turnkey | Louth | Cathedral View, Ramparts, Dundalk, Co. Louth (Phase 4) | 11 | Tuath Housing Association | [5 empty] | Q4-2021
2527 | CALF Turnkey | Louth | Clonmore Close, Ardee, Co. Louth (Phase 1) | 12 | Clúid Housing | [5 empty] | Q1-2021
2528 | CALF Turnkey | Louth | Clonmore Close, Ardee, Co. Louth (Phase 2)* | 15 | Clúid Housing | [5 empty] | Q3-2021
2529 | CALF Turnkey | Louth | Clonmore Close, Ardee, Co. Louth (Phase 3) | 15 | Clúid Housing | [5 empty] | Q4-2021
2530 | CALF Turnkey | Louth | Clonmore Close, Ardee, Co. Louth (Phase 4) | 13 | Clúid Housing | [5 empty] | Q4-2021
2531 | CALF Turnkey | Louth | Connolly Field, Dundalk, Co. Louth (Phase 1)* | 70 | Fold Housing Association Ireland Ltd |  |  |  |  | Q1-2023
2532 | CALF Turnkey | Louth | Crushrod Avenue, Drogheda, Co. Louth (Phase 1)* | 20 | Clúid Housing |  |  |  |  | Q3-2023
2533 | CALF Turnkey | Louth | Crushrod Avenue, Drogheda, Co. Louth (Phase 2) | 33 | Clúid Housing |  |  |  |  | Q3-2023
2534 | CALF Turnkey | Louth | Donore Road, Drogheda, Co. Louth (Phase 1)* | 66 | Clúid Housing | [5 empty] | Q4-2023
2535 | CALF Turnkey | Louth | Drybridge, Drogheda, Co. Louth (Phase 1)* | 16 | North and East Housing Association CLG | [5 empty] | Q4-2023
2536 | CALF Turnkey | Louth | Dublin Road, Dundalk, Co Louth (Phase 1)* | 25 | Respond | [5 empty] | Q4-2023
2537 | CALF Turnkey | Louth | Dublin Road, Dundalk, Co Louth (Phase 2)* | 40 | Respond |  |  |  |  | Q4-2020
2538 | CALF Turnkey | Louth | Duiche Roden (formerly The Kitchen Garden)Desmesne Road, Dundalk, Co. Louth (Phase 1)* | 47 | Clúid Housing | [5 empty] | Q4-2022
2539 | CALF Turnkey | Louth | Duiche Roden (formerly The Kitchen Garden)Desmesne Road, Dundalk, Co. Louth (Phase 2) | 14 | Clúid Housing | [5 empty] | Q2-2023
2540 | CALF Turnkey | Louth | Duiche Roden (formerly The Kitchen Garden)Desmesne Road, Dundalk, Co. Louth (Phase 3) | 10 | Clúid Housing | [5 empty] | Q3-2023
2541 | CALF Turnkey | Louth | Duiche Roden (formerly The Kitchen Garden)Desmesne Road, Dundalk, Co. Louth (Phase 4) | 14 | Clúid Housing | [5 empty] | Q4-2023
2542 | CALF Turnkey | Louth | Duiche Roden (formerly The Kitchen Garden)Desmesne Road, Dundalk, Co. Louth (Phase 5) | 12 | Clúid Housing | [5 empty] | Q4-2023
2543 | CALF Turnkey | Louth | Duiche Roden (formerly The Kitchen Garden)Desmesne Road, Dundalk, Co. Louth (Phase 6) | 8 | Clúid Housing | [5 empty] | Q2-2024
2544 | CALF Turnkey | Louth | Duiche Roden (formerly The Kitchen Garden)Desmesne Road, Dundalk, Co. Louth (Phase 7) | 28 | Clúid Housing | [5 empty] | Q2-2024
2545 | CALF Turnkey | Louth | Fairways Gardens, Dundalk Co Louth (Phase 1) | 8 | Clúid Housing | [5 empty] | Q4-2021
2546 | CALF Turnkey | Louth | Friary Place, Mill Lane, Drogheda, County Louth (Phase 1)* | 49 | Tuath Housing Association |  |  |  |  | Q1-2022
2547 | CALF Turnkey | Louth | Gullion Avenue, Gullion Park, Finnabair, Dundalk, Co Louth (Phase 1)* | 142 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2024
2548 | CALF Turnkey | Louth | Halliday Mills, Quay Street, Dundalk, Co. Louth (Phase 1)* | 85 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2021
2549 | CALF Turnkey | Louth | Harbour View, Coulter Place, Dundalk (Phase 1) | 24 | Clúid Housing | [5 empty] | Q3-2021
2550 | CALF Turnkey | Louth | Harbour View, Dundalk Co. Louth (Phase 1) | 18 | Clúid Housing |  |  |  |  | Q3-2023
2551 | CALF Turnkey | Louth | Lismullen Grove, Dundalk, Co. Louth (Phase 2) | 8 | Tuath Housing Association | [5 empty] | Q1-2021
2552 | CALF Turnkey | Louth | Newfoundwell Road, Drogheda, Co. Louth (Phase 1)* | 55 | Clúid Housing | [5 empty] | Q1-2022
2553 | CALF Turnkey | Louth | Newfoundwell Road, Drogheda, Co. Louth (Phase 2) | 39 | Clúid Housing | [5 empty] | Q2-2023
2554 | CALF Turnkey | Louth | Newtown, Marsh Road, Drogheda, Co. Louth (Phase 1)* | 40 | Respond | [5 empty] | Q4-2023
2555 | CALF Turnkey | Louth | Newtown, Marsh Road, Drogheda, Co. Louth (Phase 2)* | 37 | Respond |  |  |  |  | Q4-2020
2556 | CALF Turnkey | Louth | Newtown, Marsh Road, Drogheda, Co. Louth (Phase 3)* | 56 | Respond |  |  |  |  | Q4-2020
2557 | CALF Turnkey | Louth | Racecourse Meadows, Dundalk, Co. Louth - Tuathduiche (Phase 2) | 10 | Tuath Housing Association | [5 empty] | Q2-2022
2558 | CALF Turnkey | Louth | Racecourse Meadows, Dundalk, Co. Louth - Tuathduiche (Phase 3)* | 13 | Tuath Housing Association | [5 empty] | Q4-2022
2559 | CALF Turnkey | Louth | Racecourse Meadows, Dundalk, Co. Louth - Tuathduiche (Phase 4)* | 12 | Tuath Housing Association | [5 empty] | Q2-2024
2560 | CALF Turnkey | Louth | Racecourse Road, Dundalk, Co. Louth (Phase 1) | 18 | Circle Voluntary Housing Association CLG |  |  |  |  | Q1-2024
2561 | CALF Turnkey | Louth | Racecourse Road, Dundalk, Co. Louth (Phase 2) | 8 | Circle Voluntary Housing Association CLG |  |  |  |  | Q1-2024
2562 | CALF Turnkey | Louth | Racecourse Road, Dundalk, Co. Louth (Phase 3)* | 19 | Circle Voluntary Housing Association CLG |  |  |  |  | Q1-2024
2563 | CALF Turnkey | Louth | The Hawthorns, Avourwen, Drogheda, Co. Louth (Phase 1)* | 50 | Oaklee Housing |  |  |  |  | Q2-2024
2564 | CALF Turnkey | Louth | Tierney Street, Ardee, Co. Louth (Phase 1) | 11 | Circle Voluntary Housing Association CLG | [5 empty] | Q4-2023
2565 | CALF Turnkey | Louth | Tullybrook, Drogheda, Co. Louth (Phase 1) | 18 | Clúid Housing | [5 empty] | Q4-2023
2566 | CALF Turnkey | Louth | Tullybrook, Drogheda, Co. Louth (Phase 2) | 28 | Clúid Housing | [5 empty] | Q4-2023
2567 | CALF Turnkey | Louth | Tullybrook, Drogheda, Co. Louth (Phase 3)* | 39 | Clúid Housing | [5 empty] | Q2-2024
2568 | CALF Turnkey | Mayo | Humbert Close Castlebar Co. Mayo (Phase 1) | 7 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2024
2569 | CALF Turnkey | Mayo | Humbert Way, Castlebar, Co. Mayo (Phase 1) | 20 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2570 | CALF Turnkey | Mayo | The Sycamores, Ballina (Phase 1) | 11 | Clúid Housing | [5 empty] | Q2-2021
2571 | CALF Turnkey | Meath | Applewood Court, Beaufort Place, Navan, Co. Meath (Phase 1)* | 21 | Tuath Housing Association | [5 empty] | Q4-2023
2572 | CALF Turnkey | Meath | Ashewood, Ashbourne, Co Meath (Phase 1) | 11 | Clúid Housing | [5 empty] | Q4-2021
2573 | CALF Turnkey | Meath | Athboy Road, Navan, Co. Meath (Phase 1) | 20 | Respond | [5 empty] | Q1-2023
2574 | CALF Turnkey | Meath | Athboy Road, Navan, Co. Meath (Phase 2)* | 14 | Respond | [5 empty] | Q2-2023
2575 | CALF Turnkey | Meath | Athboy Road, Navan, Co. Meath (Phase 3) | 29 | Respond |  |  |  |  | Q1-2020
2576 | CALF Turnkey | Meath | Baker Hall, Navan, Co. Meath (Phase 1) | 49 | Tuath Housing Association | [5 empty] | Q4-2022
2577 | CALF Turnkey | Meath | Cluain Adáin, Clonmagaddan, Navan, Co Meath (Phase 1) | 36 | Clúid Housing | [5 empty] | Q2-2024
2578 | CALF Turnkey | Meath | Cois Glaisin, Cois Glaisin Park, Johnstown, Navan, Co Meath (Phase 1) | 5 | Clúid Housing | [5 empty] | Q2-2023
2579 | CALF Turnkey | Meath | Colliers Place, Abbey Road, Commons, Duleek, Co. Meath (Phase 1)* | 17 | North and East Housing Association CLG | [5 empty] | Q2-2022
2580 | CALF Turnkey | Meath | Colliers Place, Abbey Road, Commons, Duleek, Co. Meath (Phase 2) | 5 | North and East Housing Association CLG | [5 empty] | Q4-2022
2581 | CALF Turnkey | Meath | Dunville House, Dunville Road, Navan, Co. Meath (Phase 1)* | 45 | Tuath Housing Association | [5 empty] | Q2-2024
2582 | CALF Turnkey | Meath | Effernock, Trim, Co. Meath (Phase 1) | 20 | Clúid Housing | [5 empty] | Q2-2023
2583 | CALF Turnkey | Meath | Emmet Court, Emmet Street, Trim, Co. Meath (Phase 1)* | 12 | North and East Housing Association CLG |  |  |  |  | Q3-2021
2584 | CALF Turnkey | Meath | Frederick Manor, Ashbourne, Co. Meath (Phase 1)* | 11 | Clúid Housing | [5 empty] | Q1-2021
2585 | CALF Turnkey | Meath | Gainsfield, Commons Road, Navan, Co. Meath (Phase 3) | 7 | Tuath Housing Association | [5 empty] | Q1-2021
2586 | CALF Turnkey | Meath | Gainsfield, Commons Road, Navan, Co. Meath (Phase 4) | 9 | Tuath Housing Association | [5 empty] | Q2-2021
2587 | CALF Turnkey | Meath | Gardenrath, Kells, Co. Meath (Phase 1) | 16 | Clúid Housing |  |  |  |  | Q4-2023
2588 | CALF Turnkey | Meath | Gardenrath, Kells, Co. Meath (Phase 2) | 12 | Clúid Housing |  |  |  |  | Q4-2023
2589 | CALF Turnkey | Meath | Gardenrath, Kells, Co. Meath (Phase 3) | 5 | Clúid Housing |  |  |  |  | Q4-2023
2590 | CALF Turnkey | Meath | Gardenrath, Kells, Co. Meath (Phase 4) | 12 | Clúid Housing |  |  |  |  | Q4-2023
2591 | CALF Turnkey | Meath | Glen Boann, Donacarney Little, Mornington, Co Meath (Phase 1)* | 12 | Clúid Housing | [5 empty] | Q3-2023
2592 | CALF Turnkey | Meath | Gort Fionnbarra (Gainsfield Phase 2), Commons Road, Navan, Co. Meath (Phase 1) | 19 | Tuath Housing Association | [5 empty] | Q4-2021
2593 | CALF Turnkey | Meath | Gort Fionnbarra (Gainsfield Phase 2), Commons Road, Navan, Co. Meath (Phase 2) | 16 | Tuath Housing Association | [5 empty] | Q2-2022
2594 | CALF Turnkey | Meath | Gort Fionnbarra (Gainsfield Phase 2), Commons Road, Navan, Co. Meath (Phase 3) | 14 | Tuath Housing Association | [5 empty] | Q3-2022
2595 | CALF Turnkey | Meath | Gort Fionnbarra, Commons Road, Navan, Co. Meath (Phase 1) | 2 | Tuath Housing Association | [5 empty] | Q3-2022
2596 | CALF Turnkey | Meath | Knightsbrook Close, Iffernock, Trim, Co. Meath (Phase 1) | 5 | Tuath Housing Association | [5 empty] | Q3-2021
2597 | CALF Turnkey | Meath | Knightsbrook Close, Iffernock, Trim, Co. Meath (Phase 2) | 5 | Tuath Housing Association | [5 empty] | Q3-2021
2598 | CALF Turnkey | Meath | Knightsbrook Close, Iffernock, Trim, Co. Meath (Phase 3) | 6 | Tuath Housing Association | [5 empty] | Q4-2021
2599 | CALF Turnkey | Meath | Knightsbrook Close, Phase 2, Iffernock, Trim, Co. Meath (Phase 1) | 8 | Tuath Housing Association | [5 empty] | Q3-2022
2600 | CALF Turnkey | Meath | Knightsbrook Close, Phase 2, Iffernock, Trim, Co. Meath (Phase 2)* | 7 | Tuath Housing Association | [5 empty] | Q3-2022
2601 | CALF Turnkey | Meath | Knightsbrook Close, Phase 2, Iffernock, Trim, Co. Meath (Phase 3)* | 7 | Tuath Housing Association | [5 empty] | Q3-2022
2602 | CALF Turnkey | Meath | Maudlin Vale, Trim, Co. Meath (Phase 1) | 8 | Tuath Housing Association | [5 empty] | Q4-2022
2603 | CALF Turnkey | Meath | Maudlin Vale, Trim, Co. Meath (Phase 2) | 4 | Tuath Housing Association | [5 empty] | Q1-2023
2604 | CALF Turnkey | Meath | Maudlin Vale, Trim, Co. Meath (Phase 3) | 16 | Tuath Housing Association | [5 empty] | Q3-2023
2605 | CALF Turnkey | Meath | Maudlin Vale, Trim, Co. Meath (Phase 4) | 11 | Tuath Housing Association | [5 empty] | Q4-2023
2606 | CALF Turnkey | Meath | Maydenhayes, Donacarney, Co. Meath (Phase 1)* | 12 | Clúid Housing | [5 empty] | Q3-2021
2607 | CALF Turnkey | Meath | Narrow Ways, Bettystown, Co. Meath (Phase 1) | 6 | Tuath Housing Association | [5 empty] | Q1-2022
2608 | CALF Turnkey | Meath | Narrow Ways, Bettystown, Co. Meath (Phase 2) | 6 | Tuath Housing Association | [5 empty] | Q1-2022
2609 | CALF Turnkey | Meath | Oak Hall, Ardee Road, Carlanstown, Co. Meath (Phase 1) | 8 | Tuath Housing Association | [5 empty] | Q4-2022
2610 | CALF Turnkey | Meath | Oak Village, The Willows, Dunshaughlin, Co. Meath (Phase 1) | 20 | Clúid Housing | [5 empty] | Q2-2023
2611 | CALF Turnkey | Meath | Part 2 Baker Hall, Navan, Co. Meath (Phase 1) | 26 | Tuath Housing Association | [5 empty] | Q4-2023
2612 | CALF Turnkey | Meath | Phase 2 Cluain Adain, Clonmagadden, Navan, Co. Meath (Phase 1) | 32 | Clúid Housing |  |  |  |  | Q4-2023
2613 | CALF Turnkey | Meath | Royal Oaks, Enfield, Co. Meath (Phase 2) (Phase 2)* | 14 | Clúid Housing | [5 empty] | Q2-2021
2614 | CALF Turnkey | Meath | Royal Oaks, Enfield, Co. Meath (Phase 2) (Phase 3) | 16 | Clúid Housing | [5 empty] | Q2-2022
2615 | CALF Turnkey | Meath | Ruxton Oaks, Navan, Co. Meath (Phase 1)* | 20 | Clúid Housing | [5 empty] | Q4-2021
2616 | CALF Turnkey | Meath | St Marys Dunboyne, Co. Meath (Phase 1) | 16 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2021
2617 | CALF Turnkey | Meath | Swanbrook, Trim Road, Co. Meath (Phase 1) | 22 | Tuath Housing Association | [5 empty] | Q2-2023
2618 | CALF Turnkey | Meath | Swanbrook, Trim Road, Co. Meath (Phase 2) | 18 | Tuath Housing Association | [5 empty] | Q2-2023
2619 | CALF Turnkey | Meath | Swanbrook, Trim Road, Co. Meath (Phase 3) | 8 | Tuath Housing Association | [5 empty] | Q3-2023
2620 | CALF Turnkey | Meath | Swanbrook, Trim Road, Navan, Co. Meath_Part 2 (Phase 1) | 64 | Tuath Housing Association | [5 empty] | Q4-2023
2621 | CALF Turnkey | Meath | Swanbrook, Trim Road, Navan, Co. Meath_Part 2 (Phase 2) | 7 | Tuath Housing Association | [5 empty] | Q2-2024
2622 | CALF Turnkey | Meath | The Arches, Dunshaughlin, Co. Meath (Phase 1) | 6 | Tuath Housing Association | [5 empty] | Q1-2023
2623 | CALF Turnkey | Meath | The Maudlins, Trim, Co. Meath (Phase 1) | 9 | Clúid Housing | [5 empty] | Q1-2021
2624 | CALF Turnkey | Meath | The Willows, Dunshaughlin, Co. Meath (Phase 1)* | 24 | Clúid Housing | [5 empty] | Q4-2022
2625 | CALF Turnkey | Meath | The Willows, Dunshaughlin, Co. Meath (Phase 2)* | 72 | Clúid Housing | [5 empty] | Q4-2022
2626 | CALF Turnkey | Meath | Tubberclaire Meadows, Navan, Co. Meath (Phase 1)* | 8 | Clúid Housing | [5 empty] | Q4-2022
2627 | CALF Turnkey | Meath | Whitefield Hall, Bettystown, Co. Meath (Phase 3) | 2 | Tuath Housing Association | [5 empty] | Q3-2021
2628 | CALF Turnkey | Meath | Wood Stream, Old Athlumney Road, Navan, Co. Meath (Phase 1)* | 12 | Clúid Housing |  |  |  |  | Q3-2022
2629 | CALF Turnkey | Meath | Wood Stream, Old Athlumney Road, Navan, Co. Meath (Phase 2) | 6 | Clúid Housing |  |  |  |  | Q3-2022
2630 | CALF Turnkey | Meath | Wood Stream, Old Athlumney Road, Navan, Co. Meath (Phase 3)* | 21 | Clúid Housing |  |  |  |  | Q3-2022
2631 | CALF Turnkey | Monaghan | Ard Cuil Seana, Coolshannagh Road, Co. Monaghan (Phase 1)* | 10 | North and East Housing Association CLG |  |  |  |  | Q2-2023
2632 | CALF Turnkey | Monaghan | Bree, Castleblayney (Phase 2) | 6 | Tuath Housing Association | [5 empty] | Q2-2021
2633 | CALF Turnkey | Monaghan | Bree, Castleblayney (Phase 3) | 8 | Tuath Housing Association | [5 empty] | Q3-2021
2634 | CALF Turnkey | Monaghan | Bree, Castleblayney (Phase 4) | 8 | Tuath Housing Association | [5 empty] | Q2-2022
2635 | CALF Turnkey | Monaghan | Bree, Castleblayney (Phase 5) | 3 | Tuath Housing Association | [5 empty] | Q2-2022
2636 | CALF Turnkey | Monaghan | Drumbear Wood, Monaghan, Co. Monaghan (Phase 1) | 6 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2023
2637 | CALF Turnkey | Monaghan | Drumbear Wood, Monaghan, Co. Monaghan (Phase 2)* | 11 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2023
2638 | CALF Turnkey | Monaghan | Hall Street, Ballybay, Co. Monaghan (Phase 1) | 7 | North and East Housing Association CLG |  |  |  |  | Q3-2023
2639 | CALF Turnkey | Monaghan | Knockroe Glen, Cornacassa, Monaghan, Co. Monaghan (Phase 1) | 9 | Clúid Housing | [5 empty] | Q3-2023
2640 | CALF Turnkey | Monaghan | Lakeview Apartments, Drummond Radhairc, Carrickmacross, Co Monaghan (Phase 1)* | 12 | North and East Housing Association CLG | [5 empty] | Q2-2022
2641 | CALF Turnkey | Monaghan | Macartan View, Latlorcan, Dublin Road, Monaghan (Phase )* | 21 | Tuath Housing Association |  |  |  | Q2-2021
2642 | CALF Turnkey | Monaghan | Macartan View, Latlorcan, Dublin Road, Monaghan (Phase 1) | 20 | Tuath Housing Association |  |  |  | Q2-2021
2643 | CALF Turnkey | Monaghan | Magheross, Carrickmacross, Co Monaghan (Phase 1) | 7 | Tuath Housing Association | [5 empty] | Q2-2021
2644 | CALF Turnkey | Monaghan | Magheross, Carrickmacross, Co Monaghan (Phase 2) | 6 | Tuath Housing Association |  |  |  |  | Q3-2019
2645 | CALF Turnkey | Monaghan | Magheross, Carrickmacross, Co Monaghan (Phase 3) | 6 | Tuath Housing Association |  |  |  |  | Q3-2019
2646 | CALF Turnkey | Monaghan | Magheross, Carrickmacross, Co Monaghan (Phase 4) | 14 | Tuath Housing Association |  |  |  |  | Q3-2019
2647 | CALF Turnkey | Monaghan | Part 2, Radharc An Bhri, Bree, Castleblayney, Co. Monaghan (Phase 1)* | 2 | Tuath Housing Association | [5 empty] | Q2-2022
2648 | CALF Turnkey | Monaghan | Part 2, Radharc An Bhri, Bree, Castleblayney, Co. Monaghan (Phase 2) | 4 | Tuath Housing Association | [5 empty] | Q2-2023
2649 | CALF Turnkey | Monaghan | Part 2, Radharc An Bhri, Bree, Castleblayney, Co. Monaghan (Phase 3) | 4 | Tuath Housing Association | [5 empty] | Q3-2023
2650 | CALF Turnkey | Monaghan | Part 2, Radharc An Bhri, Bree, Castleblayney, Co. Monaghan (Phase 4) | 2 | Tuath Housing Association | [5 empty] | Q2-2024
2651 | CALF Turnkey | Monaghan | Railway View, Kilnacloy, Monaghan, Co. Monaghan (Phase 1) | 8 | Tuath Housing Association |  |  |  |  | Q3-2020
2652 | CALF Turnkey | Monaghan | Railway View, Kilnacloy, Monaghan, Co. Monaghan (Phase 2)* | 8 | Tuath Housing Association |  |  |  |  | Q3-2020
2653 | CALF Turnkey | Monaghan | The Meadows, Emy, Emyvale, Co. Monaghan (Phase 1)* | 8 | Tuath Housing Association | [5 empty] | Q3-2023
2654 | CALF Turnkey | Monaghan | The Meadows, Emy, Emyvale, Co. Monaghan (Phase 2) | 6 | Tuath Housing Association | [5 empty] | Q3-2023
2655 | CALF Turnkey | Offaly | 3 units, An Corran, Crinkle, Birr, Co. Offaly (Phase 1) | 3 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q1-2021
2656 | CALF Turnkey | Offaly | Bruach Na Canalach, An Daingean Road, Tullamore, Co.Offaly (Phase 1)* | 12 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2024
2657 | CALF Turnkey | Offaly | Bruach Na Canalach, An Daingean Road, Tullamore, Co.Offaly (Phase 2) | 7 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2024
2658 | CALF Construction | Offaly | Kearney’s Field, Tullamore, Co. Offaly (Phase 1) | 41 | Oaklee Housing | [5 empty] | Q4-2023
2659 | CALF Construction | Offaly | Killane Drive, Edenderry, Co Offaly (Phase 1) | 25 | Tuath Housing Association | [5 empty] | Q2-2021
2660 | CALF Turnkey | Offaly | Kingswood Drive, Arden Road, Tullamore, Co. Offaly (Phase 1) | 25 | Respond |  |  |  |  | Q3-2023
2661 | CALF Turnkey | Offaly | Kingswood Drive, Arden Road, Tullamore, Co. Offaly (Phase 2)* | 52 | Respond |  |  |  |  | Q3-2023
2662 | CALF Turnkey | Offaly | MacRegol Cuirt, Birr, Co Offaly (Phase 1) | 28 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q1-2021
2663 | CALF Turnkey | Offaly | Rahan Road, Tullamore, Co. Offaly (aka Jackson’s Hill) (Phase 1)* | 26 | Clúid Housing | [5 empty] | Q2-2022
2664 | CALF Turnkey | Offaly | The Hawthorns, Arden Road, Tullamore, Co. Offaly (Phase 1) | 16 | Clúid Housing | [5 empty] | Q2-2022
2665 | CALF Turnkey | Roscommon | Castle Street, Roscommon Town, Co Roscommon (Castle View Apts Block A) (Phase 1) | 10 | Tuath Housing Association |  |  |  |  | Q1-2022
2666 | CALF Turnkey | Roscommon | Meadowbank, Greatmeadow, Boyle, Co. Roscommon (Phase 1) | 4 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q4-2023
2667 | CALF Turnkey | Roscommon | Monksland, Athlone, Co. Roscommon (Cloongowna). (Phase 1)* | 35 | Tuath Housing Association | [5 empty] | Q4-2023
2668 | CALF Turnkey | Sligo | The Fairways, Tubbercurry, Co. Sligo (Phase 1) | 8 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2023
2669 | CALF Turnkey | South Dublin | 4 units, Carrigmore View, Tallaght, Dublin 24 (Phase 1) | 4 | Simon Community: Dublin Simon |  |  |  |  | Q2-2024
2670 | CALF Turnkey | South Dublin | Aderrig (Part V), Adamstown, Lucan, Co. Dublin (Phase 1)* | 2 | Clúid Housing | [5 empty] | Q4-2023
2671 | CALF Turnkey | South Dublin | Aderrig (Part V), Adamstown, Lucan, Co. Dublin (Phase 2)* | 3 | Clúid Housing |  |  |  |  | Q3-2022
2672 | CALF Turnkey | South Dublin | Aderrig (Part V), Adamstown, Lucan, Co. Dublin (Phase 3)* | 18 | Clúid Housing |  |  |  |  | Q3-2022
2673 | CALF Turnkey | South Dublin | Aderrig Square, Adamstown, Lucan, Co Dublin (Phase 1)* | 38 | Circle Voluntary Housing Association CLG | [5 empty] | Q4-2023
2674 | CALF Turnkey | South Dublin | Airton Plaza, Airton Road, Tallaght, D24 (Phase 1)* | 98 | Clúid Housing |  |  |  |  | Q2-2022
2675 | CALF Turnkey | South Dublin | Airton Road, Junction of Airton and Greenhills Road, Tallaght, Dublin 24 (Phase 1) | 93 | Respond |  |  |  |  | Q3-2022
2676 | CALF Turnkey | South Dublin | Airton Road, Junction of Airton and Greenhills Road, Tallaght, Dublin 24 (Phase 2)* | 120 | Respond |  |  |  |  | Q3-2022
2677 | CALF Turnkey | South Dublin | Ballynakelly Rise, Newcastle Boulevard and Graydon Park, Newcastle, County Dublin (Phase 1)* | 8 | Tuath Housing Association | [5 empty] | Q2-2022
2678 | CALF Turnkey | South Dublin | Ballynakelly Rise, Newcastle Boulevard and Graydon Park, Newcastle, County Dublin (Phase 2)* | 8 | Tuath Housing Association | [5 empty] | Q3-2022
2679 | CALF Turnkey | South Dublin | Barnoaks, Citywest, Dublin 24 (Phase 1)* | 10 | Tuath Housing Association | [5 empty] | Q4-2022
2680 | CALF Turnkey | South Dublin | Barnoaks, Citywest, Dublin 24 (Phase 2)* | 9 | Tuath Housing Association | [5 empty] | Q2-2023
2681 | CALF Turnkey | South Dublin | Barnoaks, Citywest, Dublin 24 (Phase 3)* | 27 | Tuath Housing Association | [5 empty] | Q4-2023
2682 | CALF Turnkey | South Dublin | Block 2, Somerton Gate, Adamstown, Lucan, Co. Dublin (Phase 1) | 68 | Clúid Housing |  |  |  | Q3-2024
2683 | CALF Turnkey | South Dublin | Block G Part V Units, The Crossings, Adamstown, Co. Dublin (Phase 1)* | 30 | Oaklee Housing | [5 empty] | Q3-2024
2684 | CALF Turnkey | South Dublin | Carrigmore Woods, Carrigmore Woods, Citywest, Dublin 24 (Phase 1) | 31 | Tuath Housing Association |  |  |  |  | Q4-2023
2685 | CALF Turnkey | South Dublin | Carrigmore Woods, Citywest, Dublin 24 (Phase 1)* | 106 | Tuath Housing Association |  |  |  |  | Q4-2023
2686 | CALF Turnkey | South Dublin | City West Village, Fortunestown Lane, City West, Dublin 24 (Phase 1)* | 10 | Tuath Housing Association | [5 empty] | Q4-2023
2687 | CALF Turnkey | South Dublin | Citywest Quarter, Citywest, Dublin 24 (Phase 1)* | 32 | Tuath Housing Association | [5 empty] | Q2-2021
2688 | CALF Turnkey | South Dublin | Citywest Village House, Citywest Village, D24 (Phase 1)* | 36 | Fold Housing Association Ireland Ltd | [5 empty] | Q1-2022
2689 | CALF Turnkey | South Dublin | Cloverhill Lodge, Cloverhill Rd, Clondalkin, D22 (Phase 1)* | 40 | Oaklee Housing | [5 empty] | Q4-2023
2690 | CALF Turnkey | South Dublin | Cúil Dúin Avenue, City West - Phase 1 (Phase 1)* | 36 | Tuath Housing Association | [5 empty] | Q2-2024
2691 | CALF Turnkey | South Dublin | Dodderbrook, Old Court Rd, Ballycullen, Dublin 24 (Phase 2)* | 9 | Clúid Housing | [5 empty] | Q1-2021
2692 | CALF Construction | South Dublin | Fernwood Green and Maplewood Heights, Tallaght, Dublin (Phase 1) | 17 | Clúid Housing | [5 empty] | Q4-2023
2693 | CALF Construction | South Dublin | Fernwood Green and Maplewood Heights, Tallaght, Dublin (Phase 2) | 23 | Clúid Housing | [5 empty] | Q4-2023
2694 | CALF Turnkey | South Dublin | Finians Way, Newcastle South, Newcastle, Co. Dublin (Phase 1)* | 2 | Clanmil Housing Association Ireland | [5 empty] | Q4-2021
2695 | CALF Turnkey | South Dublin | Finnstown, Lucan, Co. Dublin (Phase 1) | 32 | Respond | [5 empty] | Q3-2021
2696 | CALF Turnkey | South Dublin | Finnstown, Lucan, Co. Dublin (Phase 2) | 38 | Respond | [5 empty] | Q3-2021
2697 | CALF Turnkey | South Dublin | Finnstown, Lucan, Co. Dublin (Phase 3)* | 24 | Respond | [5 empty] | Q4-2021
2698 | CALF Turnkey | South Dublin | Foxwood Barn, Citywest, Dublin 24 (Phase 1)* | 20 | Tuath Housing Association |  |  |  |  | Q4-2023
2699 | CALF Turnkey | South Dublin | Foxwood Barn, Citywest, Dublin 24 (Phase 2)* | 49 | Tuath Housing Association |  |  |  |  | Q4-2023
2700 | CALF Turnkey | South Dublin | Foxwood Barn, Citywest, Dublin 24 (Phase 3)* | 39 | Tuath Housing Association |  |  |  |  | Q4-2023
2701 | CALF Turnkey | South Dublin | Graydon, Newcastle, Co. Dublin (Phase 1)* | 8 | Tuath Housing Association | [5 empty] | Q4-2021
2702 | CALF Turnkey | South Dublin | Hallwell Square, Adamstown, Co. Dublin (Phase 1) | 64 | Oaklee Housing |  |  |  |  | Q2-2022
2703 | CALF Turnkey | South Dublin | Hallwell, Tubber Lane, Adamstown, Co Dublin (Phase 1)* | 45 | The Iveagh Trust | [5 empty] | Q4-2021
2704 | CALF Turnkey | South Dublin | Kingswood, Old Ballymount Road, Tallaght, Dublin 24 (Phase 1)* | 24 | Respond | [5 empty] | Q4-2021
2705 | CALF Turnkey | South Dublin | Mountain Gate, Kiltipper, Dublin 24 (Phase 1)* | 22 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2023
2706 | CALF Turnkey | South Dublin | Palmers Gate, Kennelsfort Road Lower, Dublin 20 (Phase 1)* | 93 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2707 | CALF Turnkey | South Dublin | Parklands, Citywest, Dublin 24 (Phase 1)* | 15 | Tuath Housing Association | [5 empty] | Q3-2023
2708 | CALF Turnkey | South Dublin | Parklands, Citywest, Dublin 24 (Phase 2)* | 14 | Tuath Housing Association | [5 empty] | Q4-2023
2709 | CALF Turnkey | South Dublin | Parklands, Citywest, Dublin 24 (Phase 3)* | 23 | Tuath Housing Association | [5 empty] | Q3-2024
2710 | CALF Turnkey | South Dublin | Parkleigh, Clonburris (Phase 1) | 18 | Respond |  |  |  |  | Q1-2023
2711 | CALF Turnkey | South Dublin | Parkleigh, Clonburris (Phase 2) | 6 | Respond |  |  |  |  | Q1-2023
2712 | CALF Turnkey | South Dublin | Parkleigh, Seven Mills, Clonburris, Dublin 22 (Phase 1)* | 24 | Respond |  |  |  |  | Q1-2023
2713 | CALF Turnkey | South Dublin | Parkleigh, Seven Mills, Clonburris, Dublin 22 (Phase 2)* | 86 | Respond |  |  |  |  | Q1-2023
2714 | CALF Turnkey | South Dublin | Parkleigh, Seven Mills, Clonburris, Dublin 22 (Phase 3)* | 38 | Respond |  |  |  |  | Q1-2023
2715 | CALF Turnkey | South Dublin | Parson's Court, Newcastle, Co Dublin (Phase 1) | 8 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
2716 | CALF Turnkey | South Dublin | Part II Barnoaks, Citywest, Dublin 24 (Phase 1) | 12 | Tuath Housing Association | [5 empty] | Q3-2023
2717 | CALF Turnkey | South Dublin | Phase 2, Aylmer Drive, Aylmer Heath, Newcastle, Co. Dublin (Phase 1)* | 17 | Respond | [5 empty] | Q2-2021
2718 | CALF Turnkey | South Dublin | Sallymills, (Formerly Sallypark), Clondalkin, Dublin 22 (Phase 1)* | 85 | Clúid Housing | [5 empty] | Q4-2022
2719 | CALF Turnkey | South Dublin | San Guida, New Road, Clondalkin, Dublin 22 (Phase 1)* | 21 | Clúid Housing | [5 empty] | Q2-2023
2720 | CALF Turnkey | South Dublin | Scholarstown Road, Rathfarnham, Dublin 16 (Phase 1)* | 14 | Circle Voluntary Housing Association CLG | [5 empty] | Q1-2022
2721 | CALF Turnkey | South Dublin | Somerton Gate, Adamstown, Lucan, Co. Dublin (Phase 1)* | 36 | Clúid Housing | [5 empty] | Q4-2022
2722 | CALF Construction | South Dublin | St. Catherine’s, Knockmore Avenue, Killinarden, Tallaght, Dublin 24 (Phase 1) | 2 | Sophia Housing Association Ltd | [5 empty] | Q2-2022
2723 | CALF Turnkey | South Dublin | Tandy’s Lane, Adamstown, Lucan, Co. Dublin (Phase 1)* | 24 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2724 | CALF Construction | South Dublin | The Weir, Whitestown Way, Tallaght, Dublin 24 (Phase 1) | 81 | Clúid Housing | [5 empty] | Q4-2023
2725 | CALF Turnkey | South Dublin | Whitehall Rd West Perrystown, Dublin 12 (Phase 1) | 13 | Focus Housing Association CLG |  |  |  |  | Q4-2023
2726 | CALF Turnkey | South Dublin | Willowview, Ballyboden Road, Rathfarnham, Dublin 14 (Phase 1)* | 12 | Clúid Housing | [5 empty] | Q2-2021
2727 | CALF Turnkey | Tipperary | Abbey Court Lodges, Old Dublin Road, Nenagh, Co Tipperary (Phase 1) | 12 | Focus Housing Association CLG | [5 empty] | Q1-2022
2728 | CALF Turnkey | Tipperary | Abbey Court Lodges, Old Dublin Road, Nenagh, Co Tipperary (Phase 2) | 4 | Focus Housing Association CLG | [5 empty] | Q2-2022
2729 | CALF Turnkey | Tipperary | Ballygraigue Court, Ballygraigue Road, Nenagh (Phase 1) | 5 | Clúid Housing | [5 empty] | Q2-2022
2730 | CALF Turnkey | Tipperary | Bregawn (formerly Wallers Lott) Cashel, Co Tipperary. (Phase 1)* | 40 | Tuath Housing Association |  |  |  |  | Q1-2022
2731 | CALF Turnkey | Tipperary | Bregawn, Cashel, Co. Tipperary (Phase 1) | 2 | Tuath Housing Association | [5 empty] | Q2-2024
2732 | CALF Turnkey | Tipperary | Coopers Lot, Cashel, Co. Tipperary (Phase 1)* | 12 | Respond |  |  |  |  | Q3-2022
2733 | CALF Turnkey | Tipperary | Coopers Lot, Cashel, Co. Tipperary (Phase 2)* | 16 | Respond |  |  |  |  | Q3-2022
2734 | CALF Turnkey | Tipperary | Coopers Lot, Cashel, Co. Tipperary (Phase 3)* | 16 | Respond |  |  |  |  | Q3-2022
2735 | CALF Turnkey | Tipperary | Dun Lia , Loughtagalla, Thurles, Tipperary (Phase 1) | 61 | Clúid Housing |  |  |  |  | Q1-2024
2736 | CALF Turnkey | Tipperary | Farranlahassery, Cahir, Co. Tipperary (Phase 1)* | 17 | Respond |  |  |  |  | Q3-2023
2737 | CALF Turnkey | Tipperary | Farranlahassery, Cahir, Co. Tipperary (Phase 2)* | 10 | Respond |  |  |  |  | Q3-2023
2738 | CALF Turnkey | Tipperary | Farranlahassery, Cahir, Co. Tipperary (Phase 3)* | 21 | Respond |  |  |  |  | Q3-2023
2739 | CALF Turnkey | Tipperary | Friary Walk, Parkmore, Roscrea, Co. Tipperary (Phase 1)* | 20 | Clúid Housing |  |  |  |  | Q3-2023
2740 | CALF Turnkey | Tipperary | Friary Walk, Parkmore, Roscrea, Co. Tipperary (Phase 2)* | 12 | Clúid Housing |  |  |  |  | Q3-2023
2741 | CALF Turnkey | Tipperary | Glencarrick, Roscrea, Tipperary, (Phase 1) | 26 | Clúid Housing |  |  |  |  | Q2-2024
2742 | CALF Turnkey | Tipperary | Glencarrick, Roscrea, Tipperary, (Phase 2)* | 24 | Clúid Housing |  |  |  |  | Q2-2024
2743 | CALF Turnkey | Tipperary | Rosefield, Dundrum Road, Tipperary Town, Co. Tipperary (Phase 1)* | 16 | Clúid Housing |  |  |  |  | Q1-2024
2744 | CALF Turnkey | Tipperary | Tyone Road, Nenagh, Co. Tipperary (Phase 1)* | 67 | Respond |  |  |  |  | Q2-2024
2745 | CALF Turnkey | Waterford | Brindle Close, Summerfields, Kilbarry, Waterford (Phase 1)* | 37 | Respond | [5 empty] | Q2-2024
2746 | CALF Turnkey | Waterford | Foxwood, Kilbarry, Co. Waterford (Phase 1)* | 9 | Circle Voluntary Housing Association CLG | [5 empty] | Q2-2023
2747 | CALF Turnkey | Waterford | Knightswood, Williamstown Road, Waterford (Phase 1)* | 8 | Circle Voluntary Housing Association CLG | [5 empty] | Q4-2023
2748 | CALF Turnkey | Waterford | Mount Neil, Carrickpherish, Waterford City (Phase 1) | 47 | Tuath Housing Association |  |  |  |  | Q3-2023
2749 | CALF Turnkey | Waterford | Mount Neil, Carrickpherish, Waterford City (Phase 2) | 2 | Tuath Housing Association |  |  |  |  | Q3-2023
2750 | CALF Turnkey | Waterford | Mount Neil, Carrickphierish, Gracedieu, Co. Waterford (Phase 1) | 26 | Circle Voluntary Housing Association CLG | [5 empty] | Q4-2021
2751 | CALF Turnkey | Waterford | Mount Neil, Carrickphierish, Gracedieu, Co. Waterford (Phase 2) | 31 | Circle Voluntary Housing Association CLG | [5 empty] | Q2-2022
2752 | CALF Turnkey | Waterford | Newtown View, Newtown, Tramore, Co. Waterford (Phase 1)* | 7 | Respond | [5 empty] | Q4-2023
2753 | CALF Turnkey | Waterford | Ormonde Drive, Kilbarry, Co. Waterford (Phase 1) | 6 | Oaklee Housing | [5 empty] | Q4-2022
2754 | CALF Turnkey | Waterford | Ormonde Drive, Kilbarry, Co. Waterford (Phase 2)* | 7 | Oaklee Housing | [5 empty] | Q4-2022
2755 | CALF Turnkey | Waterford | Ormonde Drive, Kilbarry, Co. Waterford (Phase 3) | 2 | Oaklee Housing | [5 empty] | Q4-2022
2756 | CALF Turnkey | Waterford | Slí na Coille, Tramore, Co Waterford (Phase 1)* | 27 | Clúid Housing | [5 empty] | Q3-2022
2757 | CALF Turnkey | Waterford | Strand Hill, Tramore, Co Waterford (Phase 1) | 11 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2024
2758 | CALF Turnkey | Waterford | Strand Hill, Tramore, Co Waterford (Phase 2)* | 14 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2022
2759 | CALF Turnkey | Westmeath | Athlone Road, Moate, Co. Westmeath (Phase 1)* | 14 | Oaklee Housing | [5 empty] | Q2-2021
2760 | CALF Turnkey | Westmeath | Bower Hill, Lower Road, Athlone, Co. Westmeath (Phase 1)* | 15 | Clúid Housing | [5 empty] | Q4-2023
2761 | CALF Turnkey | Westmeath | Charlestown, Mullingar (Phase 1)* | 12 | Respond | [5 empty] | Q4-2023
2762 | CALF Turnkey | Westmeath | Charlestown, Mullingar (Phase 2)* | 21 | Respond |  |  |  |  | Q4-2021
2763 | CALF Turnkey | Westmeath | Charlestown, Mullingar (Phase 3)* | 24 | Respond |  |  |  |  | Q4-2021
2764 | CALF Turnkey | Westmeath | Charlestown, Mullingar (Phase 4) | 42 | Respond |  |  |  |  | Q4-2021
2765 | CALF Turnkey | Westmeath | Coill Rua, Mullingar, Co. Westmeath (Phase 2)* | 23 | Clúid Housing | [5 empty] | Q1-2021
2766 | CALF Turnkey | Westmeath | Coill Rua, Mullingar, Co. Westmeath (Phase 3) | 8 | Clúid Housing | [5 empty] | Q2-2021
2767 | CALF Turnkey | Westmeath | Dún Mhic Coluim, Ashe Road, Mullingar, Co. Westmeath (formerly Ashe Road) (Phase 1)* | 18 | Clúid Housing |  |  |  |  | Q2-2021
2768 | CALF Construction | Westmeath | Farran, Mullingar, Co. Westmeath (Phase 1) | 10 | Tuath Housing Association | [5 empty] | Q3-2021
2769 | CALF Turnkey | Westmeath | Garran Gael, Kinnegad, Westmeath (Phase 1)* | 24 | Tuath Housing Association | [5 empty] | Q4-2022
2770 | CALF Turnkey | Westmeath | Gracefields, Drumaconn, Co. Westmeath (Phase 1)* | 11 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2771 | CALF Turnkey | Westmeath | Gracefields, Drumaconn, Co. Westmeath (Phase 2)* | 16 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2772 | CALF Turnkey | Westmeath | Phase 1, Dun an Ri, Coosan, Coosan, Athlone, Co. Westmeath (Phase 1)* | 15 | Respond |  |  |  |  | Q4-2023
2773 | CALF Turnkey | Westmeath | Phase 1, Dun an Ri, Coosan, Coosan, Athlone, Co. Westmeath (Phase 2)* | 35 | Respond |  |  |  |  | Q4-2023
2774 | CALF Turnkey | Westmeath | Rahanine, Rochfortbridge, Co Westmeath (Phase 1)* | 12 | Tuath Housing Association | [5 empty] | Q2-2021
2775 | CALF Turnkey | Westmeath | Royal Canal, Ardmore Road, Mullingar, Co. Westmeath (Phase 1) | 4 | Tuath Housing Association | [5 empty] | Q1-2021
2776 | CALF Turnkey | Westmeath | Royal Canal, Ardmore Road, Mullingar, Co. Westmeath (Phase 2) | 4 | Tuath Housing Association | [5 empty] | Q2-2022
2777 | CALF Turnkey | Westmeath | Springfield Cottages, Mullingar, Co. Westmeath (Phase 1)* | 13 | Clúid Housing |  |  |  |  | Q4-2021
2778 | CALF Turnkey | Westmeath | Weavers Place, Weavers Row, Moate, Co Westmeath (Phase 1) | 6 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
2779 | CALF Turnkey | Wexford | 67 units, Coolcotts, Wexford (Barr An Aird, Coolcotts) (Phase 1)* | 67 | Clúid Housing | [5 empty] | Q4-2022
2780 | CALF Turnkey | Wexford | 9 Units, Gleann an Ghairdin, Gorey, Co. Wexford (Phase 1) | 9 | Tuath Housing Association | [5 empty] | Q2-2021
2781 | CALF Turnkey | Wexford | Beechfield, Clonard, Wexford Town, Co. Wexford (Phase 1)* | 50 | Clúid Housing |  |  |  |  | Q1-2024
2782 | CALF Turnkey | Wexford | Bridgemeadow, Enniscorthy, Co. Wexford (Phase 1)* | 12 | Clúid Housing | [5 empty] | Q2-2023
2783 | CALF Turnkey | Wexford | Coill na Giuise, Ballyteegan Road, Gorey, Co. Wexford, (Phase 1)* | 86 | Clúid Housing |  |  |  |  | Q1-2024
2784 | CALF Turnkey | Wexford | Cuil na Dara, Coolcotts, Wexford (Phase 1)* | 25 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2785 | CALF Turnkey | Wexford | Fearach Cnoic, Milehouse, Enniscorthy, Co. Wexford (Phase 1) | 17 | Circle Voluntary Housing Association CLG |  |  |  |  | Q4-2023
2786 | CALF Turnkey | Wexford | Fearach Cnoic, Milehouse, Enniscorthy, Co. Wexford (Phase 2) | 20 | Circle Voluntary Housing Association CLG |  |  |  |  | Q4-2023
2787 | CALF Turnkey | Wexford | Forgelands, Enniscorthy Co. Wexford. (Phase 1) | 10 | Tuath Housing Association | [5 empty] | Q3-2022
2788 | CALF Turnkey | Wexford | Forgelands, Old Forge Road, Milehouse Road, Enniscorthy, Co. Wexford (Phase 1)* | 18 | Tuath Housing Association | [5 empty] | Q3-2021
2789 | CALF Turnkey | Wexford | Forthview, Murntown Upper, Co Wexford (Phase 1)* | 23 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2023
2790 | CALF Turnkey | Wexford | Forthview, Murntown Upper, Co Wexford, Phase 2 (Phase 1)* | 17 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q1-2024
2791 | CALF Turnkey | Wexford | Gleann an Ghairdin, Gorey, Co Wexford (Phase 1) | 16 | Tuath Housing Association | [5 empty] | Q4-2022
2792 | CALF Turnkey | Wexford | Gleann an Ghairdin, Gorey, Co Wexford (Phase 2) | 8 | Tuath Housing Association | [5 empty] | Q3-2023
2793 | CALF Construction | Wexford | Hewitsland, New Ross, County Wexford (Phase 1) | 48 | Clúid Housing |  |  |  | Q4-2023
2794 | CALF Turnkey | Wexford | Kerlogue Manor, Roxborough, Drinagh, Wexford (Phase 3) | 16 | Tuath Housing Association | [5 empty] | Q1-2021
2795 | CALF Turnkey | Wexford | Kerlogue Manor, Roxborough, Drinagh, Wexford (Phase 4)* | 27 | Tuath Housing Association | [5 empty] | Q2-2021
2796 | CALF Turnkey | Wexford | Mill Heights, Castlebridge, Wexford (Phase 1) | 12 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2021
2797 | CALF Turnkey | Wexford | Mill Heights, Castlebridge, Wexford (Phase 2)* | 13 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q1-2022
2798 | CALF Turnkey | Wexford | Moongate, Townspark, Co Wexford (Phase 1)* | 17 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2799 | CALF Turnkey | Wexford | Moongate, Townspark, Co Wexford (Phase 2)* | 21 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2023
2800 | CALF Turnkey | Wexford | Old Forge Road, Milehouse Road, Enniscorthy, Co. Wexford (Phase 3)* | 8 | Tuath Housing Association | [5 empty] | Q1-2021
2801 | CALF Turnkey | Wexford | Old Forge Road, Milehouse Road, Enniscorthy, Co. Wexford (Phase 4)* | 8 | Tuath Housing Association | [5 empty] | Q2-2021
2802 | CALF Turnkey | Wexford | Pairc Na Bearna, Enniscorthy, Co Wexford. (Phase 1) | 5 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2024
2803 | CALF Turnkey | Wexford | Pairc na Dara, Coolcotts, Wexford, Co. Wexford (Phase 1)* | 15 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2021
2804 | CALF Turnkey | Wexford | Pairc na Dara, Coolcotts, Wexford, Co. Wexford (Phase 2) | 19 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2021
2805 | CALF Turnkey | Wexford | Páirc na gCon, Greenville Lane, Enniscorthy, Co. Wexford (Phase 1)* | 16 | Clúid Housing | [5 empty] | Q3-2021
2806 | CALF Turnkey | Wexford | Páirc na gCon, Greenville Lane, Enniscorthy, Co. Wexford (Phase 2)* | 14 | Clúid Housing | [5 empty] | Q3-2021
2807 | CALF Turnkey | Wexford | Páirc na gCon, Greenville Lane, Enniscorthy, Co. Wexford (Phase 3) | 22 | Clúid Housing | [5 empty] | Q4-2021
2808 | CALF Turnkey | Wexford | Pairc na Greine, Coolcots, Wexford, 1-24 Pairc na Greine, Coolcots, Wexford (Phase 1) | 24 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2022
2809 | CALF Turnkey | Wexford | Ramstown Phase 3, Ramstown, Gorey, Co Wexford. (Phase 1)* | 30 | Tuath Housing Association |  |  |  |  | Q3-2023
2810 | CALF Turnkey | Wexford | Ramstown, Gorey, Wexford (Phase 1) | 24 | Tuath Housing Association | [5 empty] | Q4-2022
2811 | CALF Turnkey | Wexford | Ramstown, Gorey, Wexford (Phase 2) | 20 | Tuath Housing Association | [5 empty] | Q3-2023
2812 | CALF Turnkey | Wexford | The Close , Clonattin Village, Goreybridge, Courtown Wexford (Phase 1)* | 17 | Tuath Housing Association |  |  |  |  | Q3-2023
2813 | CALF Turnkey | Wexford | The Close , Clonattin Village, Goreybridge, Courtown Wexford (Phase 2)* | 6 | Tuath Housing Association |  |  |  |  | Q3-2023
2814 | CALF Turnkey | Wexford | Tobar Mhuire, Creagh, Gorey, Wexford (Phase 1)* | 17 | Clúid Housing | [5 empty] | Q4-2022
2815 | CALF Turnkey | Wexford | Tobar Muire Place, Gorey, Co. Wexford (Phase 2) (Phase 1)* | 5 | Clúid Housing | [5 empty] | Q3-2023
2816 | CALF Turnkey | Wexford | Whiterock Hill, Wexford, Co. Wexford (Phase 1)* | 40 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2021
2817 | CALF Turnkey | Wicklow | Adelaide Villas Apartments, Adelaide Apartments, St Laurence’s Terrace, Bray, Co. Wicklow (Phase 1)* | 18 | Respond |  |  |  |  | Q2-2021
2818 | CALF Turnkey | Wicklow | Albert Place , Albert Avenue, Bray, Co. Wicklow (Phase 1)* | 3 | Respond |  |  |  |  | Q4-2023
2819 | CALF Turnkey | Wicklow | Aldborough Hall, Hawkins Wood, Greystones, Co. Wicklow (Phase 1) | 84 | Tuath Housing Association | [5 empty] | Q4-2022
2820 | CALF Turnkey | Wicklow | Aldborough Manor, Bawnogues, Baltinglass, Co Wicklow (Phase 1) | 12 | Tuath Housing Association |  |  |  |  | Q2-2024
2821 | CALF Turnkey | Wicklow | Altidore Gardens, Newtownmountkennedy, Co Wicklow (Phase 1) | 28 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
2822 | CALF Turnkey | Wicklow | Altidore Gardens, Newtownmountkennedy, Co Wicklow (Phase 2) | 28 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q3-2023
2823 | CALF Turnkey | Wicklow | Avondale Grange, Ballygannon, Rathdrum, Co. Wicklow (Phase 1)* | 36 | Respond | [5 empty] | Q4-2023
2824 | CALF Turnkey | Wicklow | Chancel Way, Newcastle, Co. Wicklow (Phase 1)* | 16 | Co - Operative Housing Ireland Society Limited |  |  |  |  | Q2-2024
2825 | CALF Turnkey | Wicklow | Fairfield Court, Fairfield, New Road, Greystones, Co. Wicklow (Phase 1)* | 8 | Oaklee Housing |  |  |  |  | Q1-2023
2826 | CALF Turnkey | Wicklow | Fairgreen Manor, Dunlavin, Co. Wicklow (Phase 1)* | 40 | Circle Voluntary Housing Association CLG | [5 empty] | Q3-2021
2827 | CALF Turnkey | Wicklow | Foggie Field, Kilruddery,Bray, Co. Wicklow (Phase 1)* | 15 | Tuath Housing Association |  |  |  |  | Q2-2023
2828 | CALF Turnkey | Wicklow | Hawkins Wood, Greystones and Archers Wood, Delgany, Wicklow (Phase 1)* | 14 | Tuath Housing Association | [5 empty] | Q4-2022
2829 | CALF Turnkey | Wicklow | Hawkins Wood, Greystones and Archers Wood, Delgany, Wicklow (Phase 2)* | 30 | Tuath Housing Association | [5 empty] | Q4-2022
2830 | CALF Turnkey | Wicklow | Hawkins Wood, Greystones and Archers Wood, Delgany, Wicklow (Phase 3)* | 16 | Tuath Housing Association | [5 empty] | Q4-2022
2831 | CALF Turnkey | Wicklow | Heatherside, Vale Road, Arklow (Phase 1) | 11 | Tuath Housing Association | [5 empty] | Q2-2022
2832 | CALF Turnkey | Wicklow | Heatherside, Vale Road, Arklow (Phase 2) | 12 | Tuath Housing Association | [5 empty] | Q3-2022
2833 | CALF Turnkey | Wicklow | Heatherside, Vale Road, Arklow (Phase 3) | 17 | Tuath Housing Association | [5 empty] | Q4-2022
2834 | CALF Turnkey | Wicklow | Heatherside, Vale Road, Arklow (Phase 4) | 9 | Tuath Housing Association | [5 empty] | Q1-2023
2835 | CALF Turnkey | Wicklow | Heatherside, Vale Road, Arklow (Phase 5) | 10 | Tuath Housing Association | [5 empty] | Q1-2023
2836 | CALF Turnkey | Wicklow | Heatherside, Vale Road, Arklow (Phase 6) | 7 | Tuath Housing Association | [5 empty] | Q3-2023
2837 | CALF Turnkey | Wicklow | Heatherside, Vale Road, Arklow (Phase 7)* | 22 | Tuath Housing Association | [5 empty] | Q3-2023
2838 | CALF Turnkey | Wicklow | Heatherside, Vale Road, Arklow, Co. Wicklow (Phase 1) | 15 | Tuath Housing Association | [5 empty] | Q4-2021
2839 | CALF Turnkey | Wicklow | Heatherside, Vale Road, Arklow, Co. Wicklow (Phase 2) | 10 | Tuath Housing Association | [5 empty] | Q1-2022
2840 | CALF Turnkey | Wicklow | Meadow Gate, Marlton Road, Co Wicklow (Phase 1)* | 6 | Tuath Housing Association | [5 empty] | Q4-2022
2841 | CALF Turnkey | Wicklow | Oak Springs, Rathdrum, County Wicklow (Phase 1)* | 5 | Tuath Housing Association | [5 empty] | Q3-2022
2842 | CALF Turnkey | Wicklow | Phase 2 Foggie Field, Kilruddery,Bray, Co. Wicklow (Phase 1) | 10 | Tuath Housing Association |  |  |  |  | Q2-2023
2843 | CALF Turnkey | Wicklow | Phase 2, Southern Cross, Bray, Co. Wicklow (Phase 1) | 80 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2022
2844 | CALF Turnkey | Wicklow | Phase 3, Southern Cross, Bray, Co. Wicklow (Phase 1)* | 80 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2023
2845 | CALF Turnkey | Wicklow | Rathcoran House, Baltinglass, Co. Wicklow (Phase 2)* | 24 | Respond | [5 empty] | Q2-2021
2846 | CALF Turnkey | Wicklow | Rathcoran House, Baltinglass, Co. Wicklow (Phase 3) | 16 | Respond | [5 empty] | Q3-2021
2847 | CALF Turnkey | Wicklow | Sorrel Woods, Blessington, Co. Wicklow (Phase 1)* | 16 | Tuath Housing Association |  |  |  |  | Q4-2023
2848 | CALF Turnkey | Wicklow | Southern Cross, Bray, Co. Wicklow (Phase 1)* | 30 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q2-2022
2849 | CALF Turnkey | Wicklow | Southern Cross, Bray, Co. Wicklow (Phase 2)* | 18 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q3-2022
2850 | CALF Turnkey | Wicklow | The Rectory (formerly The Old Rectory), Blessington, Co. Wicklow (Phase 1)* | 46 | Co - Operative Housing Ireland Society Limited | [5 empty] | Q4-2023
2851 | CALF Turnkey | Wicklow | Ushers Glen, Ashford, Co. Wicklow (Phase 1) | 51 | Clúid Housing | [5 empty] | Q3-2023
2852 | CALF Turnkey | Wicklow | Ushers Glen, Ashford, Co. Wicklow (Phase 2)* | 22 | Clúid Housing | [5 empty] | Q4-2023
2853 | CALF Turnkey | Wicklow | Ushers Glen, Ashford, Co. Wicklow (Phase 3)* | 26 | Clúid Housing | [5 empty] | Q4-2023
2854 | CALF Turnkey | Wicklow | Ushers Glen, Ashford, Co. Wicklow (Phase 4)* | 18 | Clúid Housing | [5 empty] | Q4-2023
2855 | CALF Turnkey | Wicklow | Vartry Wood, Ashford, Co. Wicklow (Phase 1)* | 16 | Clúid Housing | [5 empty] | Q4-2022
2856 | PUBLIC PRIVATE PARTNERSHIP (Bundle 1) | Dublin City | Ayrfield, Malahide Road | 150 | *N/A | [5 empty] | Q2-2021
2857 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Clare | Shannon East (Phase 1) | 20 | *N/A | [5 empty] | Q2-2021
2858 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Clare | Shannon East (Phase 2) | 31 | *N/A | [5 empty] | Q3-2021
2859 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Cork County | The Miles, Clonakilty (Phase 1) | 20 | *N/A | [5 empty] | Q2-2021
2860 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Cork County | The Miles, Clonakilty (Phase 2) | 32 | *N/A | [5 empty] | Q4-2021
2861 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Cork County | Poundhill, Skibbereen (Phase 1) | 35 | *N/A | [5 empty] | Q2-2021
2862 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Cork County | Poundhill, Skibbereen (Phase 2) | 15 | *N/A | [5 empty] | Q4-2021
2863 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Cork County | Oakwood, Macroom (Phase 1) | 37 | *N/A | [5 empty] | Q2-2021
2864 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Cork County | Oakwood, Macroom (Phase 2) | 13 | *N/A | [5 empty] | Q3-2021
2865 | PUBLIC PRIVATE PARTNERSHIP (Bundle 6) | Cork County | Broomfield, Midleton | 70 | N/A | Q1-2023
2866 | PUBLIC PRIVATE PARTNERSHIP (Bundle 6) | Cork County | Stag Park, Mitchelstown | 50 | N/A | Q1-2023
2867 | PUBLIC PRIVATE PARTNERSHIP (Bundle 6) | Cork County | Station Road, Carrigtwohill | 50 | N/A | Q1-2023
2868 | PUBLIC PRIVATE PARTNERSHIP (Bundle 6) | Cork County | The Slip, Bantry | 50 | N/A | Q1-2023
2869 | PUBLIC PRIVATE PARTNERSHIP (Bundle 5) | DLR | Balally, Dublin 16 | 62 | N/A |  | Q2 2024
2870 | PUBLIC PRIVATE PARTNERSHIP (Bundle 5) | DLR | Lambs Cross, Sandyford, Dublin 18. | 37 | N/A | Q2-2022
2871 | PUBLIC PRIVATE PARTNERSHIP (Bundle 3) | Dublin City | Ready Mix Site, East Wall, Dublin 3 | 68 | *N/A |  |  | Q4-2022
2872 | PUBLIC PRIVATE PARTNERSHIP (Bundle 3) | Dublin City | Shangan Road, Ballymun, Dublin 9* | 93 | *N/A |  |  | Q4-2022
2873 | PUBLIC PRIVATE PARTNERSHIP (Bundle 3) | Dublin City | Collins Avenue, Whitehall, Dublin 9 | 83 | *N/A |  |  | Q4-2022
2874 | PUBLIC PRIVATE PARTNERSHIP (Bundle 4) | Dublin City | Collins Avenue, Bring Centre, Dublin 9 | 106 | N/A |  |  | Q3 2024
2875 | PUBLIC PRIVATE PARTNERSHIP (Bundle 5) | Dublin City | Marrowbone Lane/Forbes Lane (Depot) | 108 | N/A |  | Q2 2024
2876 | PUBLIC PRIVATE PARTNERSHIP (Bundle 5) | Dublin City | Basin View Flats | 171 | N/A |  | Q2 2024
2877 | PUBLIC PRIVATE PARTNERSHIP (Bundle 5) | Dublin City | Ballymun - Site 5: Main Street to the south of Santry Cross Sites 15,16, 17 & 18: Balcurris | 277 | N/A |  | Q3 2024
2878 | PUBLIC PRIVATE PARTNERSHIP (Bundle 4) | Dublin City | Croke Villas | 66 | N/A |  |  | Q3 2024
2879 | PUBLIC PRIVATE PARTNERSHIP (Bundle 4) | Dublin City | Church of the Annunciation, Finglas | 110 | N/A |  |  | Q32024
2880 | PUBLIC PRIVATE PARTNERSHIP (Bundle 4) | Dublin City | Stanley Street (Depot) | 167 | N/A |  |  | Q3 2024
2881 | PUBLIC PRIVATE PARTNERSHIP (Bundle 4) | Dublin City | Wellmount Road, Cardiffsbridge Road, Finglas | 77 | N/A |  |  | Q3 2024
2882 | PUBLIC PRIVATE PARTNERSHIP (Bundle 5) | Dublin City | Barry Road, Finglas, Dublin 11 | 74 | N/A |  | Q2 2024
2883 | PUBLIC PRIVATE PARTNERSHIP (Bundle 5) | Dublin City | Cherry Orchard Avenue, Ballyfermot, Dublin 10 | 123 | N/A |  | Q2 2024
2884 | PUBLIC PRIVATE PARTNERSHIP (Bundle 7) | Dublin City | Carton Lands, Ballymun | 110 | N/A | Q4-2023
2885 | PUBLIC PRIVATE PARTNERSHIP (Bundle 7) | Dublin City | Ballymun, Silloge Road LAP Site 2 | 170 | N/A | Q4-2023
2886 | PUBLIC PRIVATE PARTNERSHIP (Bundle 7) | Dublin City | Belcamp Lane, Darndale | 170 | N/A | Q4-2023
2887 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Galway City | Ballyburke (Phase 1) | 56 | *N/A | [5 empty] | Q2-2021
2888 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Galway City | Ballyburke (Phase 2) | 18 | *N/A | [5 empty] | Q3-2021
2889 | PUBLIC PRIVATE PARTNERSHIP (Bundle 7) | Galway County | Balgaddy Road, Tuam | 60 | N/A | Q4-2023
2890 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Kildare | Butterstream, Clane | 77 | *N/A | [5 empty] | Q4-2021
2891 | PUBLIC PRIVATE PARTNERSHIP (Bundle 3) | Kildare | Ardrew, Athy, Co. Kildare | 73 | *N/A |  |  | Q4-2022
2892 | PUBLIC PRIVATE PARTNERSHIP (Bundle 4) | Kildare | Oldtown Mill, Celbridge | 60 | N/A |  |  | Q3 2024
2893 | PUBLIC PRIVATE PARTNERSHIP (Bundle 4) | Kildare | Collaghknock Glebe, Kildare Town | 99 | N/A |  |  | Q3 2024
2894 | PUBLIC PRIVATE PARTNERSHIP (Bundle 6) | Kildare | Rathaskar Road, Naas | 80 | N/A | Q1-2023
2895 | PUBLIC PRIVATE PARTNERSHIP (Bundle 6) | Kildare | Rickardstown, Newbridge | 80 | N/A | Q1-2023
2896 | PUBLIC PRIVATE PARTNERSHIP (Bundle 7) | Limerick | Toppins Field | 67 | N/A | Q4-2023
2897 | PUBLIC PRIVATE PARTNERSHIP (Bundle 5) | Louth | Ballymakenny East | 130 | N/A |  | Q2 2024
2898 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Roscommon | The Walk, Roscommon Town | 53 | *N/A | [5 empty] | Q2-2021
2899 | PUBLIC PRIVATE PARTNERSHIP (Bundle 3) | Sligo | Rathellen, Finisklin, Co. Sligo | 63 | *N/A |  |  | Q4-2022
2900 | PUBLIC PRIVATE PARTNERSHIP (Bundle 5) | South Dublin | Clonburris | 117 | N/A |  | Q2 2024
2901 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Waterford | Slievekeale, Waterford City (Phase 1) | 24 | *N/A | [5 empty] | Q2-2021
2902 | PUBLIC PRIVATE PARTNERSHIP (Bundle 2) | Waterford | Slievekeale, Waterford City (Phase 2) | 34 | *N/A | [5 empty] | Q3-2021
2903 | PUBLIC PRIVATE PARTNERSHIP (Bundle 7) | Wexford | Hospital Hill, Bunclody | 65 | N/A | Q4-2023
2904 | PUBLIC PRIVATE PARTNERSHIP (Bundle 3) | Wicklow | Burgage More, Blessington, Co. Wicklow | 106 | *N/A |  |  | Q4-2022
2905 | PUBLIC PRIVATE PARTNERSHIP (Bundle 5) | Wicklow | Burnaby, Greystones | 132 | N/A |  | Q2 2024
2906 | PUBLIC PRIVATE PARTNERSHIP (Bundle 6) | Wicklow | Tinahask, Arklow | 100 | N/A | Q1-2023